## PMR
PROVINCE OF DAVAO DE ORO | [11 empty] | Procurement Monitoring Report as of June/28/2024
[5 empty] | Actual Procurement Activities | [20 empty] | ABC (PhP) |  |  | Contract Cost (PhP) |  |  |  |  | Date of Receipt of Invitation
Code (PAP) | Procurement Project | PMO/End-User | Is this an Early Procurement Activity? | Mode of Procurement | Pre-Proc Conference | Ads/Post of IB | Ave. No. of Days to Commence Procurement (Pre-Proc to Posting of IB) (i.3) | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Average No. of Days to open bid proposals (Posting of IB to Opening of Bids) (i.4) | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Accumulated Days in Evaluation of Bids (Opening of Bids to Post Qua) | Average Number of Days to Recommend Award (Opening of Bids to Recommend Award) (i.5) | Average Number of Days to Conclude Procurement (IB to BAC Reso) (i.6) | Notice of Award | Contract Signing | Notice to Proceed | Average Number of Days to Issue Notice to Proceed (NOA to NTP) (i.7) | Average Days from (Posting of IB to NTP) (i.8) | Delivery/ Completion | Inspection & Acceptance | Source of Funds | Total | MOOE | CO | Total2 | MOOE2 | CO3 | % Variance | List of Invited Observers | Pre-bid Conf4 | Eligibility Check5 | Sub/ Open of Bids6 | Bid Evaluation7 | Post Qual8 | Delivery/ Completion/ Acceptance (If applicable) | Remarks (Explaining changes from the APP) | Column1 | Column2
COMPLETED PROCUREMENT ACTIVITIES | [31 empty] | -
23-C0756 | COMPUTER SUPPLIES | PGSO | No | NP-53.1 Two Failed Biddings | 2023-11-07 | 2023-12-21 | 44 | N/A | 2024-01-23 | 2024-01-23 | 33 | N/A | N/A | 2024-01-24 |  | 1 | 34 | 2024-01-25 | 2024-02-07 | 2024-02-26 | 32 | 67 | 2024-05-20 | 2024-05-20 | Government of the Philipppiens | 369476.76 |  | 369476.76 | 361670 |  | 361670 | 0.021129 | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed | FALSE | FALSE
23-5446 | SPAREPARTS | PDRRMO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-12-05 | 2023-12-12 |  | N/A | 2024-01-09 | 2024-01-09 |  | N/A | N/A | 2024-01-11 |  |  |  | N/A | 2024-02-06 | 2024-02-13 |  |  | 2024-02-13 | 2024-02-13 | Government of the Philipppiens | 38750 |  | 38750 | 38750 |  | 38750 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-3966 | 1 LOT CONSTRUCTION OF CENTER ISLAND WITH SOLAR LIGHTS AT BRGY. POBLACION, COMPOSTELA (180 In.m. Center Island with 12 units of Solar light | PEO | No | Competitive Bidding | 2023-09-19 | 2023-10-16 | 27 | 2023-11-07 | 2023-11-15 | 2023-11-15 | 30 | 2023-11-15 | 2024-01-04 | 2024-01-11 | 50 | 57 | 87 | 2024-01-15 | 2024-01-18 | 2024-01-19 | 4 | 95 | N/A | N/A | Government of the Philipppiens | 2876333.74 |  | 2876333.74 | 2871777.81 |  | 2871777.81 | 0.0015839 | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-11-06 | 2023-11-10 | 2023-11-10 | 2023-11-10 | 2023-11-10 | N/A | Completed | FALSE | FALSE
23-2001 | IMPROVEMENT OF DAVAO DE ORO PROVINCIAL HOSPITAL, PANTUKAN (Completion of Material Recovery Facility) | PEO | No | Competitive Bidding | 2023-04-04 | 2023-11-21 | 231 | 2023-11-29 | 2023-12-12 | 2023-12-12 | 21 | 2023-12-12 | 2024-01-04 | 2024-01-11 | 23 | 30 | 51 | 2024-01-15 | 2024-01-18 | 2024-01-19 | 4 | 59 | N/A | N/A | Government of the Philipppiens | 2299236.05 |  | 2299236.05 | 2278330.67 |  | 2278330.67 | 0.0090923 | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-11-20 | 2024-12-11 | 2024-12-11 | 2024-12-11 | 2024-12-11 | N/A | Completed | FALSE | FALSE
24-0075 | OFFICE EQUIPMENT | PACCO | No | NP-53.9 - Small Value Procurement | N/A | 2024-01-27 |  | N/A | 2024-01-31 | 2024-01-31 |  | N/A | N/A | 2024-02-06 |  |  |  | 2024-02-12 | 2024-02-14 | 2024-02-19 |  |  | 2024-03-06 | 2024-03-06 | Government of the Philipppiens | 7800 | 7800 |  | 7800 | 7800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed | FALSE | FALSE
24-0001 | FOOD/CATERING SERVICES | PGO-BAC | No | NP-53.9 - Small Value Procurement | N/A | 2024-01-27 |  | N/A | 2024-01-31 | 2024-01-31 | 4 | N/A | N/A | 2024-02-06 |  | 6 | 10 | 2024-02-12 | 2024-02-13 | 2024-02-19 | 7 | 23 | 2024-05-14 | 2024-05-14 | Government of the Philipppiens | 74520 | 74520 |  | 72900 | 72900 |  | 0.021739 | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed | FALSE | FALSE
24-0094 | OTHER SUPPLIES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-01-27 |  | N/A | 2024-01-31 | 2024-01-31 | 4 | N/A | N/A | 2024-02-06 |  | 6 | 10 | 2024-02-12 | 2024-02-13 | 2024-02-19 | 7 | 23 | 2024-03-03 | 2024-03-03 | Government of the Philipppiens | 6600 | 6600 |  | 6600 | 6600 |  | 0 | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed | FALSE | FALSE
24-0080 | OTHER SUPPLIES | PACCO | No | NP-53.9 - Small Value Procurement | N/A | 2024-01-27 |  | N/A | 2024-01-31 | 2024-01-31 |  | N/A | N/A | 2024-02-06 |  |  |  | 2024-02-12 | 2024-02-14 | 2024-02-19 |  |  | 2024-03-19 | 2024-03-19 | Government of the Philipppiens | 109800 | 109800 |  | 109800 | 109800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0093 | FOOD SUPPLIES | PGO | No | NP-53.9 - Small Value Procurement | 2024-01-23 | 2024-01-25 | 2 | N/A | 2024-01-31 | 2024-01-31 | 6 | N/A | N/A | 2024-02-06 |  | 6 | 12 | 2024-02-12 | 2024-02-12 | 2024-02-15 | 3 | 21 | 2024-02-16 | 2024-02-16 | Government of the Philipppiens | 451825 |  | 451825 | 418500 |  | 418500 | 0.073756 | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed | FALSE | FALSE
23-C0918 | STRETCHER BED FOR THE USE OF DDOPH-MARAGUSAN | PEEMO | No | Competitive Bidding | N/A | 2024-01-08 |  | N/A | 2024-01-22 | 2024-01-22 | 14 | 2024-01-22 | 2024-01-24 | 2024-02-06 | 2 | 15 | 29 | 2024-02-08 | 2024-02-21 | 2024-03-14 | 35 | 66 | 2024-03-18 | 2024-03-18 | Government of the Philipppiens | 360000 |  | 360000 | 244668 |  | 244668 | 0.32037 | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-01-02 | 2024-01-02 | 2024-01-02 | 2024-01-02 | N/A | Completed | FALSE | FALSE
23-3195 | IMPROVEMENT OF DAVAO DE ORO PROVINCIAL HOSPITAL, MONTEVISTA (Construction of Emergency Room Extension & Canopy | PEO | No | Competitive Bidding | 2024-10-17 | 2024-12-04 | 48 | 2023-12-12 | 2024-01-09 | 2024-01-09 | -330 | 2024-01-09 | 2024-01-26 | 2024-02-08 | 17 | 30 | -300 | 2024-02-13 | 2024-02-15 | 2024-02-19 | 6 | -289 | N/A | N/A | Government of the Philipppiens | 1400 |  | 1400 | 1400 |  | 1400 | 0 | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-12-11 | 2024-01-02 | 2024-01-02 | 2024-01-02 | N/A | N/A | Completed | FALSE | FALSE
23-4586 | COMPLETION OF MULTI-PURPOSE BUILDING (PGSO) | PEO | No | Competitive Bidding | 2023-11-15 | 2024-12-04 | 385 | 2023-12-12 | 2024-01-09 | 2024-01-09 | -330 | 2024-01-09 | 2024-01-26 | 2024-02-08 | 17 | 30 | -300 | 2024-02-13 | 2024-02-15 | 2024-02-19 | 6 | -289 | N/A | N/A | Government of the Philipppiens | 6428465.39 |  | 6428465.39 | 6399080.07 |  | 6399080.07 | 0.0045711 | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-12-11 | 2024-01-02 | 2024-01-02 | 2024-01-02 | 2024-01-02 | N/A | Completed | FALSE | FALSE
24-0814 | RICE (WELL MILLED - 50KG/SACK) | PDRRMO | No | NP-53.2 Emergency Cases | 2024-01-31 | 2024-02-02 |  | N/A | 2024-02-06 | 2024-02-06 |  | N/A | N/A | 2024-02-06 |  |  |  | 2024-02-06 | 2024-02-06 | 2024-02-06 |  |  | 2024-02-08 | 2024-02-08 | Government of the Philipppiens | 5016000 |  | 5016000 | 5016000 |  | 5016000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0815 | RICE (WELL MILLED - 50KG/SACK) | PDRRMO | No | NP-53.2 Emergency Cases | N/A | 2024-01-31 |  | N/A | 2024-01-31 | 2024-01-31 |  | N/A | N/A | 2024-02-01 |  |  |  | 2024-02-01 | 2024-02-01 | 2024-02-01 |  |  | 2024-02-04 | 2024-02-04 | Government of the Philipppiens | 1749000 |  | 1749000 | 1749000 |  | 1749000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0074 | JANITORIAL SUPPLIES/HOUSEKEEPING | PACCO | No | NP-53.9 - Small Value Procurement | N/A | 2024-01-27 |  | N/A | 2024-01-31 | 2024-01-31 | 4 | N/A | N/A | 2024-02-06 |  | 6 | 10 | 2024-02-12 | 2024-02-14 | 2024-02-19 | 7 | 23 | 2024-02-23 | 2024-02-23 | Government of the Philipppiens | 16920 | 16920 |  | 16450 | 16450 |  | 0.027778 | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed | FALSE | FALSE
24-0022 | JANITORIAL SUPPLIES/HOUSEKEEPING | PTO | No | NP-53.9 - Small Value Procurement | N/A | 2024-01-27 |  | N/A | 2024-01-31 | 2024-01-31 | 4 | N/A | N/A | 2024-02-06 |  | 6 | 10 | 2024-02-12 | 2024-02-19 | 2024-02-19 | 7 | 23 | 2024-02-28 | 2024-02-28 | Government of the Philipppiens | 27088 | 27088 |  | 26508 | 26508 |  | 0.021412 | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed | FALSE | FALSE
24-0096 | JANITORIAL SUPPLIES/HOUSEKEEPING | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-01-27 |  | N/A | 2024-01-31 | 2024-01-31 | 4 | N/A | N/A | 2024-02-06 |  | 6 | 10 | 2024-02-12 | 2024-02-13 | 2024-02-19 | 7 | 23 | 2024-02-23 | 2024-02-23 | Government of the Philipppiens | 3393 | 3393 |  | 3291 | 3291 |  | 0.030062 | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed | FALSE | FALSE
24-0120 | JANITORIAL SUPPLIES/HOUSEKEEPING | COA | No | NP-53.9 - Small Value Procurement | N/A | 2024-01-27 |  | N/A | 2024-01-31 | 2024-01-31 | 4 | N/A | N/A | 2024-02-06 |  | 6 | 10 | 2024-02-12 | 2024-02-14 | 2024-02-19 | 7 | 23 | 2024-02-28 | 2024-02-28 | Government of the Philipppiens | 29538 | 29538 |  | 29034 | 29034 |  | 0.017063 | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed | FALSE | FALSE
23-C0759 | VARIOUS CONSTRUCTION SUPPLY | PGSO | No | Competitive Bidding | N/A | 2023-12-11 |  | 2023-12-19 | 2024-01-09 | 2024-01-09 |  | 2024-01-09 | 2024-01-19 | 2024-02-06 |  |  |  | 2024-02-14 | 2024-02-14 | 2024-02-23 |  |  | 2024-06-26 | 2024-06-26 | Government of the Philipppiens | 1606988.6 |  | 1606988.6 | 1605527 |  | 1605527 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2023-12-18 | 2024-01-02 | 2024-01-02 | 2024-01-02 | 2024-01-02 | N/A | Completed
23-4461 | JOB ORDER (LABOR & MATERIALS) | PDRRMO | No | NP-53.1 Two Failed Biddings | N/A | 2024-01-25 |  | N/A | 2024-02-08 | 2024-02-08 |  | N/A | N/A | 2024-02-08 |  |  |  | 2024-02-15 | 2024-02-26 | 2024-02-29 |  |  | 2024-04-09 | 2024-04-09 | Government of the Philipppiens | 217926.65 |  | 217926.65 | 217925.5 |  | 217925.5 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1014 | HYGIENE KITS | PDRRMO | No | NP-53.2 Emergency Cases | 2024-02-06 | 2024-02-07 |  | N/A | 2024-02-08 | 2024-02-08 |  | N/A | N/A | 2024-02-08 |  |  |  | 2024-02-08 | 2024-02-08 | 2024-02-08 |  |  | 2024-02-10 | 2024-02-10 | Government of the Philipppiens | 950625 |  | 950625 | 929452.5 |  | 929452.5 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0667 | PACKED MEALS | PDRRMO | No | NP-53.2 Emergency Cases | N/A | 2024-01-31 |  | N/A | 2024-01-31 | 2024-01-31 |  | N/A | N/A | 2024-02-01 |  |  |  | 2024-02-01 | 2024-02-01 | 2024-02-01 |  |  | 2024-03-27 | 2024-03-27 | Government of the Philipppiens | 595000 |  | 595000 | 595000 |  | 595000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C0967 | FOOD SUPPLIES-DRY GOODS | PDRRMO | No | NP-53.2 Emergency Cases | N/A | 2024-01-31 |  | N/A | 2024-01-31 | 2024-01-31 |  | N/A | N/A | 2024-02-01 |  |  |  | 2024-02-01 | 2024-02-01 | 2024-02-01 |  |  | 2024-02-03 | 2024-02-03 | Government of the Philipppiens | 3098368 |  | 3098368 | 3070984 |  | 3070984 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C0966 | FOOD SUPPLIES - DRY GOODS | PDRRMO | No | NP-53.2 Emergency Cases | N/A | 2024-01-31 |  | N/A | 2024-02-01 | 2024-02-01 |  | N/A | N/A | 2024-02-01 |  |  |  | 2024-02-01 | 2024-02-01 | 2024-02-01 |  |  | 2024-02-03 | 2024-02-03 | Government of the Philipppiens | 1161888 |  | 1161888 | 1151619 |  | 1151619 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0818 | FOOD SUPPLIES | PDRRMO | No | NP-53.2 Emergency Cases | 2024-02-06 | 2024-02-07 |  | N/A | 2024-02-08 | 2024-02-08 |  | N/A | N/A | 2024-02-08 |  |  |  | 2024-02-09 | 2024-02-12 | 2024-02-12 |  |  | 2024-02-13 | 2024-02-13 | Government of the Philipppiens | 415690 |  | 415690 | 413670 |  | 413670 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C0950 | JANITORIAL SUPPLIES/HOUSEKEEPING | PIAO | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-02 |  | N/A | 2024-02-13 | 2024-02-13 |  | N/A | N/A | 2024-02-14 |  |  |  | N/A | 2024-02-21 | 2024-02-22 |  |  | 2024-02-27 | 2024-02-27 | Government of the Philipppiens | 8474 | 8474 |  | 8368 | 8368 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0125 | SPAREPARTS (LIGHT VEHICLES) | COA | No | NP-53.9 - Small Value Procurement | N/A | 2024-01-27 |  | N/A | 2024-02-13 | 2024-02-13 |  | N/A | N/A | 2024-02-14 |  |  |  | 2024-02-16 | 2024-02-26 | 2024-02-29 |  |  | 2024-03-06 | 2024-03-06 | Government of the Philipppiens | 53400 | 53400 |  | 52000 | 52000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0235 | COMPUTER SUPPLIES/SPAREPARTS | PACCO | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-02 |  | N/A | 2024-02-13 | 2024-02-13 |  | N/A | N/A | 2024-02-14 |  |  |  | 2024-02-14 | 2024-02-21 | 2024-02-22 |  |  | 2024-05-10 | 2024-05-10 | Government of the Philipppiens | 81446 | 81446 |  | 81134 | 81134 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C0952 | CONSTRUCTION SUPPLIES | PEO-GA | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-02 |  | N/A | 2024-02-13 | 2024-02-13 |  | N/A | N/A | 2024-02-14 |  |  |  | 2024-02-16 | 2024-02-22 | 2024-02-26 |  |  | 2024-02-29 | 2024-02-29 | Government of the Philipppiens | 107319 | 107319 |  | 107319 | 107319 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0081 | JANITORIAL SUPPLIES/HOUSEKEEPING | PBO | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-02 |  | N/A | 2024-02-13 | 2024-02-13 |  | N/A | N/A | 2024-02-14 |  |  |  | N/A | 2024-02-21 | 2024-02-22 |  |  | 2024-02-23 | 2024-02-23 | Government of the Philipppiens | 5209 | 5209 |  | 5050 | 5050 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0381 | JANITORIAL SUPPLIES/HOUSEKEEPING | PEO-GA | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-02 |  | N/A | 2024-02-13 | 2024-02-13 |  | N/A | N/A | 2024-02-14 |  |  |  | N/A | 2024-02-22 | 2024-02-29 |  |  | 2024-03-11 | 2024-03-11 | Government of the Philipppiens | 33458 | 33458 |  | 32542 | 32542 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0118 | FUEL, OIL, AND LUBRICANTS | COA | No | NP-53.9 - Small Value Procurement | N/A | 2024-01-27 |  | N/A | 2024-02-13 | 2024-02-13 |  | N/A | N/A | 2024-02-14 |  |  |  | N/A | 2024-02-26 | 2024-02-26 |  |  | 2024-03-11 | 2024-03-11 | Government of the Philipppiens | 29976 | 29976 |  | 29880 | 29880 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0124 | SPAREPARTS (LIGHT VEHICLES) | COA | No | NP-53.9 - Small Value Procurement | N/A | 2024-01-27 |  | N/A | 2024-02-13 | 2024-02-13 |  | N/A | N/A | 2024-02-14 |  |  |  | 2024-02-15 | 2024-02-21 | 2024-02-22 |  |  | 2024-02-26 | 2024-02-26 | Government of the Philipppiens | 57216 | 57216 |  | 57216 | 57216 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0123 | SPAREPARTS (HEAVY EQUIPMENT) | COA | No | NP-53.9 - Small Value Procurement | N/A | 2024-01-27 |  | N/A | 2024-02-13 | 2024-02-13 |  | N/A | N/A | 2024-02-14 |  |  |  | N/A | 2024-02-20 | 2024-02-22 |  |  | 2024-02-26 | 2024-02-26 | Government of the Philipppiens | 27225 | 27225 |  | 26910 | 26910 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C0931 | PRINTERS | PHO |  | NP-53.9 - Small Value Procurement | N/A | 2024-01-27 |  | N/A | 2024-02-13 | 2024-02-13 |  | N/A | N/A | 2024-02-14 |  |  |  | 2024-02-16 | 2024-02-22 | 2024-02-26 |  |  | 2024-04-16 | 2024-04-16 | Government of the Philipppiens | 58000 |  | 58000 | 58000 |  | 58000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
24-0133 | FOOD/CATERING SERVICES | PAO-ADMIN |  | NP-53.9 - Small Value Procurement | 2024-01-23 | 2024-01-27 |  | N/A | 2024-02-13 | 2024-02-13 |  | N/A | N/A | 2024-02-14 |  |  |  | 2024-02-16 | 2024-02-19 | 2024-02-22 |  |  | 2024-03-25 | 2024-03-25 | Government of the Philipppiens | 70000 | 70000 |  | 68000 | 68000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | COMPLETED
24-0719 | SPAREPARTS (LIGHT VEHICLES) | PDRRMO | No | Shopping 52.1(a) - Unforeseen Contingency | 2024-01-31 | 2024-02-02 |  | N/A | 2024-02-13 | 2024-02-13 |  | N/A | N/A | 2024-02-14 |  |  |  | N/A | 2024-02-21 | 2024-02-22 |  |  | 2024-02-22 | 2024-02-22 | Government of the Philipppiens | 52000 |  | 52000 | 52000 |  | 52000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C0932 | CONSTRUCTION MATERIALS | PEO | No | Competitive Bidding | N/A | 2024-01-29 |  | N/A | 2024-02-06 | 2024-02-06 |  | 2024-02-06 | 2024-02-12 | 2024-02-14 |  |  |  | 2024-02-15 | 2024-03-18 | 2024-03-21 |  |  | 2024-04-11 | 2024-04-11 | Government of the Philipppiens | 638625.04 |  | 638625.04 | 635746.1 |  | 635746.1 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-02-02 | 2024-02-02 | 2024-02-02 | 2024-02-02 | N/A | Completed
24-C1294 | MEDICAL SUPPLIES | PEEMO | No | NP-53.9 - Small Value Procurement | 2024-04-02 | 2024-04-08 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | 2024-05-29 | 2024-06-10 | 2024-06-24 |  |  | 2024-06-25 | 2024-06-25 | Government of the Philipppiens | 289643 | 289643 |  | 289049 | 289049 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C0951 | OFFICE SUPPLIES | PIAO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-02-02 |  | N/A | 2024-02-13 | 2024-02-13 |  | N/A | N/A | 2024-02-14 |  |  |  | N/A | 2024-02-21 | 2024-02-22 |  |  | 2024-03-07 | 2024-03-07 | Government of the Philipppiens | 18122 | 18122 |  | 17857 | 17857 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C0972 | OFFICE SUPPLIES | PACCO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-02-02 |  | N/A | 2024-02-13 | 2024-02-13 |  | N/A | N/A | 2024-02-14 |  |  |  | 2024-02-16 | 2024-02-20 | 2024-02-22 |  |  | 2024-02-29 | 2024-02-29 | Government of the Philipppiens | 134377 | 134377 |  | 130772 | 130772 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0013 | SUPPLY AND DELIVERY OF ARC MEGA TENT | PGO | No | Competitive Bidding | 2024-01-09 | 2024-01-24 |  | 2024-01-31 | 2024-02-13 | 2024-02-13 |  | 2024-02-13 | 2024-02-16 | 2024-02-22 |  |  |  | 2024-02-27 | 2024-03-01 | 2024-03-04 |  |  | 2024-03-25 | 2024-03-25 | Government of the Philipppiens | 5000000 |  | 5000000 | 4998500 |  | 4998500 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2024-01-25 | 2024-02-12 | 2024-02-12 | 2024-02-12 | 2024-02-12 | N/A | Completed
24-0686 | SUPPLY AND DELIVERY OF WARNING DEVICES/SIGNAGES | PDRRMO | No | Competitive Bidding | N/A | 2024-02-02 |  | N/A | 2024-02-13 | 2024-02-13 |  | 2024-02-13 | 2024-02-16 | 2024-02-22 |  |  |  | 2024-03-01 | 2024-03-04 | 2024-03-06 |  |  | 2024-06-06 | 2024-06-06 | Government of the Philipppiens | 985600 |  | 985600 | 776000 |  | 776000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-02-12 | 2024-02-12 | 2024-02-12 | 2024-02-12 | N/A | Completed
24-0071 | OFFICE SUPPLIES | PGO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-02-09 |  | N/A | 2024-02-20 | 2024-02-20 |  | N/A | N/A | 2024-02-22 |  |  |  | 2024-02-28 | 2024-03-01 | 2024-03-05 |  |  | 2024-03-15 | 2024-03-15 | Government of the Philipppiens | 149415 | 149415 |  | 146985 | 146985 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0086 | INK | PBO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-02-13 |  | N/A | 2024-02-20 | 2024-02-20 |  | N/A | N/A | 2024-02-22 |  |  |  | N/A | 2024-02-29 | 2024-03-01 |  |  | 2024-03-11 | 2024-03-11 | Government of the Philipppiens | 7233 | 7233 |  | 7140 | 7140 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C0939 | OFFICE SUPPLIES | PBO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-02-09 |  | N/A | 2024-02-20 | 2024-02-20 |  | N/A | N/A | 2024-02-22 |  |  |  | 2024-02-26 | 2024-02-29 | 2024-03-01 |  |  | 2024-03-18 | 2024-03-18 | Government of the Philipppiens | 64722 | 64722 |  | 62181 | 62181 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1000 | OFFICE SUPPLIES | PGSO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-02-15 |  | N/A | 2024-02-20 | 2024-02-20 |  | N/A | N/A | 2024-02-22 |  |  |  | 2024-02-26 | 2024-03-05 | 2024-03-06 |  |  | 2024-03-13 | 2024-03-13 | Government of the Philipppiens | 56591 | 56591 |  | 55825 | 55825 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C0981 | FOOD/CATERING SERVICES | PSWDO | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-09 |  | N/A | 2024-02-20 | 2024-02-20 |  | N/A | N/A | 2024-02-22 |  |  |  | 2024-02-29 | 2024-02-29 | 2024-03-05 |  |  | 2024-05-16 | 2024-05-16 | Government of the Philipppiens | 303740 |  | 303740 | 301062 |  | 301062 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0515 | FOOD/CATERING SERVICES | PAO-ADMIN | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-09 |  | N/A | 2024-02-20 | 2024-02-20 |  | N/A | N/A | 2024-02-22 |  |  |  | 2024-02-26 | 2024-03-01 | 2024-03-05 |  |  | 2024-04-18 | 2024-04-18 | Government of the Philipppiens | 149940 | 149940 |  | 147792 | 147792 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C0961 | FOOD/CATERING SERVICES | PAO-ADMIN | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-15 |  | N/A | 2024-02-20 | 2024-02-20 |  | N/A | N/A | 2024-02-22 |  |  |  | 2024-02-26 | 2024-02-29 | 2024-03-05 |  |  | 2024-05-24 | 2024-05-24 | Government of the Philipppiens | 79970 | 79970 |  | 78630 | 78630 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0089 | PRINTED FORMS | PAO-ADMIN | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-02 |  | N/A | 2024-02-20 | 2024-02-20 |  | N/A | N/A | 2024-02-22 |  |  |  | N/A | 2024-02-29 | 2024-03-01 |  |  | 2024-04-29 | 2024-04-29 | Government of the Philipppiens | 25000 | 25000 |  | 25000 | 25000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0543 | PRINTING | PAO-ADMIN | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-13 |  | N/A | 2024-02-20 | 2024-02-20 |  | N/A | N/A | 2024-02-22 |  |  |  | N/A | 2024-02-29 | 2024-03-05 |  |  | 2024-06-07 | 2024-06-07 | Government of the Philipppiens | 9996 | 9996 |  | 9996 | 9996 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0023 | GARMENTS | PTO | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-13 |  | N/A | 2024-02-20 | 2024-02-20 |  | N/A | N/A | 2024-02-22 |  |  |  | N/A | 2024-02-29 | 2024-03-01 |  |  | 2024-04-01 | 2024-04-01 | Government of the Philipppiens | 20000 | 20000 |  | 20000 | 20000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0039 | PRINTING | SEF | No | NP-53.9 - Small Value Procurement | 2024-01-31 | 2024-02-02 |  | N/A | 2024-02-20 | 2024-02-20 |  | N/A | N/A | 2024-02-22 |  |  |  | N/A | 2024-03-04 | 2024-03-06 |  |  | 2024-05-22 | 2024-05-22 | Government of the Philipppiens | 1792 |  | 1792 | 1664 |  | 1664 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0127 | PRINTING | SEF | No | NP-53.9 - Small Value Procurement | 2024-01-31 | 2024-02-02 |  | N/A | 2024-02-20 | 2024-02-20 |  | N/A | N/A | 2024-02-22 |  |  |  | N/A | 2024-03-04 | 2024-03-06 |  |  | 2024-05-22 | 2024-05-22 | Government of the Philipppiens | 1792 |  | 1792 | 1664 |  | 1664 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0592 | PRINTING | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-02 |  | N/A | 2024-02-20 | 2024-02-20 |  | N/A | N/A | 2024-02-22 |  |  |  | N/A | 2024-02-28 | 2024-02-29 |  |  | 2024-03-07 | 2024-03-07 | Government of the Philipppiens | 40852 |  | 40852 | 40852 |  | 40852 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0590 | UNIFORM SUPPLIES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-09 |  | N/A | 2024-02-20 | 2024-02-20 |  | N/A | N/A | 2024-02-22 |  |  |  | N/A | 2024-02-28 | 2024-02-29 |  |  | 2024-03-06 | 2024-03-06 | Government of the Philipppiens | 38250 |  | 38250 | 38250 |  | 38250 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0593 | ACCESSORIES & DECORATION | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-09 |  | N/A | 2024-02-20 | 2024-02-20 |  | N/A | N/A | 2024-02-22 |  |  |  | N/A | 2024-02-28 | 2024-02-29 |  |  | 2024-03-06 | 2024-03-06 | Government of the Philipppiens | 1500 |  | 1500 | 1500 |  | 1500 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C0977 | PLAQUE/TROPHIES/MEDAL | PHRMDO | No | NP-53.9 - Small Value Procurement | 2024-01-31 | 2024-02-02 |  | N/A | 2024-02-20 | 2024-02-20 |  | N/A | N/A | 2024-02-22 |  |  |  | N/A | 2024-02-28 | 2024-02-29 |  |  | 2024-03-06 | 2024-03-06 | Government of the Philipppiens | 38200 | 38200 | 0 | 38200 | 38200 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0588 | OFFICE SUPPLIES | PHRMDO | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-09 |  | N/A | 2024-02-20 | 2024-02-20 |  | N/A | N/A | 2024-02-22 |  |  |  | N/A | 2024-02-28 | 2024-02-29 |  |  | 2024-03-06 | 2024-03-06 | Government of the Philipppiens | 1830 |  | 1830 | 1830 |  | 1830 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0486 | LUMBER | DDOPH-Montevista | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-02 |  | N/A | 2024-02-20 | 2024-02-20 |  | N/A | N/A | 2024-02-22 |  |  |  | N/A | 2024-03-12 | 2024-03-19 |  |  | 2024-06-14 | 2024-06-14 | Government of the Philipppiens | 39229.02 |  | 39229.02 | 29213.1 |  | 29213.1 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-4391 | LUMBER | PGSO | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-02 |  | N/A | 2024-02-20 | 2024-02-20 |  | N/A | N/A | 2024-02-22 |  |  |  | N/A | 2024-03-21 | 2024-03-26 |  |  | 2024-05-17 | 2024-05-17 | Government of the Philipppiens | 2240 | 2240 |  | 2240 | 2240 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C0980 | ELECTRICAL SUPPLIES | PHRMDO | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-13 |  | N/A | 2024-02-20 | 2024-02-20 |  | N/A | N/A | 2024-02-22 |  |  |  | 2024-02-26 | 2024-02-29 | 2024-03-01 |  |  | 2024-03-06 | 2024-03-06 | Government of the Philipppiens | 121224 | 121224 |  | 120202.5 | 120202.5 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0616 | LUMBER | PHRMDO | No | NP-53.9 - Small Value Procurement | 2024-01-31 | 2024-02-02 |  | N/A | 2024-02-20 | 2024-02-20 |  | N/A | N/A | 2024-02-22 |  |  |  | N/A | 2024-02-28 | 2024-02-28 |  |  | 2024-03-01 | 2024-03-01 | Government of the Philipppiens | 12840 |  | 12840 | 12840 |  | 12840 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0680 | JANITORIAL SUPPLIES/HOUSEKEEPING | PHRMDO | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-13 |  | N/A | 2024-02-20 | 2024-02-20 |  | N/A | N/A | 2024-02-22 |  |  |  | N/A | 2024-02-29 | 2024-03-01 |  |  | 2024-03-11 | 2024-03-11 | Government of the Philipppiens | 45835 | 45835 |  | 44385 | 44385 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0315 | OFFICE EQUIPMENT | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-02 |  | N/A | 2024-02-20 | 2024-02-20 |  | N/A | N/A | 2024-02-22 |  |  |  | 2024-02-26 | 2024-02-29 | 2024-03-04 |  |  | 2024-03-25 | 2024-03-25 | Government of the Philipppiens | 82500 |  | 82500 | 53900 |  | 53900 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0288 | FOOD/CATERING SERVICES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-13 |  | N/A | 2024-02-20 | 2024-02-20 |  | N/A | N/A | 2024-02-22 |  |  |  | 2024-02-28 | 2024-02-29 | 2024-03-01 |  |  | 2024-03-08 | 2024-03-08 | Government of the Philipppiens | 142000 |  | 142000 | 141900 |  | 141900 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C0940 | COMPUTER SERVICES | PBO | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-02 |  | N/A | 2024-02-20 | 2024-02-20 |  | N/A | N/A | 2024-02-22 |  |  |  | 2024-02-26 | 2024-02-29 | 2024-03-01 |  |  | 2024-03-11 | 2024-03-11 | Government of the Philipppiens | 63619 | 63619 |  | 63300 | 63300 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0090 | OFFICE EQUIPMENT | PACCO | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-02 |  | N/A | 2024-02-20 | 2024-02-20 |  | N/A | N/A | 2024-02-22 |  |  |  | 2024-02-26 | 2024-02-29 | 2024-03-01 |  |  | 2024-03-11 | 2024-03-11 | Government of the Philipppiens | 60400 | 60400 |  | 59800 | 59800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1029 | OTHER MACHINERIES AND EQUIPMENT | PHRMDO | No | NP-53.9 - Small Value Procurement | 2024-02-08 | 2024-02-13 |  | N/A | 2024-02-20 | 2024-02-20 |  | N/A | N/A | 2024-02-22 |  |  |  | 2024-02-27 | 2024-02-29 | 2024-03-04 |  |  | 2024-03-08 | 2024-03-08 | Government of the Philipppiens | 175000 |  | 175000 | 174800 |  | 174800 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1039 | RENTALS | PHRMDO | No | NP-53.9 - Small Value Procurement | 2024-02-08 | 2024-02-13 |  | N/A | 2024-02-20 | 2024-02-20 |  | N/A | N/A | 2024-02-22 |  |  |  | 2024-02-27 | 2024-02-29 | 2024-03-01 |  |  | 2024-03-08 | 2024-03-08 | Government of the Philipppiens | 480000 |  | 480000 | 480000 |  | 480000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1086 | FOOD/CATERING SERVICES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-15 |  | N/A | 2024-02-20 | 2024-02-20 |  | N/A | N/A | 2024-02-22 |  |  |  | N/A | 2024-02-28 | 2024-02-29 |  |  | 2024-03-07 | 2024-03-07 | Government of the Philipppiens | 25000 |  | 25000 | 25000 |  | 25000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0648 | DUPLICATING PRODUCTS/SPAREPARTS | PASSO | No | Direct Contracting | N/A | 2024-02-08 |  | N/A | 2024-02-20 | 2024-02-20 |  | N/A | N/A | 2024-02-22 |  |  |  | N/A | 2024-02-28 | 2024-03-04 |  |  | 2024-03-07 | 2024-03-07 | Government of the Philipppiens | 49533 | 49533 |  | 42875 | 42875 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C0985 | LABORATORY SUPPLIES | PEEMO | No | Direct Contracting | 2024-01-31 | 2024-02-13 |  | N/A | 2024-02-20 | 2024-02-20 |  | N/A | N/A | 2024-02-22 |  |  |  | N/A | 2024-03-01 | 2024-03-04 |  |  | 2024-03-04 | 2024-03-04 | Government of the Philipppiens | 2292500 | 2292500 |  | 2292500 | 2292500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C0984 | MEDICAL SUPPLIES | PEEMO | No | Direct Contracting | 2024-01-31 | 2024-02-13 |  | N/A | 2024-02-20 | 2024-02-20 |  | N/A | N/A | 2024-02-22 |  |  |  | N/A | 2024-02-29 | 2024-03-04 |  |  | 2024-03-09 | 2024-03-09 | Government of the Philipppiens | 3138000 | 3138000 |  | 3138000 | 3138000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C0989 | LABORATORY SUPPLIES | PEEMO | No | Direct Contracting | 2024-01-31 | 2024-02-13 |  | N/A | 2024-02-20 | 2024-02-20 |  | N/A | N/A | 2024-02-22 |  |  |  | N/A | 2024-02-29 | 2024-03-04 |  |  | 2024-04-22 | 2024-04-22 | Government of the Philipppiens | 1254000 | 1254000 |  | 1254000 | 1254000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1006 | LABORATORY SUPPLIES/REAGENT | DDOPH-Montevista | No | Direct Contracting | 2024-01-31 | 2024-02-13 |  | N/A | 2024-02-20 | 2024-02-20 |  | N/A | N/A | 2024-02-22 |  |  |  | N/A | 2024-02-29 | 2024-03-04 |  |  | 2024-05-08 | 2024-05-08 | Government of the Philipppiens | 106000 | 106000 |  | 102000 | 102000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C0991 | LABORATORY SUPPLIES/REAGENT | PEEMO | No | Direct Contracting | N/A | 2024-02-13 |  | N/A | 2024-02-20 | 2024-02-20 |  | N/A | N/A | 2024-02-22 |  |  |  | N/A | 2024-02-29 | 2024-03-04 |  |  | 2024-06-03 | 2024-06-03 | Government of the Philipppiens | 985450 | 985450 |  | 985450 | 985450 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C0987 | LABORATORY SUPPLIES | PEEMO | No | Direct Contracting | 2024-01-31 | 2024-02-13 |  | N/A | 2024-02-20 | 2024-02-20 |  | N/A | N/A | 2024-02-22 |  |  |  | N/A | 2024-02-29 | 2024-03-04 |  |  | 2024-06-07 | 2024-06-07 | Government of the Philipppiens | 768750 | 768750 |  | 768750 | 768750 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1075 | FOOD SUPPLIES | PDRRMO | No | NP-53.2 Emergency Cases | N/A | 2024-02-13 |  | N/A | 2024-02-13 | 2024-02-13 |  | N/A | N/A | 2024-02-15 |  |  |  | 2024-02-15 | 2024-02-15 | 2024-02-15 |  |  | 2024-02-15 | 2024-02-15 | Government of the Philipppiens | 3098368 |  | 3098368 | 3070984 |  | 3070984 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1149 | CAUTION 500M | PDRRMO | No | NP-53.2 Emergency Cases | N/A | 2024-02-20 |  | N/A | 2024-02-20 | 2024-02-20 |  | N/A | N/A | 2024-02-22 |  |  |  | 2024-02-29 | 2024-03-04 | 2024-03-06 |  |  | 2024-03-07 | 2024-03-07 | Government of the Philipppiens | 67500 |  | 67500 | 66500 |  | 66500 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0867 | SPAREPARTS (LIGHT VEHICLES) | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-02-16 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-04-02 | 2024-04-08 |  |  | 2024-04-08 | 2024-04-08 | Government of the Philipppiens | 7316 | 7316 |  | 7316 | 7316 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1196 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-01 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-25 | 2024-04-03 |  |  | 2024-04-03 | 2024-04-03 | Government of the Philipppiens | 46000 | 46000 |  | 46000 | 46000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1275 | SPAREPARTS(MOTOR CYCLE) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-01 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-22 | 2024-04-02 |  |  | 2024-04-02 | 2024-04-02 | Government of the Philipppiens | 2850 | 2850 |  | 2850 | 2850 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1177 | SPAREPARTS(MOTOR CYCLE) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-01 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-22 | 2024-04-02 |  |  | 2024-04-02 | 2024-04-02 | Government of the Philipppiens | 6160 | 6160 |  | 6160 | 6160 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1200 | SPAREPARTS(MOTOR CYCLE) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-01 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-25 | 2024-04-03 |  |  | 2024-04-03 | 2024-04-03 | Government of the Philipppiens | 3100 | 3100 |  | 3100 | 3100 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1203 | SPAREPARTS(MOTOR CYCLE) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-01 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-21 | 2024-03-26 |  |  | 2024-03-26 | 2024-03-26 | Government of the Philipppiens | 8345 | 8345 |  | 8345 | 8345 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1192 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-01 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-22 | 2024-03-26 |  |  | 2024-03-26 | 2024-03-26 | Government of the Philipppiens | 880 | 880 |  | 880 | 880 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1193 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-01 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-26 | 2024-04-02 |  |  | 2024-04-02 | 2024-04-02 | Government of the Philipppiens | 700 | 700 |  | 700 | 700 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1195 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-01 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-25 | 2024-04-03 |  |  | 2024-04-04 | 2024-04-04 | Government of the Philipppiens | 14150 | 14150 |  | 14150 | 14150 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1194 | SPAREPARTS (MOTORCYCLE) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-01 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-21 | 2024-03-26 |  |  | 2024-03-26 | 2024-03-26 | Government of the Philipppiens | 23503 | 23503 |  | 23503 | 23503 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1199 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-01 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-21 | 2024-03-26 |  |  | 2024-03-26 | 2024-03-26 | Government of the Philipppiens | 31600 | 31600 |  | 31600 | 31600 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1191 | SPAREPARTS(LIGHT VEHICLE) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-01 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-21 | 2024-03-26 |  |  | 2024-03-26 | 2024-03-26 | Government of the Philipppiens | 10650 | 10650 |  | 10650 | 10650 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1175 | SPAREPARTS (MOTORCYCLE) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-01 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-21 | 2024-03-26 |  |  | 2024-03-26 | 2024-03-26 | Government of the Philipppiens | 6080 | 6080 |  | 6080 | 6080 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1255 | SPAREPARTS(LIGHT VEHICLE) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-01 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-25 | 2024-03-26 |  |  | 2024-03-26 | 2024-03-26 | Government of the Philipppiens | 85915 | 85915 |  | 85915 | 85915 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1293 | SPAREPARTS (MOTORCYCLE) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-01 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-26 | 2024-04-02 |  |  | 2024-04-02 | 2024-04-02 | Government of the Philipppiens | 22300 | 22300 |  | 22300 | 22300 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1264 | SPAREPARTS(LIGHT VEHICLE) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-01 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-26 | 2024-04-02 |  |  | 2024-04-02 | 2024-04-02 | Government of the Philipppiens | 16400 | 16400 |  | 16400 | 16400 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1268 | SPAREPARTS(LIGHT VEHICLE) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-01 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-26 | 2024-04-03 |  |  | 2024-04-03 | 2024-04-03 | Government of the Philipppiens | 155480 | 155480 |  | 155480 | 155480 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1259 | SPAREPARTS(LIGHT VEHICLE) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-01 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-26 | 2024-04-02 |  |  | 2024-04-02 | 2024-04-02 | Government of the Philipppiens | 12175 | 12175 |  | 12175 | 12175 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1256 | SPAREPARTS(LIGHT VEHICLE) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-01 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-26 | 2024-04-03 |  |  | 2024-04-03 | 2024-04-03 | Government of the Philipppiens | 52480 | 52480 |  | 52480 | 52480 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1251 | SPAREPARTS(LIGHT VEHICLE) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-01 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-26 | 2024-04-02 |  |  | 2024-04-02 | 2024-04-02 | Government of the Philipppiens | 67950 | 67950 |  | 67950 | 67950 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1252 | SPAREPARTS(LIGHT VEHICLE) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-01 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-25 | 2024-03-26 |  |  | 2024-03-26 | 2024-03-26 | Government of the Philipppiens | 800 | 800 |  | 800 | 800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1281 | SPAREPARTS (MOTORCYCLE) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-01 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-26 | 2024-04-04 |  |  | 2024-04-04 | 2024-04-04 | Government of the Philipppiens | 8280 | 8280 |  | 8280 | 8280 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1206 | SPAREPARTS(LIGHT VEHICLE) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-01 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-26 | 2024-04-02 |  |  | 2024-04-02 | 2024-04-02 | Government of the Philipppiens | 21950 | 21950 |  | 21950 | 21950 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-5517 | DISTILLED WATER | PAGRO | No | NP-53.9 - Small Value Procurement | 2023-12-12 | 2024-01-25 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-18 | 2024-03-21 |  |  | 2024-04-01 | 2024-04-01 | Government of the Philipppiens | 56371.5 | 9000 | 47371.5 | 56212 | 9000 | 47212 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0062 | FOOD/CATERING SERVICES | PBO | No | NP-53.9 - Small Value Procurement | 2023-12-12 | 2024-01-25 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-18 | 2024-03-20 |  |  | 2024-05-17 | 2024-05-17 | Government of the Philipppiens | 17000 | 17000 | 0 | 16900 | 16900 | 0 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0038 | PAINTING MATERIALS | SEF | No | NP-53.9 - Small Value Procurement | 2023-12-12 | 2024-01-25 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | 2024-03-06 | 2024-03-22 | 2024-03-26 |  |  | 2024-04-12 | 2024-04-12 | Government of the Philipppiens | 203766.44 | 84785 | 118981.44 | 201994.5 | 83835 | 118159.5 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0088 | BINDER | PACCO | No | NP-53.9 - Small Value Procurement | N/A | 2024-01-27 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-21 | 2024-03-26 |  |  | 2024-04-12 | 2024-04-12 | Government of the Philipppiens | 9000 | 9000 | 0 | 9000 | 9000 | 0 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0645 | COSMETOLOGY SUPPLIES | PAO-ADMIN | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-16 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | 2024-03-06 | 2024-03-20 | 2024-03-21 |  |  | 2024-03-25 | 2024-03-25 | Government of the Philipppiens | 84785 |  | 84785 | 83835 |  | 83835 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C0942 | FIRE EXTINGUISHER & REFILL | PEEMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-16 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | 2024-03-06 | 2024-03-22 | 2024-03-26 |  |  | 2024-04-17 | 2024-04-17 | Government of the Philipppiens | 264033 | 264033 |  | 261540 | 261540 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0869 | JANITORIAL SUPPLIES/HOUSEKEEPING | SPO | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-13 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-05-03 | 2024-05-07 |  |  | 2024-05-09 | 2024-05-09 | Government of the Philipppiens | 39685 | 39685 |  | 39685 | 39685 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0083 | COMPUTER SUPPLIES | PBO | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-13 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-18 | 2024-03-21 |  |  | 2024-04-22 | 2024-04-22 | Government of the Philipppiens | 1948 | 1948 |  | 1948 | 1948 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0204 | JANITORIAL SUPPLIES/HOUSEKEEPING | PAO-ADMIN | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-09 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-20 | 2024-03-21 |  |  | 2024-04-03 | 2024-04-03 | Government of the Philipppiens | 17062 | 17062 |  | 16912 | 16912 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0082 | KITCHENWARE & UTENSILS | PBO | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-02 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-18 | 2024-03-19 |  |  | 2024-03-25 | 2024-03-25 | Government of the Philipppiens | 385 | 385 |  | 378 | 378 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C0955 | TONER | PEO-GA | No | NP-53.9 - Small Value Procurement | 2024-02-13 | 2024-02-15 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | 2024-03-06 | 2024-03-25 | 2024-04-02 |  |  | 2024-06-03 | 2024-06-03 | Government of the Philipppiens | 80000 | 80000 |  | 80000 | 80000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C0957 | BATTERY | PEEMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-16 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | 2024-03-06 | 2024-03-22 | 2024-03-26 |  |  | 2024-04-03 | 2024-04-03 | Government of the Philipppiens | 208785 | 208785 |  | 171000 | 171000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C0971 | SPAREPARTS (LIGHT VEHICLES) | PEEMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-16 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | 2024-03-06 | 2024-03-22 | 2024-03-26 |  |  | 2024-04-03 | 2024-04-03 | Government of the Philipppiens | 165815 | 165815 |  | 110150 | 110150 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1019 | BARCODE SCANNER & COMPUTER DESKTOP | PAO-ADMIN | No | NP-53.9 - Small Value Procurement | 2024-02-20 | 2024-02-22 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | 2024-03-06 | 2024-03-20 | 2024-03-26 |  |  | 2024-04-15 | 2024-04-15 | Government of the Philipppiens | 51600 | 51600 |  | 51398 | 51398 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1050 | COMPUTERS SUPPLIES | PHRMDO | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-22 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | 2024-03-06 | 2024-03-15 | 2024-03-19 |  |  | 2024-05-10 | 2024-05-10 | Government of the Philipppiens | 148500 | 84000 | 64500 | 132239 | 84000 | 48239 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0372 | COMPUTER SUPPLIES/SPAREPARTS | PEO-GA | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-09 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | 2024-03-06 | 2024-03-21 | 2024-03-26 |  |  | 2024-04-11 | 2024-04-11 | Government of the Philipppiens | 51316 | 51316 |  | 47000 | 47000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1318 | GARMENTS | SEF | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-22 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | 2024-03-07 | 2024-03-22 | 2024-04-08 |  |  | 2024-04-23 | 2024-04-23 | Government of the Philipppiens | 280800 |  | 280800 | 280800 |  | 280800 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1317 | UNIFORM SUPPLIES | SEF | No | NP-53.9 - Small Value Procurement | 2024-02-20 | 2024-02-22 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | 2024-03-07 | 2024-03-21 | 2024-03-27 |  |  | 2024-03-27 | 2024-03-27 | Government of the Philipppiens | 84000 |  | 84000 | 84000 |  | 84000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0203 | FOOD/CATERING SERVICES | PGSO | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-22 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-25 | 2024-04-02 |  |  | 2024-05-06 | 2024-05-06 | Government of the Philipppiens | 12500 | 12500 |  | 12150 | 12150 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0266 | COMPUTER SUPPLIES/SPAREPARTS | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-22 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-20 | 2024-03-21 |  |  | 2024-04-16 | 2024-04-16 | Government of the Philipppiens | 7950 |  | 7950 | 7875 |  | 7875 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0033 | GARMENTS | PTO | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-22 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-19 | 2024-03-26 |  |  | 2024-04-25 | 2024-04-25 | Government of the Philipppiens | 35000 | 35000 |  | 32900 | 32900 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0126 | LUMBER | SEF | No | NP-53.9 - Small Value Procurement | 2024-01-31 | 2024-02-02 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-21 | 2024-03-26 |  |  | 2024-06-14 | 2024-06-14 | Government of the Philipppiens | 2256 |  | 2256 | 2256 |  | 2256 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1008 | SPAREPARTS (FARM MACHINERIES AND EQUIPMENT) | PVO | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-09 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-19 | 2024-03-25 |  |  | 2024-05-03 | 2024-05-03 | Government of the Philipppiens | 2932 | 2932 |  | 2930 | 2930 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1029 | FURNITURE & FIXTURES | PICTO | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-13 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-18 | 2024-03-19 |  |  | 2024-04-02 | 2024-04-02 | Government of the Philipppiens | 48600 | 48600 |  | 47630 | 47630 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0098 | SAFETY GEARS & EQUIPMENT | SEF | No | NP-53.9 - Small Value Procurement | 2024-01-31 | 2024-02-02 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-22 | 2024-03-26 |  |  | 2024-04-02 | 2024-04-02 | Government of the Philipppiens | 1925 |  | 1925 | 1895 |  | 1895 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0497 | SAFETY GEARS & EQUIPMENT | PEO | No | NP-53.9 - Small Value Procurement | 2024-02-08 | 2024-02-13 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-21 | 2024-03-26 |  |  | 2024-04-02 | 2024-04-02 | Government of the Philipppiens | 1925 |  | 1925 | 1895 |  | 1895 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0040 | LUMBER | SEF | No | NP-53.9 - Small Value Procurement | 2024-01-31 | 2024-02-02 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-21 | 2024-03-26 |  |  | 2024-05-17 | 2024-05-17 | Government of the Philipppiens | 3552 |  | 3552 | 3552 |  | 3552 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1007 | FOOD SUPPLIES | PEEMO | No | NP-53.9 - Small Value Procurement | 2024-02-13 | 2024-02-15 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | 2024-03-06 | 2024-03-22 | 2024-03-22 |  |  | 2024-04-17 | 2024-04-17 | Government of the Philipppiens | 134344 | 134344 |  | 133132 | 133132 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C0982 | FUEL, OIL, AND LUBRICANTS | PEEMO | No | NP-53.9 - Small Value Procurement | 2024-02-20 | 2024-02-22 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | 2024-03-06 | 2024-04-05 | 2024-04-08 |  |  | 2024-04-08 | 2024-04-08 | Government of the Philipppiens | 153240.8 | 153240.8 |  | 147415 | 147415 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C0956 | SAFETY GEARS | PEEMO | No | NP-53.9 - Small Value Procurement | 2024-02-20 | 2024-02-22 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-21 | 2024-03-22 |  |  | 2024-04-04 | 2024-04-04 | Government of the Philipppiens | 8690 | 8690 |  | 8660 | 8660 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C0944 | SPAREPARTS (LIGHT VEHICLES) | PEEMO | No | NP-53.9 - Small Value Procurement | 2024-02-20 | 2024-02-22 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | 2024-03-06 | 2024-03-22 | 2024-03-22 |  |  | 2024-04-03 | 2024-04-03 | Government of the Philipppiens | 185720 | 185720 |  | 174760 | 174760 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1060 | OFFICE SUPPLIES | PGO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-02-22 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | 2024-03-06 | 2024-03-20 | 2024-03-21 |  |  | 2024-04-19 | 2024-04-19 | Government of the Philipppiens | 234117 |  | 234117 | 229455 |  | 229455 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1009 | OFFICE SUPPLIES | PEEMO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2024-02-20 | 2024-02-22 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | 2024-03-06 | 2024-03-21 | 2024-03-22 |  |  | 2024-04-04 | 2024-04-04 | Government of the Philipppiens | 77598 | 77598 |  | 76920 | 76920 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C0935 | OFFICE SUPPLIES | PTO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2024-02-20 | 2024-02-22 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | 2024-03-06 | 2024-03-22 | 2024-04-01 |  |  | 2024-04-08 | 2024-04-08 | Government of the Philipppiens | 167603 | 167603 |  | 162834 | 162834 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C0970 | INK & MASTER ROLL | PEEMO | No | Direct Contracting | N/A | 2024-02-16 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-21 | 2024-04-03 |  |  | 2024-04-11 | 2024-04-11 | Government of the Philipppiens | 8015 | 8015 |  | 8015 | 8015 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C0969 | SPAREPARTS & TONER FOR DUPLICATING MACHINE | PEEMO | No | Direct Contracting | N/A | 2024-02-16 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-21 | 2024-04-03 |  |  | 2024-04-18 | 2024-04-18 | Government of the Philipppiens | 29703.6 | 29703.6 |  | 29703.6 | 29703.6 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0044 | JOB ORDER (LABOR & MATERIALS) | PGO | No | Direct Contracting | N/A | 2024-02-22 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-14 | 2024-03-14 |  |  | 2024-04-11 | 2024-04-11 | Government of the Philipppiens | 20000 | 20000 |  | 20000 | 20000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0666 | DUPLICATING PRODUCTS/SPAREPARTS | PTO | No | Direct Contracting | 2024-02-20 | 2024-02-22 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-19 | 2024-04-03 |  |  | 2024-04-18 | 2024-04-18 | Government of the Philipppiens | 12046 | 12046 |  | 10950 | 10950 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C0954 | SUPPLY AND DELIVERY OF OFFICE SUPPLIES | PEO | No | Competitive Bidding | N/A | 2024-02-12 |  | N/A | 2024-02-20 | 2024-02-20 |  | 2024-02-20 | 2024-02-27 | 2024-03-06 |  |  |  | 2024-03-12 | 2024-03-25 | 2024-04-02 |  |  | 2024-04-05 | 2024-04-05 | Government of the Philipppiens | 459114 | 459114 |  | 390169 | 390169 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-02-19 | 2024-02-19 | 2024-02-19 | 2024-02-19 | N/A | Completed
24-0248 | SUPPLY AND DELIVEY OF MEALS AND SNACKS | PEEMO | No | Competitive Bidding | N/A | 2024-01-29 |  | N/A | 2024-02-20 | 2024-02-20 |  | 2024-02-20 | 2024-02-27 | 2024-03-06 |  |  |  | 2024-03-06 | 2024-03-06 | 2024-03-07 |  |  | 2024-03-08 | 2024-03-08 | Government of the Philipppiens | 433440 |  | 433440 | 425736 |  | 425736 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-02-19 | 2024-02-19 | 2024-02-19 | 2024-02-19 | N/A | Completed
24-0169 | SUPPLY AND DELIVERY OF FOOD SUPPLIES | PSWDO | No | Competitive Bidding | N/A | 2024-02-12 |  | N/A | 2024-02-20 | 2024-02-20 |  | 2024-02-20 | 2024-03-13 | 2024-03-21 |  |  |  | 2024-03-25 | 2024-04-11 | 2024-04-15 |  |  | 2024-04-22 | 2024-04-22 | Government of the Philipppiens | 790240 |  | 790240 | 585969.5 |  | 585969.5 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2024-02-05 | 2024-02-19 | 2024-02-19 | 2024-02-19 | 2024-02-19 | N/A | Completed
24-C0941 | SUPPLY AND DELIVERY OF OFFICE SUPPLIES | PEEMO | No | Competitive Bidding | N/A | 2024-02-19 |  | N/A | 2024-03-05 | 2024-03-05 |  | 2024-03-05 | 2024-03-13 | 2024-03-22 |  |  |  | 2024-03-26 | 2024-04-11 | 2024-04-16 |  |  | 2024-04-25 | 2024-04-25 | Government of the Philipppiens | 839080 | 839080 |  | 631974 | 631974 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | N/A | Completed
24-0458 | SUPPLY AND DELIVERY OF CONSTRUCTION MATERIALS | PEO | No | Competitive Bidding | N/A | 2024-02-26 |  | N/A | 2024-03-05 | 2024-03-05 |  | 2024-03-05 | 2024-03-13 | 2024-03-21 |  |  |  | 2024-03-27 | 2024-04-12 | 2024-04-22 |  |  | 2024-04-30 | 2024-04-30 | Government of the Philipppiens | 505747.94 |  | 505747.94 | 503824.5 |  | 503824.5 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | N/A | Completed
24-C1057 | SUPPLY AND DELIVERY OF RICE (WELL-MILLED) 50KG/SACK | PSWDO | No | Competitive Bidding | N/A | 2024-02-12 |  | 2024-02-20 | 2024-03-05 | 2024-03-05 |  | 2024-05-30 | 2024-03-13 | 2024-03-21 |  |  |  | 2024-03-22 | 2024-04-04 | 2024-04-11 |  |  | 2024-04-17 | 2024-04-17 | Government of the Philipppiens | 1348050 |  | 1348050 | 1290000 |  | 1290000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2024-02-19 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | N/A | Completed
24-C0983 | SUPPLY AND DELIVERY OF RICE (WELL-MILLED) 50KG/SACK | PEEMO | No | Competitive Bidding | 2024-01-31 | 2024-02-12 |  | 2024-02-20 | 2024-03-05 | 2024-03-05 |  | 2024-03-05 | 2024-03-13 | 2024-03-21 |  |  |  | 2024-03-22 | 2024-03-22 | 2024-04-02 |  |  | 2024-04-04 | 2024-04-04 | Government of the Philipppiens | 1059630 | 1059630 |  | 1014000 | 1014000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2024-02-19 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | N/A | Completed
24-0165 | SUPPLY AND DELIVERY OF MEALS AND SNACKS | PDRRMO | No | Competitive Bidding | N/A | 2024-02-12 |  | 2024-02-20 | 2024-03-22 | 2024-03-22 |  | 2024-03-22 | 2024-03-13 | 2024-03-21 |  |  |  | 2024-03-22 | 2024-03-26 | 2024-04-11 |  |  | 2024-06-18 | 2024-06-18 | Government of the Philipppiens | 1505000 |  | 1505000 | 1484000 |  | 1484000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2024-02-19 | 2024-03-21 | 2024-03-21 | 2024-03-21 | 2024-03-21 | N/A | Completed
24-C0930 | SUPPLY AND DELIVERY OF RICE (WELL-MILLED) 50KG/SACK | PGO | No | Competitive Bidding | N/A | 2024-02-12 |  | 2024-02-20 | 2024-03-05 | 2024-03-05 |  | 2024-03-05 | 2024-03-13 | 2024-03-21 |  |  |  | 2024-03-22 | 2024-04-04 | 2024-04-15 |  |  | 2024-04-24 | 2024-04-24 | Government of the Philipppiens | 1485990 |  | 1485990 | 1422000 |  | 1422000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2024-02-19 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | N/A | Completed
24-C1053 | SUPPLY AND DELIVERY OF SPARE PARST | PGSO | No | Competitive Bidding | N/A | 2024-02-19 |  | N/A | 2024-03-05 | 2024-03-05 |  | 2024-03-05 | 2024-03-13 | 2024-03-21 |  |  |  | 2024-03-27 | 2024-04-17 | 2024-04-25 |  |  | 2024-04-29 | 2024-04-29 | Government of the Philipppiens | 547615 | 547615 |  | 394660 | 394660 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | N/A | Completed
24-C1077 | SUPPLY AND DELIVERY OF SPARE PARTS (TIRES AND BATTERY) | PDRRMO | No | Competitive Bidding | N/A | 2024-02-19 |  | N/A | 2024-03-05 | 2024-03-05 |  | 2024-03-05 | 2024-03-13 | 2024-03-21 |  |  |  | 2024-03-27 | 2024-04-05 | 2024-04-12 |  |  | 2024-04-15 | 2024-04-15 | Government of the Philipppiens | 558824 | 558824 |  | 329400 | 329400 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | N/A | Completed
24-C1036 | SUPPLY AND DELIVERY OF SPARE PARTS/BATTERY | PEEMO | No | Competitive Bidding | 2024-02-20 | 2024-02-26 |  | N/A | 2024-03-05 | 2024-03-05 |  | 2024-05-30 | 2024-03-13 | 2024-03-21 |  |  |  | 2024-03-27 | 2024-04-12 | 2024-04-22 |  |  | 2024-04-25 | 2024-04-25 | Government of the Philipppiens | 790600 | 790600 |  | 552000 | 552000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | N/A | Completed
24-C1001 | SUPPLY AND DELIVERY OF MEDICAL SUPPLIES | PEEMO | No | Competitive Bidding | 2024-02-20 | 2024-02-26 |  | N/A | 2024-03-05 | 2024-03-05 |  | 2024-03-05 | 2024-03-13 | 2024-03-21 |  |  |  | 2024-03-26 | 2024-04-11 | 2024-04-23 |  |  | 2024-04-30 | 2024-04-30 | Government of the Philipppiens | 564043 | 564043 |  | 343226 | 343226 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | N/A | Completed
24-1266 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-01 |  | N/A |  | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-23 | 2024-05-10 |  |  | 2024-05-10 | 2024-05-10 | Government of the Philipppiens | 44000 | 44000 |  | 44000 | 44000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1260 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-01 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-23 | 2024-04-25 |  |  | 2024-04-25 | 2024-04-25 | Government of the Philipppiens | 38230 | 38230 |  | 38230 | 38230 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1263 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-01 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-23 | 2024-04-25 |  |  | 2024-04-25 | 2024-04-25 | Government of the Philipppiens | 49000 | 49000 |  | 49000 | 49000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1276 | SPAREPARTS (MOTORCYCLE) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-01 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-23 | 2024-04-26 |  |  | 2024-04-26 | 2024-04-26 | Government of the Philipppiens | 8650 | 8650 |  | 8650 | 8650 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1271 | SPAREPARTS (MOTORCYCLE) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-01 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-25 | 2024-04-30 |  |  | 2024-04-30 | 2024-04-30 | Government of the Philipppiens | 3180 | 3180 |  | 3180 | 3180 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1250 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-01 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-25 | 2024-04-29 |  |  | 2024-04-29 | 2024-04-29 | Government of the Philipppiens | 30750 | 30750 |  | 30750 | 30750 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1253 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-01 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-25 | 2024-04-29 |  |  | 2024-04-29 | 2024-04-29 | Government of the Philipppiens | 28600 | 28600 |  | 28600 | 28600 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1254 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-01 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-25 | 2024-04-29 |  |  | 2024-04-29 | 2024-04-29 | Government of the Philipppiens | 10000 | 10000 |  | 10000 | 10000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1283 | SPAREPARTS (MOTORCYCLE) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-01 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-23 | 2024-04-26 |  |  | 2024-04-26 | 2024-04-26 | Government of the Philipppiens | 10500 | 10500 |  | 10500 | 10500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1205 | SPAREPARTS (MOTORCYCLE) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-01 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-25 | 2024-04-30 |  |  | 2024-04-30 | 2024-04-30 | Government of the Philipppiens | 12300 | 12300 |  | 12300 | 12300 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1172 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-01 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-23 | 2024-04-25 |  |  | 2024-04-25 | 2024-04-25 | Government of the Philipppiens | 14800 | 14800 |  | 14800 | 14800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1202 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-01 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-23 | 2024-04-25 |  |  | 2024-04-25 | 2024-04-25 | Government of the Philipppiens | 50400 | 50400 |  | 50400 | 50400 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1197 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-01 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-23 | 2024-04-25 |  |  | 2024-04-25 | 2024-04-25 | Government of the Philipppiens | 40000 | 40000 |  | 40000 | 40000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1204 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-01 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-23 | 2024-04-25 |  |  | 2024-04-25 | 2024-04-25 | Government of the Philipppiens | 2200 | 2200 |  | 2200 | 2200 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1180 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-01 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-23 | 2024-04-25 |  |  | 2024-04-25 | 2024-04-25 | Government of the Philipppiens | 10300 | 10300 |  | 10300 | 10300 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1190 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-01 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-25 | 2024-04-29 |  |  | 2024-04-29 | 2024-04-29 | Government of the Philipppiens | 12900 | 12900 |  | 12900 | 12900 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1198 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-01 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-23 | 2024-04-25 |  |  | 2024-04-25 | 2024-04-25 | Government of the Philipppiens | 8950 | 8950 |  | 8950 | 8950 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1233 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-01 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-22 | 2024-04-30 |  |  | 2024-04-30 | 2024-04-30 | Government of the Philipppiens | 3500 | 3500 |  | 3500 | 3500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1230 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-01 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-16 | 2024-04-22 |  |  | 2024-04-22 | 2024-04-22 | Government of the Philipppiens | 5000 | 5000 |  | 5000 | 5000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1330 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-01 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-04 | 2024-04-12 |  |  | 2024-04-12 | 2024-04-12 | Government of the Philipppiens | 15550 |  | 15550 | 15550 | 0 | 15550 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1569 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-01 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-25 | 2024-04-29 |  |  | 2024-04-29 | 2024-04-29 | Government of the Philipppiens | 25500 | 25500 |  | 25500 | 25500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1235 | SPAREPARTS (MOTORCYCLE) | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | 2024-03-05 | 2024-03-08 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-16 | 2024-04-18 |  |  | 2024-04-18 | 2024-04-18 | Government of the Philipppiens | 2640 | 2640 |  | 2640 | 2640 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1024 | FUEL, OIL, AND LUBRICANTS | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | 2024-03-05 | 2024-03-08 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-22 | 2024-04-30 |  |  | 2024-04-30 | 2024-04-30 | Government of the Philipppiens | 2960 | 2960 |  | 2960 | 2960 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1545 | JOB ORDER (LABOR & MATERIALS) | PDRRMO | No | Shopping 52.1(a) - Unforeseen Contingency | 2024-03-05 | 2024-03-08 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-04 | 2024-04-12 |  |  | 2024-04-12 | 2024-04-12 | Government of the Philipppiens | 4500 |  | 4500 | 4500 |  | 4500 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0115 | SPAREPARTS (MOTORCYCLE) | COA | No | NP-53.9 - Small Value Procurement | N/A | 2024-01-27 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-08 | 2024-04-15 |  |  | 2024-04-24 | 2024-04-24 | Government of the Philipppiens | 4510 | 4510 |  | 4510 | 4510 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0875 | FURNITURE & FIXTURES | SPO | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-22 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-05-27 | 2024-06-03 |  |  | 2024-06-06 | 2024-06-06 | Government of the Philipppiens | 7000 | 7000 |  | 7000 | 7000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0754 | CONSTRUCTION SUPPLIES | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-01 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-04 | 2024-04-15 |  |  | 2024-05-29 | 2024-05-29 | Government of the Philipppiens | 35950 |  | 35950 | 35890 |  | 35890 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1115 | SAFETY GEARS | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-01 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-04 | 2024-04-12 |  |  | 2024-05-14 | 2024-05-14 | Government of the Philipppiens | 40490 |  | 40490 | 40432 |  | 40432 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0529 | LABORATORY SUPPLIES | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-01 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-04 | 2024-04-12 |  |  | 2024-05-14 | 2024-05-14 | Government of the Philipppiens | 10200 |  | 10200 | 10183 |  | 10183 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0032 | SAFETY GEARS & EQUIPMENT | PTO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-01 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-08 | 2024-04-12 |  |  | 2024-04-29 | 2024-04-29 | Government of the Philipppiens | 18480 | 18480 |  | 18441.5 | 18441.5 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1301 | OFFICE EQUIPMENT | PAO-ADMIN | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-01 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | 2024-03-27 | 2024-04-04 | 2024-04-12 |  |  | 2024-05-06 | 2024-05-06 | Government of the Philipppiens | 53790 |  | 53790 | 52989 |  | 52989 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1394 | PRINTERS | PTO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-01 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-08 | 2024-04-12 |  |  | 2024-04-15 | 2024-04-15 | Government of the Philipppiens | 14500 | 14500 |  | 14406 | 14406 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1228 | TARPAULIN | PAO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-01 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-04 | 2024-04-12 |  |  | 2024-06-07 | 2024-06-07 | Government of the Philipppiens | 9800 |  | 9800 | 9800 |  | 9800 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0706 | FOOD/CATERING SERVICES | PAO-ADMIN | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-01 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | 2024-03-25 | 2024-04-04 | 2024-04-16 |  |  | 2024-06-11 | 2024-06-11 | Government of the Philipppiens | 100000 |  | 100000 | 97200 |  | 97200 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1098 | OTHER SUPPLIES & MATERIALS | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-01 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | 2024-03-27 | 2024-04-04 | 2024-04-15 |  |  | 2024-05-03 | 2024-05-03 | Government of the Philipppiens | 459943.2 |  | 459943.2 | 439600 |  | 439600 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1170 | FOOD/CATERING SERVICES | PAO-ADMIN | No | NP-53.9 - Small Value Procurement | 2024-03-05 | 2024-03-08 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | 2024-03-25 | 2024-04-04 | 2024-04-16 |  |  | 2024-06-18 | 2024-06-18 | Government of the Philipppiens | 63750 |  | 63750 | 61125 |  | 61125 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1137 | FOOD/CATERING SERVICES | PGO | No | NP-53.9 - Small Value Procurement | 2024-03-05 | 2024-03-08 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | 2024-03-25 | 2024-05-07 | 2024-05-10 |  |  | 2024-03-25 | 2024-03-25 | Government of the Philipppiens | 251000 |  | 251000 | 251000 |  | 251000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C0990 | FOOD/CATERING SERVICES | PENRO | No | NP-53.9 - Small Value Procurement | 2024-03-05 | 2024-03-08 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | 2024-03-25 | 2024-04-08 | 2024-04-11 |  |  | 2024-05-16 | 2024-05-16 | Government of the Philipppiens | 160260 |  | 160260 | 160260 |  | 160260 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C0996 | FOOD/CATERING SERVICES | PHRMDO | No | NP-53.9 - Small Value Procurement | 2024-03-05 | 2024-03-08 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | 2024-03-25 | 2024-04-03 | 2024-04-03 |  |  | 2024-03-26 | 2024-03-26 | Government of the Philipppiens | 242990 |  | 242990 | 242990 |  | 242990 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1391 | FOOD CATERING/SERVICES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-08 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | 2024-04-03 | 2024-04-04 | 2024-04-15 |  |  | 2024-05-31 | 2024-05-31 | Government of the Philipppiens | 180000 | 180000 |  | 179798.75 | 179798.75 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1127 | FOOD CATERING/SERVICES | PTO | No | NP-53.9 - Small Value Procurement | 2024-03-05 | 2024-03-08 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | 2024-03-25 | 2024-04-05 | 2024-04-15 |  |  | 2024-05-23 | 2024-05-23 | Government of the Philipppiens | 117300 | 117300 |  | 117300 | 117300 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1116 | JANITORIAL SUPPLIES | PDRRMO | No | NP-53.9 - Small Value Procurement | 2024-03-05 | 2024-03-08 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | 2024-04-01 | 2024-04-05 | 2024-04-12 |  |  | 2024-04-24 | 2024-04-24 | Government of the Philipppiens | 174490 |  | 174490 | 174240 |  | 174240 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1555 | OFFICE EQUIPMENT | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-12 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-04 | 2024-04-12 |  |  | 2024-04-24 | 2024-04-24 | Government of the Philipppiens | 26400 |  | 26400 | 26200 |  | 26200 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1078 | JANITORIAL SUPPLIES | PAO-ADMIN | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-08 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | 2024-03-27 | 2024-04-05 | 2024-04-12 |  |  | 2024-04-25 | 2024-04-25 | Government of the Philipppiens | 54864 | 54864 |  | 54665 | 54665 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1111 | COMPUTER SUPPLIES | PENRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-01 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-05 | 2024-04-12 |  |  | 2024-05-28 | 2024-05-28 | Government of the Philipppiens | 18995 |  | 18995 | 18991 |  | 18991 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0148 | OFFICE EQUIPMENT | PPDO | No | NP-53.9 - Small Value Procurement | 2024-03-05 | 2024-03-08 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-08 | 2024-04-12 |  |  | 2024-05-28 | 2024-05-28 | Government of the Philipppiens | 26840 | 26840 |  | 26840 | 26840 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1346 | OFFICE EQUIPMENT | PPDO | No | NP-53.9 - Small Value Procurement | 2024-03-05 | 2024-03-08 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-08 | 2024-04-12 |  |  | 2024-04-26 | 2024-04-26 | Government of the Philipppiens | 7800 | 7800 |  | 7800 | 7800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1450 | JANITORIAL SUPPLIES/HOUSEKEEPING | PLO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-08 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-05 | 2024-04-12 |  |  | 2024-06-18 | 2024-06-18 | Government of the Philipppiens | 15193 | 15193 |  | 15141 | 15141 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1117 | SAFETY GEARS | PENRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-08 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-04 | 2024-04-15 |  |  | 2024-05-08 | 2024-05-08 | Government of the Philipppiens | 46680 |  | 46680 | 46331 |  | 46331 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1858 | GARMENTS | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-15 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-19 |  |  |  | 2024-03-19 | 2024-03-19 | 2024-03-19 |  |  | 2024-03-27 | 2024-03-27 | Government of the Philipppiens | 25000 |  | 25000 | 25000 |  | 25000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1035 | OFFICE SUPPLIES | PEO-GA | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-03-01 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | 2024-03-27 | 2024-04-23 | 2024-04-26 |  |  | 2024-05-06 | 2024-05-06 | Government of the Philipppiens | 70535 | 70535 |  | 69128 | 69128 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1332 | OFFICE SUPPLIES | PGO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2024-03-05 | 2024-03-08 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-11 | 2024-04-12 |  |  | 2024-04-29 | 2024-04-29 | Government of the Philipppiens | 28060 | 28060 |  | 28020 | 28020 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1092 | OFFICE SUPPLIES | PICTO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2024-03-05 | 2024-03-08 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | 2024-04-01 | 2024-04-05 | 2024-04-12 |  |  | 2024-04-29 | 2024-04-29 | Government of the Philipppiens | 76638 | 76638 |  | 76525 | 76525 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1376 | OFFICE SUPPLIES | PGO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-03-08 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-05 | 2024-04-12 |  |  | 2024-04-26 | 2024-04-26 | Government of the Philipppiens | 5540 |  | 5540 | 5540 |  | 5540 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1331 | OFFICE SUPPLIES | PGO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2024-03-05 | 2024-03-08 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | 2024-04-01 | 2024-04-11 | 2024-04-12 |  |  | 2024-05-06 | 2024-05-06 | Government of the Philipppiens | 68168 | 68168 |  | 67949 | 67949 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1096 | OFFICE SUPPLIES | PGO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-03-08 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | 2024-04-01 | 2024-04-11 | 2024-04-15 |  |  | 2024-04-22 | 2024-04-22 | Government of the Philipppiens | 94976 |  | 94976 | 93273 |  | 93273 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0877 | SPAREPARTS (PHOTOCOPIER MACHINE) | SPO | No | Direct Contracting | 2024-03-05 | 2024-03-08 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-16 | 2024-04-23 |  |  | 2024-05-16 | 2024-05-16 | Government of the Philipppiens | 3750 | 3750 |  | 3750 | 3750 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0073 | DUPLICATING PRODUCTS/SPAREPARTS | PACCO | No | Direct Contracting | N/A | 2024-03-01 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-23 | 2024-04-30 |  |  | 2024-05-02 | 2024-05-02 | Government of the Philipppiens | 35400 | 35400 |  | 35400 | 35400 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0896 | JANITORIAL SUPPLIES | PVGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-22 |  | N/A | 2024-03-22 | 2024-03-22 |  | N/A | N/A | 2024-03-25 |  |  |  | N/A | 2024-05-27 | 2024-06-13 |  |  | 2024-06-21 | 2024-06-21 | Government of the Philipppiens | 39995 | 39995 |  | 39830 | 39830 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1051 | SPORTS SUPPLIES & EQUIPMENT | SEF | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-22 |  | N/A | 2024-03-22 | 2024-03-22 |  | N/A | N/A | 2024-03-25 |  |  |  | 2024-04-02 | 2024-05-13 | 2024-05-20 |  |  | 2024-06-21 | 2024-06-21 | Government of the Philipppiens | 381709 |  | 381709 | 380983 |  | 380983 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1097 | JANITORIAL SUPPLIES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-22 |  | N/A | 2024-03-22 | 2024-03-22 |  | N/A | N/A | 2024-03-25 |  |  |  | 2024-04-02 | 2024-04-11 | 2024-04-23 |  |  | 2024-05-28 | 2024-05-28 | Government of the Philipppiens | 60718.5 | 60718.5 |  | 60256 | 60256 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1063 | TARPAULIN | PSWDO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-12 |  | N/A | 2024-03-22 | 2024-03-22 |  | N/A | N/A | 2024-03-25 |  |  |  | N/A | 2024-04-08 | 2024-04-12 |  |  | 2024-06-19 | 2024-06-19 | Government of the Philipppiens | 34692 | 34692 |  | 34692 | 34692 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1012 | PLUMBING SUPPLIES | PEEMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-08 |  | N/A | 2024-03-22 | 2024-03-22 |  | N/A | N/A | 2024-03-25 |  |  |  | 2024-04-04 | 2024-04-12 | 2024-04-25 |  |  | 2024-05-10 | 2024-05-10 | Government of the Philipppiens | 62860 | 62860 |  | 62504 | 62504 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1112 | LAMINATING MACHINE | PENRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-08 |  | N/A | 2024-03-22 | 2024-03-22 |  | N/A | N/A | 2024-03-25 |  |  |  | 2024-04-04 | 2024-04-05 | 2024-04-15 |  |  | 2024-04-24 | 2024-04-24 | Government of the Philipppiens | 51070 | 51070 |  | 51000 | 51000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1703 | COMPUTER SUPPLIES/SPAREPARTS | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-12 |  | N/A | 2024-03-22 | 2024-03-22 |  | N/A | N/A | 2024-03-25 |  |  |  | N/A | 2024-04-11 | 2024-04-15 |  |  | 2024-04-29 | 2024-04-29 | Government of the Philipppiens | 13312 |  | 13312 | 13280 |  | 13280 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1669 | JANITORIAL SUPPLIES/HOUSEKEEPING | PAO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-12 |  | N/A | 2024-03-22 | 2024-03-22 |  | N/A | N/A | 2024-03-25 |  |  |  | N/A | 2024-04-11 | 2024-04-15 |  |  | 2024-04-22 | 2024-04-22 | Government of the Philipppiens | 6048 |  | 6048 | 5878 |  | 5878 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1103 | SPAREPARTS AND BATTERY FOR GEN SET | PHO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-12 |  | N/A | 2024-03-22 | 2024-03-22 |  | N/A | N/A | 2024-03-25 |  |  |  | N/A | 2024-04-08 | 2024-04-12 |  |  | 2024-05-16 | 2024-05-16 | Government of the Philipppiens | 19239.32 | 19239.32 |  | 19221.4 | 19221.4 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1118 | PORTLAND CEMENT & PULLITUFF BODY FILLER | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-08 |  | N/A | 2024-03-22 | 2024-03-22 |  | N/A | N/A | 2024-03-25 |  |  |  | N/A | 2024-04-08 | 2024-04-12 |  |  | 2024-05-16 | 2024-05-16 | Government of the Philipppiens | 7780 |  | 7780 | 7770.5 |  | 7770.5 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1708 | PADLOCK | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-12 |  | N/A | 2024-03-22 | 2024-03-22 |  | N/A | N/A | 2024-03-25 |  |  |  | N/A | 2024-04-11 | 2024-04-12 |  |  | 2024-05-16 | 2024-05-16 | Government of the Philipppiens | 2200 |  | 2200 | 2198 |  | 2198 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1309 | TARPAULIN | PDRRMO | No | NP-53.9 - Small Value Procurement | 2024-03-05 | 2024-03-08 |  | N/A | 2024-03-22 | 2024-03-22 |  | N/A | N/A | 2024-03-25 |  |  |  | 2024-04-02 | 2024-04-08 | 2024-04-12 |  |  | 2024-06-05 | 2024-06-05 | Government of the Philipppiens | 140000 |  | 140000 | 125000 |  | 125000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1051 | OFFICE SUPPLIES | PHRMDO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2024-02-20 | 2024-02-22 |  | N/A | 2024-03-22 | 2024-03-22 |  | N/A | N/A | 2024-03-25 |  |  |  | 2024-04-02 | 2024-04-05 | 2024-04-12 |  |  | 2024-04-30 | 2024-04-30 | Government of the Philipppiens | 270846 |  | 270846 | 266761.95 |  | 266761.95 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1055 | OFFICE SUPPLIES | PSWDO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-02-22 |  | N/A | 2024-03-22 | 2024-03-22 |  | N/A | N/A | 2024-03-25 |  |  |  | 2024-04-04 | 2024-04-08 | 2024-04-15 |  |  | 2024-04-24 | 2024-04-24 | Government of the Philipppiens | 57597.4 | 57597.4 |  | 56023 | 56023 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0114 | OFFICE SUPPLIES | PGO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-02-22 |  | N/A | 2024-03-22 | 2024-03-22 |  | N/A | N/A | 2024-03-25 |  |  |  | N/A | 2024-04-05 | 2024-04-15 |  |  | 2024-04-22 | 2024-04-22 | Government of the Philipppiens | 5414 |  | 5414 | 5260 |  | 5260 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1135 | OFFICE SUPPLIES | PSWDO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2024-03-05 | 2024-03-08 |  | N/A | 2024-03-22 | 2024-03-22 |  | N/A | N/A | 2024-03-25 |  |  |  | 2024-04-02 | 2024-04-08 | 2024-04-12 |  |  | 2024-04-26 | 2024-04-26 | Government of the Philipppiens | 80912 |  | 80912 | 80912 |  | 80912 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1109 | OFFICE SUPPLIES | PDRRMO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-03-12 |  | N/A | 2024-03-22 | 2024-03-22 |  | N/A | N/A | 2024-03-25 |  |  |  | N/A | 2024-04-04 | 2024-04-15 |  |  | 2024-04-24 | 2024-04-24 | Government of the Philipppiens | 21336 |  | 21336 | 21268 |  | 21268 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1166 | OFFICE SUPPLIES | PBO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-03-12 |  | N/A | 2024-03-22 | 2024-03-22 |  | N/A | N/A | 2024-03-25 |  |  |  | N/A | 2024-04-08 | 2024-04-15 |  |  | 2024-04-26 | 2024-04-26 | Government of the Philipppiens | 27301 | 27301 |  | 27046 | 27046 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1162 | OFFICE SUPPLIES | PLO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-03-12 |  | N/A | 2024-03-22 | 2024-03-22 |  | N/A | N/A | 2024-03-25 |  |  |  | 2024-03-26 | 2024-04-05 | 2024-04-15 |  |  | 2024-04-24 | 2024-04-24 | Government of the Philipppiens | 78080 | 78080 |  | 76924 | 76924 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1145 | OFFICE SUPPLIES | PGO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-03-12 |  | N/A | 2024-03-22 | 2024-03-22 |  | N/A | N/A | 2024-03-25 |  |  |  | 2024-04-01 | 2024-05-07 | 2024-05-10 |  |  | 2024-05-13 | 2024-05-13 | Government of the Philipppiens | 66552 |  | 66552 | 64724 |  | 64724 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1713 | JOB OUT | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-25 |  | N/A | 2024-04-02 | 2024-04-02 |  | N/A | N/A | 2024-04-04 |  |  |  | N/A | 2024-04-12 | 2024-05-08 |  |  | 2024-05-08 | 2024-05-08 | Government of the Philipppiens | 3500 | 3500 |  | 3500 | 3500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1786 | SPAREPARTS (HEAVY EQUIPT) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-25 |  | N/A | 2024-04-02 | 2024-04-02 |  | N/A | N/A | 2024-04-04 |  |  |  | N/A | 2024-04-12 | 2024-05-08 |  |  | 2024-05-08 | 2024-05-08 | Government of the Philipppiens | 1500 | 1500 |  | 1500 | 1500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1234 | SPAREPARTS (MOTORCYCLE) | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-25 |  | N/A | 2024-04-02 | 2024-04-02 |  | N/A | N/A | 2024-04-04 |  |  |  | N/A | 2024-04-24 | 2024-04-30 |  |  | 2024-04-30 | 2024-04-30 | Government of the Philipppiens | 1100 | 1100 |  | 1100 | 1100 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0264 | BOX FILE TOP AND SIDE OPENING | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-22 |  | N/A | 2024-04-02 | 2024-04-02 |  | N/A | N/A | 2024-04-04 |  |  |  | N/A | 2024-04-24 | 2024-05-07 |  |  | 2024-06-21 | 2024-06-21 | Government of the Philipppiens | 1180 |  | 1180 | 1178 |  | 1178 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1099 | JANITORIAL SUPPLIES | PASSO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-01 |  | N/A | 2024-04-02 | 2024-04-02 |  | N/A | N/A | 2024-04-04 |  |  |  | N/A | 2024-04-23 | 2024-05-10 |  |  | 2024-06-21 | 2024-06-21 | Government of the Philipppiens | 41732 |  | 41732 | 41610.5 |  | 41610.5 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0527 | GLOVES, LAUNDRY | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-01 |  | N/A | 2024-04-02 | 2024-04-02 |  | N/A | N/A | 2024-04-04 |  |  |  | N/A | 2024-04-24 | 2024-05-07 |  |  | 2024-05-28 | 2024-05-28 | Government of the Philipppiens | 1104 |  | 1104 | 1080 |  | 1080 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0031 | TRAINING FOLDING TABLE | PTO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-01 |  | N/A | 2024-04-02 | 2024-04-02 |  | N/A | N/A | 2024-04-04 |  |  |  | N/A | 2024-04-17 | 2024-05-07 |  |  | 2024-05-28 | 2024-05-28 | Government of the Philipppiens | 13860 | 13860 |  | 13500 | 13500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1086 | BRAKE FLUID | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-01 |  | N/A | 2024-04-02 | 2024-04-02 |  | N/A | N/A | 2024-04-04 |  |  |  | N/A | 2024-04-24 | 2024-04-30 |  |  | 2024-05-16 | 2024-05-16 | Government of the Philipppiens | 19592 |  | 19592 | 19260 |  | 19260 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0269 | GARMENTS | PENRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-20 |  | N/A | 2024-04-02 | 2024-04-02 |  | N/A | N/A | 2024-04-04 |  |  |  | N/A | 2024-04-24 | 2024-04-30 |  |  | 2024-05-27 | 2024-05-27 | Government of the Philipppiens | 12000 | 12000 |  | 11400 | 11400 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1756 | FOOD/CATERING SERVICES | PAO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-20 |  | N/A | 2024-04-02 | 2024-04-02 |  | N/A | N/A | 2024-04-04 |  |  |  | N/A | 2024-04-18 | 2024-04-18 |  |  | 2024-05-28 | 2024-05-28 | Government of the Philipppiens | 30000 | 30000 |  | 30000 | 30000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1735 | FOOD/CATERING SERVICES | PAO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-20 |  | N/A | 2024-04-02 | 2024-04-02 |  | N/A | N/A | 2024-04-04 |  |  |  | 2024-04-08 | 2024-04-19 | 2024-05-07 |  |  | 2024-06-13 | 2024-06-13 | Government of the Philipppiens | 150000 |  | 150000 | 148250 |  | 148250 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1212 | ELECTRICAL SUPPLIES | PHO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-20 |  | N/A | 2024-04-02 | 2024-04-02 |  | N/A | N/A | 2024-04-04 |  |  |  | 2024-04-11 | 2024-04-23 | 2024-05-14 |  |  | 2024-05-14 | 2024-05-14 | Government of the Philipppiens | 65650 | 65650 |  | 40400 | 40400 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1798 | FOOD/CATERING SERVICES | PIAO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-20 |  | N/A | 2024-04-02 | 2024-04-02 |  | N/A | N/A | 2024-04-04 |  |  |  | N/A | 2024-04-23 | 2024-04-25 |  |  | 2024-06-18 | 2024-06-18 | Government of the Philipppiens | 17000 | 17000 |  | 16500 | 16500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1523 | KITCHENWARE & UTENSILS | PAO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-20 |  | N/A | 2024-04-02 | 2024-04-02 |  | N/A | N/A | 2024-04-04 |  |  |  | N/A | 2024-04-24 | 2024-04-26 |  |  | 2024-05-06 | 2024-05-06 | Government of the Philipppiens | 17680 | 17680 |  | 17670 | 17670 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1108 | AGRICULTURAL SUPPLIES | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-20 |  | N/A | 2024-04-02 | 2024-04-02 |  | N/A | N/A | 2024-04-04 |  |  |  | N/A | 2024-04-24 | 2024-04-26 |  |  | 2024-05-28 | 2024-05-28 | Government of the Philipppiens | 12320 |  | 12320 | 12316 |  | 12316 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1188 | VETERINARY DRUGS AND BIOLOGICS | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-20 |  | N/A | 2024-04-02 | 2024-04-02 |  | N/A | N/A | 2024-04-04 |  |  |  | 2024-04-05 | 2024-04-12 | 2024-05-10 |  |  | 2024-06-03 | 2024-06-03 | Government of the Philipppiens | 83500 |  | 83500 | 83266 |  | 83266 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1617 | FOOD/CATERING SERVICES | PBO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-20 |  | N/A | 2024-04-02 | 2024-04-02 |  | N/A | N/A | 2024-04-04 |  |  |  | N/A | 2024-04-24 | 2024-04-29 |  |  | 2024-06-21 | 2024-06-21 | Government of the Philipppiens | 25500 | 25500 |  | 24975 | 24975 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1297 | ELECTRICAL SUPPLIES | PGSO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-20 |  | N/A | 2024-04-02 | 2024-04-02 |  | N/A | N/A | 2024-04-04 |  |  |  | N/A | 2024-04-23 | 2024-05-06 |  |  | 2024-05-31 | 2024-05-31 | Government of the Philipppiens | 20400 | 20400 |  | 20388 | 20388 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1131 | SAFETY GEARS | PGSO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-20 |  | N/A | 2024-04-02 | 2024-04-02 |  | N/A | N/A | 2024-04-04 |  |  |  | N/A | 2024-04-23 | 2024-05-08 |  |  | 2024-06-10 | 2024-06-10 | Government of the Philipppiens | 37641.3 | 37641.3 |  | 24750 | 24750 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1473 | FURNITURE & FIXTURES | PAO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-12 |  | N/A | 2024-04-02 | 2024-04-02 |  | N/A | N/A | 2024-04-04 |  |  |  | 2024-04-12 | 2024-04-24 | 2024-05-14 |  |  | 2024-05-22 | 2024-05-22 | Government of the Philipppiens | 64400 |  | 64400 | 64395 |  | 64395 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1652 | JANITORIAL SUPPLIES/HOUSEKEEPING | PTO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-20 |  | N/A | 2024-04-02 | 2024-04-02 |  | N/A | N/A | 2024-04-04 |  |  |  | N/A | 2024-04-12 | 2024-04-26 |  |  | 2024-05-06 | 2024-05-06 | Government of the Philipppiens | 14457 | 14457 |  | 14077 | 14077 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1069 | LUBRICANTS | PDRRMO | No | NP-53.9 - Small Value Procurement | 2024-03-05 | 2024-03-08 |  | N/A | 2024-04-02 | 2024-04-02 |  | N/A | N/A | 2024-04-04 |  |  |  | 2024-04-08 | 2024-04-24 | 2024-05-07 |  |  | 2024-05-14 | 2024-05-14 | Government of the Philipppiens | 133717 | 133717 |  | 131105 | 131105 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1182 | BATTERY & EXTENSION WIRE | PAGRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-20 |  | N/A | 2024-04-02 | 2024-04-02 |  | N/A | N/A | 2024-04-04 |  |  |  | N/A | 2024-04-19 | 2024-04-23 |  |  | 2024-05-03 | 2024-05-03 | Government of the Philipppiens | 5004 |  | 5004 | 4978 |  | 4978 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1801 | JANITORIAL SUPPLIES/HOUSEKEEPING | PIAO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-20 |  | N/A | 2024-04-02 | 2024-04-02 |  | N/A | N/A | 2024-04-04 |  |  |  | N/A | 2024-04-24 | 2024-04-26 |  |  | 2024-05-03 | 2024-05-03 | Government of the Philipppiens | 6397 | 6397 |  | 6170 | 6170 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1684 | JANITORIAL SUPPLIES/HOUSEKEEPING | PAO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-20 |  | N/A | 2024-04-02 | 2024-04-02 |  | N/A | N/A | 2024-04-04 |  |  |  | N/A | 2024-04-24 | 2024-04-26 |  |  | 2024-05-03 | 2024-05-03 | Government of the Philipppiens | 8120.5 | 8120.5 |  | 8055 | 8055 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1686 | CONSTRUCTION SUPPLIES | PAO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-20 |  | N/A | 2024-04-02 | 2024-04-02 |  | N/A | N/A | 2024-04-04 |  |  |  | N/A | 2024-04-24 | 2024-04-26 |  |  | 2024-05-03 | 2024-05-03 | Government of the Philipppiens | 1350 | 1350 |  | 1340 | 1340 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1100 | CONSTRUCTION SUPPLIES | PAGRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-20 |  | N/A | 2024-04-02 | 2024-04-02 |  | N/A | N/A | 2024-04-04 |  |  |  | N/A | 2024-04-24 | 2024-04-26 |  |  | 2024-05-06 | 2024-05-06 | Government of the Philipppiens | 5905 | 5905 |  | 5773 | 5773 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1187 | FAUCET & SILICONE GASKET | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-20 |  | N/A | 2024-04-02 | 2024-04-02 |  | N/A | N/A | 2024-04-04 |  |  |  | N/A | 2024-04-24 | 2024-04-26 |  |  | 2024-05-03 | 2024-05-03 | Government of the Philipppiens | 3940 |  | 3940 | 3905 |  | 3905 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1678 | KITCHENWARE & UTENSILS | PAO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-20 |  | N/A | 2024-04-02 | 2024-04-02 |  | N/A | N/A | 2024-04-04 |  |  |  | N/A | 2024-04-24 | 2024-04-26 |  |  | 2024-05-03 | 2024-05-03 | Government of the Philipppiens | 4675 | 4675 |  | 4665 | 4665 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1661 | PADLOCK (BIG) HEAVY DUTY | PTO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-20 |  | N/A | 2024-04-02 | 2024-04-02 |  | N/A | N/A | 2024-04-04 |  |  |  | N/A | 2024-04-17 | 2024-04-26 |  |  | 2024-05-03 | 2024-05-03 | Government of the Philipppiens | 84431 | 4400 | 80031 | 4360 | 4360 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1156 | FOOD SUPPLIES | PDRRMO | No | NP-53.2 Emergency Cases | N/A | 2024-03-05 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | 2024-03-07 | 2024-03-07 | 2024-03-10 |  |  | 2024-03-10 | 2024-03-10 | Government of the Philipppiens | 3104168 |  | 3104168 | 3076724 |  | 3076724 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1171 | OFFICE SUPPLIES | PAGRO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-03-20 |  | N/A | 2024-04-02 | 2024-04-02 |  | N/A | N/A | 2024-04-04 |  |  |  | 2024-04-05 | 2024-04-24 | 2024-04-26 |  |  | 2024-05-14 | 2024-05-14 | Government of the Philipppiens | 80031 |  | 80031 | 78316 |  | 78316 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C0988 | HEMOGLOBIN A1C | PEEMO | No | Direct Contracting | N/A | 2024-03-20 |  | N/A | 2024-04-02 | 2024-04-02 |  | N/A | N/A | 2024-04-04 |  |  |  | N/A | 2024-04-29 | 2024-05-24 |  |  | 2024-06-07 | 2024-06-07 | Government of the Philipppiens | 38340 | 38340 |  | 38340 | 38340 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C0943 | SUPPLY AND DELIVERY OF JANITORIAL SUPPLIES | PEEMO | No | Competitive Bidding | 2024-02-20 | 2024-02-26 |  | 2024-03-05 | 2024-03-19 | 2024-03-19 |  | 2024-03-19 | 2024-04-01 | 2024-04-04 |  |  |  | 2024-04-15 | 2024-04-30 | 2024-05-02 |  |  | 2024-05-10 | 2024-05-10 | Government of the Philipppiens | 1105816 | 1105816 |  | 1010945 | 1010945 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2024-03-01 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | N/A | Completed
24-C0999 | SUPPLY AND DELIVERY OF RICE (WELL-MILLED) 50KG/SACK | PGO | No | Competitive Bidding | 2024-02-20 | 2024-02-26 |  | 2024-03-05 | 2024-03-19 | 2024-03-19 |  | 2024-03-19 | 2024-04-01 | 2024-04-04 |  |  |  | 2024-04-08 | 2024-04-17 | 2024-04-26 |  |  | 2024-05-03 | 2024-05-03 | Government of the Philipppiens | 2276010 |  | 2276010 | 2105400 |  | 2105400 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2024-03-01 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | N/A | Completed
24-C1022 | SUPPLY AND DELIVERY OF MEALS AND SNACKS | PDRRMO | No | Competitive Bidding | N/A | 2024-03-05 |  | N/A | 2024-03-19 | 2024-03-19 |  | 2024-03-19 | 2024-04-01 | 2024-04-04 |  |  |  | 2024-04-04 | 2024-04-24 | 2024-04-29 |  |  | 2024-06-14 | 2024-06-14 | Government of the Philipppiens | 1130610 |  | 1130610 | 1117904 |  | 1117904 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | N/A | Completed
24-1395 | SUPPLY AND DELIVERY OF MEALS AND SNACKS WITH ACCOMMODATION | PWDO | No | Competitive Bidding | N/A | 2024-03-11 |  | N/A | 2024-03-19 | 2024-03-19 |  | 2024-03-19 | 2024-04-01 | 2024-04-04 |  |  |  | 2024-04-04 | 2024-04-05 | 2024-04-05 |  |  | 2024-04-12 | 2024-04-12 | Government of the Philipppiens | 653200 |  | 653200 | 651780 |  | 651780 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | N/A | Completed
24-C1020 | SUPPLY AND DELIVERY OF MEALS AND SNACKS | PVO | No | Competitive Bidding | 2024-03-05 | 2024-03-11 |  | N/A | 2024-03-19 | 2024-03-19 |  | 2024-03-19 | 2024-04-01 | 2024-04-04 |  |  |  | 2024-04-19 | 2024-04-19 | 2024-04-19 |  |  | 2024-05-14 | 2024-05-14 | Government of the Philipppiens | 802730 |  | 802730 | 790748 |  | 790748 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | N/A | Completed
24-C1120 | SUPPLY AND DELIVERY OF MEALS AND SNACKS | PSWDO | No | Competitive Bidding | 2024-03-05 | 2024-03-11 |  | N/A | 2024-03-19 | 2024-03-19 |  | 2024-03-19 | 2024-04-01 | 2024-04-04 |  |  |  | 2024-04-04 | 2024-04-23 | 2024-04-29 |  |  | 2024-05-23 | 2024-05-23 | Government of the Philipppiens | 795590 |  | 795590 | 784904 |  | 784904 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | N/A | Completed
24-C1121 | SUPPLY AND DELIVERY OF MEALS AND SNACKS | PGO | No | Competitive Bidding | 2024-03-05 | 2024-03-11 |  | N/A | 2024-03-19 | 2024-03-19 |  | 2024-03-19 | 2024-04-01 | 2024-04-04 |  |  |  | 2024-04-04 | 2024-04-15 | 2024-05-08 |  |  | 2024-05-24 | 2024-05-24 | Government of the Philipppiens | 414020 |  | 414020 | 408920 |  | 408920 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | N/A | Completed
24-1339 | SUPPLY AND DELIVERY OF MEALS AND SNACKS | PGO | No | Competitive Bidding | 2024-03-05 | 2024-03-11 |  | N/A | 2024-03-19 | 2024-03-19 |  | 2024-03-19 | 2024-04-01 | 2024-04-04 |  |  |  | 2024-04-04 | 2024-04-15 | 2024-04-19 |  |  | 2024-06-11 | 2024-06-11 | Government of the Philipppiens | 621000 |  | 621000 | 614960 |  | 614960 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | N/A | Completed
24-C0936 | OFFICE SUPPLIES | PPDO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-03-25 |  | N/A | 2024-04-03 | 2024-04-03 |  | N/A | N/A | 2024-04-04 |  |  |  | 2024-04-05 | 2024-04-24 | 2024-04-26 |  |  | 2024-05-08 | 2024-05-08 | Government of the Philipppiens | 261449 | 261449 |  | 255010 | 255010 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1331 | CONSTRUCTION SUPPLIES | PDRRMO | No | NP-53.2 Emergency Cases | N/A | 2024-04-03 |  | N/A | 2024-04-03 | 2024-04-03 |  | N/A | N/A | 2024-04-04 |  |  |  | 2024-04-04 | 2024-04-05 | 2024-04-08 |  |  | 2024-05-15 | 2024-05-15 | Government of the Philipppiens | 2599011.85 |  | 2599011.85 | 2594573.25 |  | 2594573.25 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0539 | OTHER SUPPLIES/MATERIALS | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-08 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-05 | 2024-04-12 |  |  | 2024-04-26 | 2024-04-26 | Government of the Philipppiens | 71288 |  | 71288 | 63232.8 |  | 63232.8 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1203 | SPORTS SUPPLIES & EQUIPMENT | SEF | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-25 |  | N/A | 2024-04-03 | 2024-04-03 |  | N/A | N/A | 2024-04-04 |  |  |  | 2024-04-05 | 2024-05-03 | 2024-05-06 |  |  | 2024-06-03 | 2024-06-03 | Government of the Philipppiens | 422848 |  | 422848 | 418361.5 |  | 418361.5 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1414 | SPAREPARTS (GRASS CUTTER) | PGSO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-20 |  | N/A | 2024-04-03 | 2024-04-03 |  | N/A | N/A | 2024-04-04 |  |  |  | N/A | 2024-04-12 | 2024-05-08 |  |  | 2024-05-24 | 2024-05-24 | Government of the Philipppiens | 15580 | 15580 |  | 15100 | 15100 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1417 | SPAREPARTS (MOTORCYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-03-05 | 2024-03-08 |  | N/A | 2024-04-03 | 2024-04-03 |  | N/A | N/A | 2024-04-04 |  |  |  | N/A | 2024-04-12 | 2024-05-21 |  |  | 2024-05-28 | 2024-05-28 | Government of the Philipppiens | 810 | 810 |  | 810 | 810 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1421 | SPAREPARTS (MOTORCYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-03-05 | 2024-03-08 |  | N/A | 2024-04-03 | 2024-04-03 |  | N/A | N/A | 2024-04-04 |  |  |  | N/A | 2024-04-12 | 2024-05-21 |  |  | 2024-05-28 | 2024-05-28 | Government of the Philipppiens | 8400 | 8400 |  | 8400 | 8400 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1279 | SPAREPARTS (MOTORCYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-03-05 | 2024-03-08 |  | N/A | 2024-04-03 | 2024-04-03 |  | N/A | N/A | 2024-04-04 |  |  |  | N/A | 2024-04-12 | 2024-05-21 |  |  | 2024-05-28 | 2024-05-28 | Government of the Philipppiens | 9850 | 9850 |  | 9850 | 9850 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1204 | SPORTS UNIFORM | SEF | No | Competitive Bidding | N/A | 2024-03-14 |  | 2024-03-22 | 2024-04-03 | 2024-04-03 |  | 2024-04-03 | 2024-04-05 | 2024-04-05 |  |  |  | 2024-04-06 | 2024-04-08 | 2024-04-08 |  |  | 2024-04-24 | 2024-04-24 | Government of the Philipppiens | 1133060 |  | 1133060 | 1132791.75 |  | 1132791.75 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2024-03-21 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-01 | N/A | Completed
24-C1146 | MEDICAL SUPPLIES | PGO | No | Competitive Bidding | N/A | 2024-03-11 |  | N/A | 2024-03-19 | 2024-03-19 |  | 2024-03-19 | 2024-04-04 | 2024-04-06 |  |  |  | 2024-04-11 | 2024-04-30 | 2024-05-21 |  |  | 2024-06-19 | 2024-06-19 | Government of the Philipppiens | 323640 |  | 323640 | 152980 |  | 152980 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | N/A | Completed
24-1284 | SPAREPARTS (MOTORCYCLE) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2024-03-05 | 2024-03-20 |  | N/A | 2024-04-05 | 2024-04-05 |  | N/A | N/A | 2024-04-12 |  |  |  | N/A | 2024-04-23 | 2024-05-08 |  |  | 2024-05-08 | 2024-05-08 | Government of the Philipppiens | 31620 | 31620 |  | 31620 | 31620 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1570 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-20 |  | N/A | 2024-04-05 | 2024-04-05 |  | N/A | N/A | 2024-04-12 |  |  |  | N/A | 2024-04-23 | 2024-05-08 |  |  | 2024-05-08 | 2024-05-08 | Government of the Philipppiens | 8700 | 8700 |  | 8700 | 8700 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1154 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-20 |  | N/A | 2024-04-05 | 2024-04-05 |  | N/A | N/A | 2024-04-12 |  |  |  | N/A | 2024-04-23 | 2024-05-14 |  |  | 2024-05-14 | 2024-05-14 | Government of the Philipppiens | 52550 | 52550 |  | 52550 | 52550 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1685 | OFFICE SUPPLIES | PGO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-03-12 |  | N/A | 2024-04-05 | 2024-04-05 |  | N/A | N/A | 2024-04-12 |  |  |  | 2024-04-19 | 2024-04-23 | 2024-05-06 |  |  | 2024-05-16 | 2024-05-16 | Government of the Philipppiens | 53059 |  | 53059 | 52008 |  | 52008 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1614 | OFFICE SUPPLIES | PBO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-03-12 |  | N/A | 2024-04-05 | 2024-04-05 |  | N/A | N/A | 2024-04-12 |  |  |  | N/A | 2024-04-23 | 2024-05-07 |  |  | 2024-05-09 | 2024-05-09 | Government of the Philipppiens | 12405 | 12405 |  | 40779 | 12400 | 28379 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1150 | OFFICE SUPPLIES | PGO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-03-12 |  | N/A | 2024-04-05 | 2024-04-05 |  | N/A | N/A | 2024-04-12 |  |  |  | N/A | 2024-04-24 | 2024-04-30 |  |  | 2024-05-07 | 2024-05-07 | Government of the Philipppiens | 5983 |  | 5983 | 5968 |  | 5968 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1682 | OFFICE SUPPLIES | PGO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-03-12 |  | N/A | 2024-04-05 | 2024-04-05 |  | N/A | N/A | 2024-04-12 |  |  |  | N/A | 2024-04-24 | 2024-04-30 |  |  | 2024-05-07 | 2024-05-07 | Government of the Philipppiens | 16927 |  | 16927 | 16921 |  | 16921 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1688 | OFFICE SUPPLIES | PGO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-03-20 |  | N/A | 2024-04-05 | 2024-04-05 |  | N/A | N/A | 2024-04-12 |  |  |  | N/A | 2024-04-17 | 2024-04-30 |  |  | 2024-05-16 | 2024-05-16 | Government of the Philipppiens | 29402 |  | 29402 | 28379 |  | 28379 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1200 | OFFICE SUPPLIES | PIAO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-03-20 |  | N/A | 2024-04-05 | 2024-04-05 |  | N/A | N/A | 2024-04-12 |  |  |  | N/A | 2024-04-24 | 2024-04-30 |  |  | 2024-05-10 | 2024-05-10 | Government of the Philipppiens | 23780 | 23780 |  | 23308 | 23308 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1070 | SPAREPARTS (LIGHT VEHICLES) | PGO | No | NP-53.9 - Small Value Procurement | 2024-03-05 | 2024-03-08 |  | N/A | 2024-04-05 | 2024-04-05 |  | N/A | N/A | 2024-04-12 |  |  |  | 2024-04-17 | 2024-04-24 | 2024-04-29 |  |  | 2024-05-08 | 2024-05-08 | Government of the Philipppiens | 350000 |  | 350000 | 350000 |  | 350000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1429 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-03-05 | 2024-03-08 |  | N/A | 2024-04-05 | 2024-04-05 |  | N/A | N/A | 2024-04-12 |  |  |  | N/A | 2024-04-23 | 2024-05-23 |  |  | 2024-05-28 | 2024-05-28 | Government of the Philipppiens | 40500 | 40500 |  | 40500 | 40500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1658 | LEAFLETS, LEGAL SIZE | PTO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-20 |  | N/A | 2024-04-05 | 2024-04-05 |  | N/A | N/A | 2024-04-12 |  |  |  | 2024-04-16 | 2024-04-23 | 2024-05-08 |  |  | 2024-05-16 | 2024-05-16 | Government of the Philipppiens | 50000 | 50000 |  | 44000 | 44000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1425 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-03-05 | 2024-03-08 |  | N/A | 2024-04-05 | 2024-04-05 |  | N/A | N/A | 2024-04-12 |  |  |  | N/A | 2024-04-23 | 2024-05-13 |  |  | 2024-05-14 | 2024-05-14 | Government of the Philipppiens | 8500 | 8500 |  | 8500 | 8500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1419 | SPAREPARTS (MOTORCYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-03-05 | 2024-03-08 |  | N/A | 2024-04-05 | 2024-04-05 |  | N/A | N/A | 2024-04-12 |  |  |  | N/A | 2024-04-23 | 2024-05-23 |  |  | 2024-05-28 | 2024-05-28 | Government of the Philipppiens | 8415 | 8415 |  | 8415 | 8415 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1430 | TARPAULIN | PEO | No | NP-53.9 - Small Value Procurement | 2024-03-05 | 2024-03-08 |  | N/A | 2024-04-05 | 2024-04-05 |  | N/A | N/A | 2024-04-12 |  |  |  | N/A | 2024-04-23 | 2024-05-14 |  |  | 2024-05-22 | 2024-05-22 | Government of the Philipppiens | 1792 |  | 1792 | 1779.2 |  | 1779.2 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0029 | STICKER, OUTDOOR | PTO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-08 |  | N/A | 2024-04-05 | 2024-04-05 |  | N/A | N/A | 2024-04-12 |  |  |  | N/A | 2024-04-25 | 2024-05-14 |  |  | 2024-05-22 | 2024-05-22 | Government of the Philipppiens | 14000 | 14000 |  | 14000 | 14000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1618 | JANITORIAL SUPPLIES/HOUSEKEEPING | PHO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-12 |  | N/A | 2024-04-05 | 2024-04-05 |  | N/A | N/A | 2024-04-12 |  |  |  | N/A | 2024-04-23 | 2024-05-07 |  |  | 2024-05-09 | 2024-05-09 | Government of the Philipppiens | 1339 | 1339 |  | 1339 | 1339 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1113 | PRINTER, INK TANK SYSTEM | PHO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-12 |  | N/A | 2024-04-05 | 2024-04-05 |  | N/A | N/A | 2024-04-12 |  |  |  | N/A | 2024-04-23 | 2024-05-07 |  |  | 2024-05-09 | 2024-05-09 | Government of the Philipppiens | 43500 | 43500 |  | 43494 | 43494 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1085 | TARPAULIN | PENRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-12 |  | N/A | 2024-04-05 | 2024-04-05 |  | N/A | N/A | 2024-04-12 |  |  |  | N/A | 2024-04-24 | 2024-04-30 |  |  | 2024-05-29 | 2024-05-29 | Government of the Philipppiens | 33964 |  | 33964 | 33721.4 |  | 33721.4 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1295 | PLASTIC STORAGE BOX | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-12 |  | N/A | 2024-04-05 | 2024-04-05 |  | N/A | N/A | 2024-04-12 |  |  |  | N/A | 2024-04-23 | 2024-05-07 |  |  | 2024-05-09 | 2024-05-09 | Government of the Philipppiens | 3200 |  | 3200 | 3196 |  | 3196 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1619 | PLASTIC UTILITY BOX | PBO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-12 |  | N/A | 2024-04-05 | 2024-04-05 |  | N/A | N/A | 2024-04-12 |  |  |  | N/A | 2024-04-23 | 2024-05-02 |  |  | 2024-05-31 | 2024-05-31 | Government of the Philipppiens | 1800 | 1800 |  | 1800 | 1800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1296 | ECO TANK ALL-IN-ONE INK PRINTER | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-12 |  | N/A | 2024-04-05 | 2024-04-05 |  | N/A | N/A | 2024-04-12 |  |  |  | N/A | 2024-04-19 | 2024-05-10 |  |  | 2024-05-13 | 2024-05-13 | Government of the Philipppiens | 15400 |  | 15400 | 15398 |  | 15398 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0366 | FOOD SUPPLIES | PSWDO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-12 |  | N/A | 2024-04-05 | 2024-04-05 |  | N/A | N/A | 2024-04-12 |  |  |  | N/A | 2024-04-23 | 2024-05-21 |  |  | 2024-06-06 | 2024-06-06 | Government of the Philipppiens | 21945 | 21945 |  | 21398 | 21398 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0954 | DISTILLED WATER | PAGRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-20 |  | N/A | 2024-04-05 | 2024-04-05 |  | N/A | N/A | 2024-04-12 |  |  |  | N/A | 2024-04-23 | 2024-05-07 |  |  | 2024-05-09 | 2024-05-09 | Government of the Philipppiens | 2970 |  | 2970 | 2960 |  | 2960 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1799 | COMPUTER SUPPLIES/SPAREPARTS | PIAO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-20 |  | N/A | 2024-04-05 | 2024-04-05 |  | N/A | N/A | 2024-04-12 |  |  |  | N/A | 2024-04-24 | 2024-04-29 |  |  | 2024-05-06 | 2024-05-06 | Government of the Philipppiens | 9000 | 9000 |  | 8900 | 8900 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1651 | COMPUTER SUPPLIES/SPAREPARTS | PTO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-20 |  | N/A | 2024-04-05 | 2024-04-05 |  | N/A | N/A | 2024-04-12 |  |  |  | N/A | 2024-04-25 | 2024-04-30 |  |  | 2024-05-06 | 2024-05-06 | Government of the Philipppiens | 4123 | 4123 |  | 4050 | 4050 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1680 | FOOD/CATERING SERVICES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-20 |  | N/A | 2024-04-05 | 2024-04-05 |  | N/A | N/A | 2024-04-12 |  |  |  | N/A | 2024-04-23 | 2024-04-26 |  |  | 2024-05-31 | 2024-05-31 | Government of the Philipppiens | 40800 |  | 40800 | 36000 |  | 36000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1409 | COMPUTER SUPPLIES/SPAREPARTS | PPDO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-20 |  | N/A | 2024-04-05 | 2024-04-05 |  | N/A | N/A | 2024-04-12 |  |  |  | N/A | 2024-04-24 | 2024-04-29 |  |  | 2024-05-06 | 2024-05-06 | Government of the Philipppiens | 5760 | 5760 |  | 5600 | 5600 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1691 | HAND CUFF | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-20 |  | N/A | 2024-04-05 | 2024-04-05 |  | N/A | N/A | 2024-04-12 |  |  |  | 2024-04-17 | 2024-04-24 | 2024-05-02 |  |  | 2024-05-31 | 2024-05-31 | Government of the Philipppiens | 108460 |  | 108460 | 106140 |  | 106140 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1693 | CHAIR, MONOBLOC | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-20 |  | N/A | 2024-04-05 | 2024-04-05 |  | N/A | N/A | 2024-04-12 |  |  |  | N/A | 2024-04-19 | 2024-05-08 |  |  | 2024-05-21 | 2024-05-21 | Government of the Philipppiens | 3900 |  | 3900 | 3850 |  | 3850 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1547 | WATER DISPENSER-HOT AND COLD | PAGRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-20 |  | N/A | 2024-04-05 | 2024-04-05 |  | N/A | N/A | 2024-04-12 |  |  |  | N/A | 2024-04-23 | 2024-05-07 |  |  | 2024-05-09 | 2024-05-09 | Government of the Philipppiens | 29200 | 13200 | 16000 | 13200 | 13200 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1130 | AGRICULTURAL (BOLO, GARBAGE BIN, GARBAGE HOSE) | PGSO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-12 |  | N/A | 2024-04-08 | 2024-04-08 |  | N/A | N/A | 2024-04-12 |  |  |  | 2024-04-17 | 2024-04-23 | 2024-05-08 |  |  | 2024-06-25 | 2024-06-25 | Government of the Philipppiens | 100252 | 94852 | 5400 | 94800 | 94800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1090 | TABLE NAME HOLDER | PGO | No | NP-53.9 - Small Value Procurement | 2024-03-19 | 2024-03-25 |  | N/A | 2024-04-08 | 2024-04-08 |  | N/A | N/A | 2024-04-12 |  |  |  | N/A | 2024-04-24 | 2024-04-30 |  |  | 2024-05-16 | 2024-05-16 | Government of the Philipppiens | 16000 |  | 16000 | 16000 |  | 16000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1431 | FOOD/CATERING SERVICES | PAO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-02 |  | N/A | 2024-04-08 | 2024-04-08 |  | N/A | N/A | 2024-04-12 |  |  |  | 2024-04-12 | 2024-04-23 | 2024-05-07 |  |  | 2024-05-15 | 2024-05-15 | Government of the Philipppiens | 56280 |  | 56280 | 55878 |  | 55878 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1420 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-03-19 | 2024-03-25 |  | N/A | 2024-04-08 | 2024-04-08 |  | N/A | N/A | 2024-04-12 |  |  |  | N/A | 2024-04-23 | 2024-05-14 |  |  | 2024-05-21 | 2024-05-21 | Government of the Philipppiens | 12500 | 12500 |  | 12000 | 12000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1101 | SPAREPARTS (LIGHT VEHICLES) | PAGRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-25 |  | N/A | 2024-04-08 | 2024-04-08 |  | N/A | N/A | 2024-04-12 |  |  |  | N/A | 2024-04-23 | 2024-05-08 |  |  | 2024-05-16 | 2024-05-16 | Government of the Philipppiens | 29760.89 | 29760.89 |  | 25730 | 25730 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1122 | MEDALS & PLAQUES | PSWDO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-25 |  | N/A | 2024-04-08 | 2024-04-08 |  | N/A | N/A | 2024-04-12 |  |  |  | 2024-04-16 | 2024-04-23 | 2024-05-14 |  |  | 2024-06-19 | 2024-06-19 | Government of the Philipppiens | 68058 |  | 68058 | 66948 |  | 66948 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1636 | FOOD/CATERING SERVICES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-02 |  | N/A | 2024-04-08 | 2024-04-08 |  | N/A | N/A | 2024-04-12 |  |  |  | 2024-04-12 | 2024-04-23 | 2024-05-13 |  |  | 2024-06-11 | 2024-06-11 | Government of the Philipppiens | 74460 | 74460 |  | 73584 | 73584 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1147 | MEDALS, PLAQUE, TROPHY & TOKEN | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-02 |  | N/A | 2024-04-08 | 2024-04-08 |  | N/A | N/A | 2024-04-12 |  |  |  | 2024-04-16 | 2024-04-23 | 2024-05-08 |  |  | 2024-06-26 | 2024-06-26 | Government of the Philipppiens | 83875 |  | 83875 | 83575 |  | 83575 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1202 | SPAREPARTS (HEAVY EQUIPT) | PEO-Motorpool | No | NP-53.9 - Small Value Procurement | 2024-03-22 | 2024-04-02 |  | N/A | 2024-04-08 | 2024-04-08 |  | N/A | N/A | 2024-04-12 |  |  |  | 2024-04-16 | 2024-04-17 | 2024-05-08 |  |  | 2024-06-10 | 2024-06-10 | Government of the Philipppiens | 250445 | 250445 |  | 239525 | 239525 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2322 | FOOD SUPPLIES | PGO | No | NP-53.9 - Small Value Procurement | 2024-04-02 | 2024-04-04 |  | N/A | 2024-04-08 | 2024-04-08 |  | N/A | N/A | 2024-04-12 |  |  |  | 2024-04-08 | 2024-04-08 | 2024-04-08 |  |  | 2024-04-08 | 2024-04-08 | Government of the Philipppiens | 288600 |  | 288600 | 277500 |  | 277500 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1881 | FOOD/CATERING SERVICES | PAO | No | NP-53.9 - Small Value Procurement | 2024-03-19 | 2024-03-25 |  | N/A | 2024-04-08 | 2024-04-08 |  | N/A | N/A | 2024-04-12 |  |  |  | 2024-04-12 | 2024-04-24 | 2024-04-29 |  |  | 2024-06-05 | 2024-06-05 | Government of the Philipppiens | 285000 |  | 285000 | 285000 |  | 285000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1174 | ACETYLENE REFILL AND INDUSTRIAL OXYGEN REFILL | PAGRO | No | Direct Contracting | 2024-03-22 | 2024-04-02 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-04-30 | 2024-05-10 |  |  | 2024-06-19 | 2024-06-19 | Government of the Philipppiens | 11640 |  | 11640 | 9265 |  | 9265 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1301 | EXPANDED NEWBORN SCREENING TEST | PEEMO | No | Direct Contracting | N/A | 2024-04-03 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-05-06 | 2024-06-13 |  |  | 2024-06-18 | 2024-06-18 | Government of the Philipppiens | 4046000 | 4046000 |  | 4046000 | 4046000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1311 | HEMATOLOGY ANALYZER | PEEMO | No | Direct Contracting | N/A | 2024-04-03 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-05-03 | 2024-05-24 |  |  | 2024-06-10 | 2024-06-10 | Government of the Philipppiens | 1102000 | 1102000 |  | 1102000 | 1102000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1309 | BLOOD UREA NITROGEN AND SERUM GLUTAMIC PYRUVIC TRANSAMINASE | PEEMO | No | Direct Contracting | N/A | 2024-04-03 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-05-17 | 2024-05-22 |  |  | 2024-06-03 | 2024-06-03 | Government of the Philipppiens | 52000 | 52000 |  | 52000 | 52000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2111 | TONER | PTO | No | Direct Contracting | 2024-04-02 | 2024-04-08 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-04-30 | 2024-05-15 |  |  | 2024-05-22 | 2024-05-22 | Government of the Philipppiens | 24092 | 24092 |  | 24092 | 24092 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2024 | OFFICE SUPPLIES | PGO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-03-25 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-05-10 | 2024-05-13 |  |  | 2024-05-20 | 2024-05-20 | Government of the Philipppiens | 17952 |  | 17952 | 17460 |  | 17460 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1211 | OFFICE SUPPLIES | SPO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-03-25 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-05-13 | 2024-05-21 |  |  | 2024-06-26 | 2024-06-26 | Government of the Philipppiens | 17129 | 17129 |  | 17040 | 17040 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1347 | OFFICE SUPPLIES | PGO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-03-25 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-05-06 | 2024-05-08 |  |  | 2024-05-13 | 2024-05-13 | Government of the Philipppiens | 4670 |  | 4670 | 4592 |  | 4592 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1195 | OFFICE SUPPLIES | PDRRMO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2024-03-22 | 2024-04-02 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-04-25 | 2024-05-13 |  |  | 2024-06-24 | 2024-06-24 | Government of the Philipppiens | 35025 |  | 35025 | 34536 |  | 34536 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1163 | OFFICE SUPPLIES | PLO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-03-25 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-04-30 | 2024-06-06 |  |  | 2024-06-14 | 2024-06-14 | Government of the Philipppiens | 22156 |  | 22156 | 21934 |  | 21934 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1780 | OFFICE SUPPLIES | PGO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-03-25 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-04-30 | 2024-05-13 |  |  | 2024-05-20 | 2024-05-20 | Government of the Philipppiens | 23985 | 23985 |  | 23099 | 23099 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1282 | OFFICE SUPPLIES | PTO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2024-03-22 | 2024-04-02 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | 2024-04-24 | 2024-04-30 | 2024-05-13 |  |  | 2024-05-21 | 2024-05-21 | Government of the Philipppiens | 137774 | 137774 |  | 135193 | 135193 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1563 | SPAREPARTS (HEAVY EQUIPT) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-03-19 | 2024-03-25 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-04-23 | 2024-05-23 |  |  | 2024-06-03 | 2024-06-03 | Government of the Philipppiens | 10300 | 10300 |  | 9530 | 9530 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1030 | COMPUTER SUPPLIES/SPAREPARTS | PAO | No | NP-53.9 - Small Value Procurement | 2024-03-22 | 2024-04-02 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-04-25 | 2024-05-08 |  |  | 2024-06-10 | 2024-06-10 | Government of the Philipppiens | 49772 | 49772 |  | 49650 | 49650 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1541 | COMPUTER SET WITH COMPLETE ACCESSORIES | PAO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-25 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-04-25 | 2024-05-06 |  |  | 2024-05-15 | 2024-05-15 | Government of the Philipppiens | 45000 | 45000 |  | 44900 | 44900 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0442 | HP-711 DESIGN JET PRINT HEAD REPLACEMENT | PPDO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-25 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-04-30 | 2024-05-13 |  |  | 2024-05-27 | 2024-05-27 | Government of the Philipppiens | 24900 | 24900 |  | 24900 | 24900 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1178 | JANITORIAL SUPPLIES | PAGRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-25 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-05-21 | 2024-05-22 |  |  | 2024-05-29 | 2024-05-29 | Government of the Philipppiens | 25296 |  | 25296 | 24692 |  | 24692 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0467 | LAGARAW (LIKONG) | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-25 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-04-30 | 2024-05-20 |  |  | 2024-06-26 | 2024-06-26 | Government of the Philipppiens | 22725 |  | 22725 | 22725 |  | 22725 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1483 | SPORTS SUPPLIES & EQUIPMENT | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-25 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-04-30 | 2024-05-10 |  |  | 2024-06-06 | 2024-06-06 | Government of the Philipppiens | 3360 |  | 3360 | 3360 |  | 3360 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2195 | MONEY DETECTOR & MONEY COUNTER | PTO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-25 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-04-30 | 2024-05-13 |  |  | 2024-05-20 | 2024-05-20 | Government of the Philipppiens | 20179 | 20179 |  | 20175 | 20175 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1594 | ELECTRIC HAND DRILL | PGSO | No | NP-53.9 - Small Value Procurement | 2024-03-19 | 2024-03-25 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-05-13 | 2024-05-23 |  |  | 2024-05-29 | 2024-05-29 | Government of the Philipppiens | 10720 | 10720 |  | 10710 | 10710 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0464 | BACK PACK | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-25 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-05-15 | 2024-05-20 |  |  | 2024-05-28 | 2024-05-28 | Government of the Philipppiens | 34500 |  | 34500 | 34500 |  | 34500 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1677 | MONITOR, COMPUTER | PTO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-25 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-04-30 | 2024-05-13 |  |  | 2024-05-24 | 2024-05-24 | Government of the Philipppiens | 7500 | 7500 |  | 7500 | 7500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1123 | WEIGHING SCALE | PHO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-25 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-05-06 | 2024-05-10 |  |  | 2024-05-21 | 2024-05-21 | Government of the Philipppiens | 570 |  | 570 | 570 |  | 570 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1988 | WIRE, EXTENSION WITH HANDLE | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-25 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-04-23 | 2024-05-06 |  |  | 2024-05-20 | 2024-05-20 | Government of the Philipppiens | 5280 |  | 5280 | 5268 |  | 5268 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2147 | BEEF LOAF | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-02 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-04-23 | 2024-05-07 |  |  | 2024-05-09 | 2024-05-09 | Government of the Philipppiens | 3740 |  | 3740 | 3730 |  | 3730 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1352 | HELMET, FULL FACED AND RAIN COAT | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-25 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-05-06 | 2024-05-16 |  |  | 2024-06-10 | 2024-06-10 | Government of the Philipppiens | 13400 |  | 13400 | 13400 |  | 13400 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1207 | ACCESSORIES & DECORATION | PAO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-25 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-05-09 | 2024-05-13 |  |  | 2024-05-21 | 2024-05-21 | Government of the Philipppiens | 5898 |  | 5898 | 5820 |  | 5820 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1262 | BOX, STORAGE, WHISTLE | PENRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-02 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-04-25 | 2024-05-10 |  |  | 2024-05-13 | 2024-05-13 | Government of the Philipppiens | 9860 |  | 9860 | 9768 |  | 9768 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1185 | MEDICAL SUPPLIES | PHO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-20 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | 2024-04-23 | 2024-04-29 | 2024-05-08 |  |  | 2024-06-26 | 2024-06-26 | Government of the Philipppiens | 209117 |  | 209117 | 208957 |  | 208957 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2010 | CHICK EMBRO CELL | PVO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-25 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-04-30 | 2024-05-22 |  |  | 2024-05-31 | 2024-05-31 | Government of the Philipppiens | 73600 |  | 73600 | 64905.08 |  | 64905.08 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1575 | JOB OUT-WHEEL ALIGNMENT & WHEEL BALANCING | PGSO | No | NP-53.9 - Small Value Procurement | 2024-03-19 | 2024-03-25 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-04-30 | 2024-05-14 |  |  | 2024-05-23 | 2024-05-23 | Government of the Philipppiens | 6300 | 6300 |  | 6300 | 6300 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1353 | VETERINARY DRUGS AND BIOLOGICS | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-25 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-04-30 | 2024-05-24 |  |  | 2024-05-28 | 2024-05-28 | Government of the Philipppiens | 21800 |  | 21800 | 20250 |  | 20250 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1593 | FIRE EXTINGUISHER & REFILL | PGSO | No | NP-53.9 - Small Value Procurement | 2024-03-19 | 2024-03-25 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-05-09 | 2024-05-16 |  |  | 2024-05-24 | 2024-05-24 | Government of the Philipppiens | 42845 | 42845 |  | 42550 | 42550 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1871 | JANITORIAL SUPPLIES/HOUSEKEEPING | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-25 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-04-23 | 2024-05-06 |  |  | 2024-05-14 | 2024-05-14 | Government of the Philipppiens | 25950 | 0 | 25950 | 25140 |  | 25140 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2120 | BATTERY | PENRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-02 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-04-23 | 2024-05-10 |  |  | 2024-05-27 | 2024-05-27 | Government of the Philipppiens | 7800 | 7800 |  | 7788 | 7788 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1472 | RICE, WELL MILLED | PGO | No | NP-53.9 - Small Value Procurement | 2024-03-19 | 2024-03-25 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | 2024-04-24 | 2024-05-06 | 2024-05-08 |  |  | 2024-05-16 | 2024-05-16 | Government of the Philipppiens | 128535 |  | 128535 | 127920 |  | 127920 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1278 | SPAREPARTS (MOTORCYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-03-19 | 2024-03-25 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-04-25 | 2024-05-23 |  |  | 2024-06-20 | 2024-06-20 | Government of the Philipppiens | 2280 | 2280 |  | 2280 | 2280 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1700 | COMPUTER KEYBOARD AND MOUSE | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-25 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-04-25 | 2024-05-06 |  |  | 2024-05-15 | 2024-05-15 | Government of the Philipppiens | 2894 | 0 | 2894 | 2790 |  | 2790 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1280 | SPAREPARTS (MOTORCYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-03-19 | 2024-03-25 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-04-25 | 2024-05-23 |  |  | 2024-06-20 | 2024-06-20 | Government of the Philipppiens | 9480 | 9480 |  | 9480 | 9480 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2093 | COLORED PRINTER W/ SCANNER | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-02 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-04-25 | 2024-05-06 |  |  | 2024-05-15 | 2024-05-15 | Government of the Philipppiens | 14500 |  | 14500 | 14500 |  | 14500 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0890 | OFFICE CHAIR W/ ARMS | PLO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-08 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-04-25 | 2024-05-14 |  |  | 2024-05-20 | 2024-05-20 | Government of the Philipppiens | 4400 | 4400 |  | 4250 | 4250 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1265 | MEDICAL KIT | SEF | No | NP-53.9 - Small Value Procurement | 2024-03-22 | 2024-04-02 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-04-25 | 2024-05-23 |  |  | 2024-06-06 | 2024-06-06 | Government of the Philipppiens | 1925 |  | 1925 | 1925 |  | 1925 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0516 | LAPTOP BAG | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-25 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-04-25 | 2024-05-08 |  |  | 2024-05-31 | 2024-05-31 | Government of the Philipppiens | 2500 |  | 2500 | 2500 |  | 2500 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1564 | SPAREPARTS (MOTORCYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-03-19 | 2024-03-25 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-04-25 | 2024-05-23 |  |  | 2024-05-28 | 2024-05-28 | Government of the Philipppiens | 8400 | 8400 |  | 8400 | 8400 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2048 | OIL FOR GRASS CUTTER | PVO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-25 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-04-25 | 2024-05-10 |  |  | 2024-05-21 | 2024-05-21 | Government of the Philipppiens | 5200 | 5200 |  | 5150 | 5150 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1565 | SPAREPARTS (MOTORCYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-03-19 | 2024-03-25 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-04-25 | 2024-05-23 |  |  | 2024-06-05 | 2024-06-05 | Government of the Philipppiens | 18570 | 18570 |  | 18570 | 18570 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1535 | CASING, SELF INKING STAMP | PAO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-02 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-04-25 | 2024-05-08 |  |  | 2024-05-16 | 2024-05-16 | Government of the Philipppiens | 4136 | 4136 |  | 4136 | 4136 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0249 | JOB ORDER (BOOKBINDING) | PAO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-12 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-04-25 | 2024-05-08 |  |  | 2024-06-28 | 2024-06-28 | Government of the Philipppiens | 10000 | 10000 |  | 10000 | 10000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1436 | CABINET, MOBILE | PENRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-08 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-04-25 | 2024-05-14 |  |  | 2024-05-20 | 2024-05-20 | Government of the Philipppiens | 14850 | 14850 |  | 13125 | 13125 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1427 | MEDICAL KIT | PEO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-08 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | N/A | 2024-04-23 | 2024-05-14 |  |  | 2024-05-20 | 2024-05-20 | Government of the Philipppiens | 1925 |  | 1925 | 1925 |  | 1925 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1339 | FOOD SUPPLIES | PDRRMO | No | NP-53.2 Emergency Cases | N/A | 2024-04-15 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-22 |  |  |  | 2024-04-22 | 2024-04-22 | 2024-04-26 |  |  | 2024-04-30 | 2024-04-30 | Government of the Philipppiens | 1679480 |  | 1679480 | 1663865 |  | 1663865 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1045 | OIL AND LUBRICANTS | PEO | No | Competitive Bidding | N/A | 2024-02-19 |  | 2024-03-05 | 2024-03-19 | 2024-03-19 |  | 2024-04-05 | 2024-04-05 | 2024-04-22 |  |  |  | 2024-04-23 | 2024-04-29 | 2024-05-21 |  |  | 2024-05-27 | 2024-05-27 | Government of the Philipppiens | 1343882.5 | 1343882.5 |  | 812840 | 812840 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2024-03-01 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | N/A | Completed
24-C0997 | SPAREPARTS (LIGHT VEHICLES) | PGSO-Inventory | No | Competitive Bidding | 2024-02-20 | 2024-02-26 |  | 2024-03-05 | 2024-03-19 | 2024-03-19 |  | 2024-04-11 | 2024-04-11 | 2024-04-22 |  |  |  | 2024-04-23 | 2024-04-30 | 2024-05-10 |  |  | 2024-06-10 | 2024-06-10 | Government of the Philipppiens | 4493654.28 | 4493654.28 |  | 1990169 | 1990169 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2024-03-01 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | N/A | Completed
24-C1002 | LABORATORY SUPPLIES | PEEMO | No | Competitive Bidding | N/A | 2024-02-19 |  | 2024-03-05 | 2024-03-19 | 2024-03-19 |  | 2024-03-19 | 2024-04-17 | 2024-04-29 |  |  |  | 2024-05-08 | 2024-05-13 | 2024-05-22 |  |  | 2024-06-11 | 2024-06-11 | Government of the Philipppiens | 1412808 | 1412808 |  | 911483 | 911483 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2024-03-01 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | N/A | Completed
24-C0928 | RACK MOUNTED SERVER AND SERVER MANAGEMENT SOFTWARE WITH CLOUD SUPPORT | PHO | No | Competitive Bidding | 2024-02-20 | 2024-02-26 |  | 2024-03-05 | 2024-03-19 | 2024-03-19 |  | 2024-03-19 | 2024-04-10 | 2024-04-29 |  |  |  | 2024-05-07 | 2024-05-17 | 2024-05-22 |  |  | 2024-06-14 | 2024-06-14 | Government of the Philipppiens | 516848.55 |  | 516848.55 | 510000 |  | 510000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2024-03-01 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | N/A | Completed
24-C1042 | TIRES | PEO | No | Competitive Bidding | 2024-02-20 | 2024-02-26 |  | 2024-03-05 | 2024-03-19 | 2024-03-19 |  | 2024-03-19 | 2024-04-11 | 2024-04-29 |  |  |  | 2024-05-08 | 2024-05-13 | 2024-05-22 |  |  | 2024-06-26 | 2024-06-26 | Government of the Philipppiens | 7001000 | 7001000 |  | 3994700 | 3994700 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2024-03-01 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | N/A | Completed
24-0905 | PUMP IRRIGATION SYSTEM OPEN SOURCE (PISOS)-PUMP & ENGINE SET | PAGRO | No | Competitive Bidding | 2024-02-20 | 2024-02-26 |  | 2024-03-05 | 2024-03-19 | 2024-03-19 |  | 2024-03-19 | 2024-04-19 | 2024-04-29 |  |  |  | 2024-05-08 | 2024-05-13 | 2024-05-29 |  |  | 2024-06-05 | 2024-06-05 | Government of the Philipppiens | 3000000 |  | 3000000 | 2970000 |  | 2970000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2024-03-01 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | N/A | Completed
24-C1011 | FLUIDS | PEEMO | No | Competitive Bidding | 2024-02-20 | 2024-02-26 |  | 2024-03-05 | 2024-03-19 | 2024-03-19 |  | 2024-03-19 | 2024-04-18 | 2024-04-29 |  |  |  | 2024-05-09 | 2024-05-20 | 2024-05-21 |  |  | 2024-05-28 | 2024-05-28 | Government of the Philipppiens | 1678204 | 1678204 |  | 1093996 | 1093996 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2024-03-01 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | N/A | Completed
24-C1095 | FUEL, OIL, AND LUBRICANTS | PGSO | No | Competitive Bidding | N/A | 2024-03-04 |  | 2024-03-19 | 2024-04-02 | 2024-04-02 |  | 2024-04-02 | 2024-04-11 | 2024-04-29 |  |  |  | 2024-05-06 | 2024-05-13 | 2024-05-23 |  |  | 2024-06-06 | 2024-06-06 | Government of the Philipppiens | 1548381.74 | 1548381.74 |  | 890290 | 890290 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2024-03-15 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-01 | N/A | Completed
24-C1136 | SPAREPARTS (SPAREPARTS) | PEO | No | Competitive Bidding | N/A | 2024-03-11 |  | 2024-03-19 | 2024-04-02 | 2024-04-02 |  | 2024-02-04 | 2024-04-24 | 2024-04-29 |  |  |  | 2024-05-07 | 2024-05-21 | 2024-05-23 |  |  | 2024-06-03 | 2024-06-03 | Government of the Philipppiens | 1823618 | 1823618 |  | 1684350 | 1684350 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2024-03-15 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-01 | N/A | Completed
24-C1088 | MEALS AND SNACKS WITH ACCOMMODATION | PDRRMO | No | Competitive Bidding | 2024-03-05 | 2024-03-25 |  | N/A | 2024-04-02 | 2024-04-02 |  | 2024-04-02 | 2024-04-17 | 2024-04-29 |  |  |  | 2024-05-02 | 2024-05-13 | 2024-05-23 |  |  | 2024-06-21 | 2024-06-21 | Government of the Philipppiens | 437400 |  | 437400 | 436995 |  | 436995 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-01 | N/A | Completed
24-C1076 | OFFICE SUPPLIES | PASSO | No | Competitive Bidding | N/A | 2024-03-25 |  | N/A | 2024-04-02 | 2024-04-02 |  | 2024-04-02 | 2024-04-23 | 2024-04-29 |  |  |  | 2024-05-08 | 2024-05-13 | 2024-05-21 |  |  | 2024-06-11 | 2024-06-11 | Government of the Philipppiens | 375571 |  | 375571 | 371631 |  | 371631 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-01 | N/A | Completed
24-0919 | MOLY BEARING GREASE | PEO | No | Competitive Bidding | N/A | 2024-03-25 |  | N/A | 2024-04-02 | 2024-04-02 |  | 2024-04-02 | 2024-04-24 | 2024-04-29 |  |  |  | 2024-05-09 | 2024-05-17 | 2024-05-22 |  |  | 2024-05-23 | 2024-05-23 | Government of the Philipppiens | 346800 | 346800 |  | 346104 | 346104 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-01 | N/A | Completed
24-C1143 | OFFICE SUPPLIES | PENRO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-04-02 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | 2024-05-06 | 2024-05-13 | 2024-05-22 |  |  | 2024-06-07 | 2024-06-07 | Government of the Philipppiens | 128635 |  | 128635 | 127596 |  | 127596 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1917 | OFFICE SUPPLIES | PGO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-04-02 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-05-15 | 2024-05-21 |  |  | 2024-05-27 | 2024-05-27 | Government of the Philipppiens | 1980 |  | 1980 | 1950 |  | 1950 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1271 | OFFICE SUPPLIES | SPO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-03-25 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-06-06 | 2024-06-11 |  |  | 2024-06-21 | 2024-06-21 | Government of the Philipppiens | 49648 | 49648 |  | 49483 | 49483 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1208 | OFFICE SUPPLIES | PVO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-04-03 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | 2024-05-07 | 2024-05-20 | 2024-05-24 |  |  | 2024-06-21 | 2024-06-21 | Government of the Philipppiens | 99064 | 99064 |  | 98676.5 | 98676.5 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1260 | OFFICE SUPPLIES | PHRMDO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2024-04-02 | 2024-04-08 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | 2024-05-07 | 2024-05-22 | 2024-05-22 |  |  | 2024-05-31 | 2024-05-31 | Government of the Philipppiens | 78882 | 78882 |  | 77577 | 77577 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1209 | OFFICE SUPPLIES | PGO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-04-08 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | 2024-05-06 | 2024-05-15 | 2024-06-03 |  |  | 2024-06-07 | 2024-06-07 | Government of the Philipppiens | 76340 |  | 76340 | 74800 |  | 74800 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1744 | OFFICE SUPPLIES | PAO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2024-04-02 | 2024-04-08 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-05-17 | 2024-05-20 |  |  | 2024-05-24 | 2024-05-24 | Government of the Philipppiens | 5582 | 5582 |  | 5460 | 5460 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1297 | OFFICE SUPPLIES | PAGRO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-04-08 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-05-20 | 2024-05-21 |  |  | 2024-06-20 | 2024-06-20 | Government of the Philipppiens | 5588 |  | 5588 | 5370 |  | 5370 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1205 | OFFICE SUPPLIES | PGSO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-03-25 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-05-15 | 2024-06-05 |  |  | 2024-06-25 | 2024-06-25 | Government of the Philipppiens | 41238 | 41238 |  | 41196 | 41196 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1926 | RICE, WELL MILLED | PGO | No | NP-53.9 - Small Value Procurement | 2024-03-19 | 2024-03-25 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | 2024-05-06 | 2024-05-08 | 2024-05-13 |  |  | 2024-05-15 | 2024-05-15 | Government of the Philipppiens | 482790 |  | 482790 | 477400 |  | 477400 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1650 | SPHYGMOMANOMETER | PAO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-03 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-05-13 | 2024-05-20 |  |  | 2024-06-05 | 2024-06-05 | Government of the Philipppiens | 6600 | 6600 |  | 2000 | 2000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2085 | OIL, 2T | PENRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-02 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-05-20 | 2024-05-24 |  |  | 2024-05-28 | 2024-05-28 | Government of the Philipppiens | 408 |  | 408 | 402 |  | 402 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1915 | TARPAULIN | PSWDO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-03 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-05-13 | 2024-05-23 |  |  | 2024-06-19 | 2024-06-19 | Government of the Philipppiens | 6720 |  | 6720 | 6720 |  | 6720 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1181 | JANITORIAL SUPPLIES | PHO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-25 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | 2024-05-09 | 2024-05-13 | 2024-05-21 |  |  | 2024-06-15 | 2024-06-15 | Government of the Philipppiens | 115118.6 | 115118.6 |  | 110548 | 110548 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1292 | SPAREPARTS (LIGHT VEHICLES) | PEEMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-03 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | 2024-05-08 | 2024-05-21 | 2024-05-24 |  |  | 2024-06-25 | 2024-06-25 | Government of the Philipppiens | 233417 | 233417 |  | 228172 | 228172 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1199 | TARPAULIN | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-03 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-05-15 | 2024-06-03 |  |  | 2024-06-19 | 2024-06-19 | Government of the Philipppiens | 42784 |  | 42784 | 42784 |  | 42784 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1659 | SAFETY GEARS & EQUIPMENT | PTO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-25 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-05-13 | 2024-05-21 |  |  | 2024-06-21 | 2024-06-21 | Government of the Philipppiens | 45496 | 45496 |  | 45475 | 45475 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1695 | FIRST AID KIT | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-03 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-05-20 | 2024-05-24 |  |  | 2024-06-21 | 2024-06-21 | Government of the Philipppiens | 4000 |  | 4000 | 3990 |  | 3990 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2134 | CHAIR, MONOBLOC | SEF | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-02 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | 2024-05-06 | 2024-05-13 | 2024-05-23 |  |  | 2024-05-31 | 2024-05-31 | Government of the Philipppiens | 72098 |  | 72098 | 72068.5 |  | 72068.5 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C0937 | BOOKBINDING AND TARPAULIN | PPDO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-25 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-05-13 | 2024-05-21 |  |  | 2024-06-06 | 2024-06-06 | Government of the Philipppiens | 25350 | 25350 |  | 25350 | 25350 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1149 | MEIDCAL SUPPLIES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-03 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | 2024-05-02 | 2024-05-15 | 2024-05-21 |  |  | 2024-06-05 | 2024-06-05 | Government of the Philipppiens | 173835 |  | 173835 | 153060 |  | 153060 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1704 | OIL, DIESEL ENGINE | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-02 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-05-20 | 2024-05-23 |  |  | 2024-05-29 | 2024-05-29 | Government of the Philipppiens | 10560 |  | 10560 | 10320 |  | 10320 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1980 | MEDICAL SUPPLIES | PHO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-25 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-05-20 | 2024-05-23 |  |  | 2024-06-14 | 2024-06-14 | Government of the Philipppiens | 17024 |  | 17024 | 12790 |  | 12790 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1574 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-03-19 | 2024-03-25 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | 2024-05-06 | 2024-05-13 | 2024-06-05 |  |  | 2024-06-10 | 2024-06-10 | Government of the Philipppiens | 70600 | 70600 |  | 56400 | 56400 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1153 | LABOR FOR REPLACEMENT | PGSO | No | NP-53.9 - Small Value Procurement | 2024-03-19 | 2024-03-25 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | 2024-05-09 | 2024-05-15 | 2024-06-05 |  |  | 2024-06-15 | 2024-06-15 | Government of the Philipppiens | 103500 | 103500 |  | 83000 | 83000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1298 | JANITORIAL SUPPLIES | PAGRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-08 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-05-20 | 2024-05-21 |  |  | 2024-06-14 | 2024-06-14 | Government of the Philipppiens | 13451 | 13451 |  | 13002 | 13002 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1320 | MEDICAL CERTIFICATE | PVO | No | NP-53.9 - Small Value Procurement | 2024-04-02 | 2024-04-08 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-05-15 | 2024-05-21 |  |  | 2024-06-03 | 2024-06-03 | Government of the Philipppiens | 3850 |  | 3850 | 3746 |  | 3746 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C0968 | ELECTRICAL SUPPLIES | PEEMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-08 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | 2024-05-06 | 2024-05-13 | 2024-05-22 |  |  | 2024-06-28 | 2024-06-28 | Government of the Philipppiens | 162933.4 | 162933.4 |  | 161647 | 161647 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2345 | COMPUTER SET | PTO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-15 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | 2024-05-07 | 2024-05-13 | 2024-05-21 |  |  | 2024-05-31 | 2024-05-31 | Government of the Philipppiens | 135000 | 135000 |  | 134700 | 134700 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1304 | VETERINARY SUPPLIES | PVO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-03 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | 2024-05-06 | 2024-05-21 | 2024-05-23 |  |  | 2024-06-13 | 2024-06-13 | Government of the Philipppiens | 72177 | 72177 |  | 71932 | 71932 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2340 | EXTERNAL DRIVE | PTO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-15 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-05-17 | 2024-05-21 |  |  | 2024-05-27 | 2024-05-27 | Government of the Philipppiens | 18700 | 18700 |  | 18000 | 18000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1214 | DOG VACCINATION CERTIFICATE AND TARPAULIN | PVO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-08 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-05-20 | 2024-05-23 |  |  | 2024-06-04 | 2024-06-04 | Government of the Philipppiens | 31560 | 31560 |  | 31560 | 31560 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2289 | SPAREPARTS (MOTORCYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-08 | 2024-04-15 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-05-14 | 2024-06-03 |  |  | 2024-06-06 | 2024-06-06 | Government of the Philipppiens | 8680 | 8680 |  | 8620 | 8620 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2279 | SPAREPARTS (MOTORCYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-08 | 2024-04-15 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-05-15 | 2024-06-03 |  |  | 2024-06-06 | 2024-06-06 | Government of the Philipppiens | 4900 | 4900 |  | 4863 | 4863 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2286 | SPAREPARTS (MOTORCYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-08 | 2024-04-15 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-05-13 | 2024-06-03 |  |  | 2024-06-06 | 2024-06-06 | Government of the Philipppiens | 12430 | 12430 |  | 12250 | 12250 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1906 | RICE, WELL MILLED | PGO | No | NP-53.9 - Small Value Procurement | 2024-04-02 | 2024-04-08 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | 2024-05-06 | 2024-05-13 | 2024-05-21 |  |  | 2024-05-24 | 2024-05-24 | Government of the Philipppiens | 128535 |  | 128535 | 123000 |  | 123000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2281 | SPAREPARTS (MOTORCYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-08 | 2024-04-25 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-05-15 | 2024-06-03 |  |  | 2024-06-06 | 2024-06-06 | Government of the Philipppiens | 10300 | 10300 |  | 10252 | 10252 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2288 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-08 | 2024-04-15 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | 2024-05-07 | 2024-05-22 | 2024-05-23 |  |  | 2024-05-29 | 2024-05-29 | Government of the Philipppiens | 70212 | 70212 |  | 70212 | 70212 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0542 | TARPAULIN | PGO | No | NP-53.9 - Small Value Procurement | 2024-04-08 | 2024-04-15 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-05-20 | 2024-05-23 |  |  | 2024-06-18 | 2024-06-18 | Government of the Philipppiens | 24976 |  | 24976 | 24976 |  | 24976 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1325 | POWER SPRAYER, ELECTRIC POWER SPRAY | PGSO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-25 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-05-15 | 2024-06-05 |  |  | 2024-06-21 | 2024-06-21 | Government of the Philipppiens | 26000 | 26000 |  | 25999.6 | 25999.6 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0853 | MEGAPHONE W/ SIREN & WHISTLE | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-08 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-05-20 | 2024-05-22 |  |  | 2024-06-04 | 2024-06-04 | Government of the Philipppiens | 7000 |  | 7000 | 5000 |  | 5000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2119 | SPAREPARTS ( MOTORCYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-08 | 2024-04-15 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-05-15 | 2024-06-03 |  |  | 2024-06-18 | 2024-06-18 | Government of the Philipppiens | 17390 | 17390 |  | 17225 | 17225 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1119 | OFFICE EQUIPMENT | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-03 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | 2024-05-07 | 2024-05-13 | 2024-05-21 |  |  | 2024-05-28 | 2024-05-28 | Government of the Philipppiens | 196864 |  | 196864 | 196200 |  | 196200 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1332 | GRASSCUTTER & SUBMERSIBLE PUMP | PAGRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-15 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-05-20 | 2024-05-21 |  |  | 2024-05-28 | 2024-05-28 | Government of the Philipppiens | 28500 |  | 28500 | 27750 |  | 27750 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1283 | RICE-WELL MILLED | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-03 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | 2024-05-06 | 2024-05-20 | 2024-05-22 |  |  | 2024-06-06 | 2024-06-06 | Government of the Philipppiens | 272745 |  | 272745 | 272745 |  | 272745 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1286 | FOOD SUPPLIES | PEEMO | No | NP-53.9 - Small Value Procurement | 2024-04-08 | 2024-04-15 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | 2024-05-06 | 2024-05-13 | 2024-05-22 |  |  | 2024-06-03 | 2024-06-03 | Government of the Philipppiens | 251886.51 | 133014 | 118872.51 | 251121.51 | 132249 | 118872.51 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1192 | SPAREPARTS (OFFICE & IT EQUIPMENT) | PICTO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-03 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | 2024-05-07 | 2024-05-13 | 2024-05-21 |  |  | 2024-06-21 | 2024-06-21 | Government of the Philipppiens | 157734 |  | 157734 | 142348 |  | 142348 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1932 | SPAREPARTS (HEAVY EQUIPMENT) | PEO-Motorpool | No | Direct Contracting | 2024-03-22 | 2024-04-02 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-05-20 | 2024-05-22 |  |  | 2024-06-18 | 2024-06-18 | Government of the Philipppiens | 30825.75 | 30825.75 |  | 30825.75 | 30825.75 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1622 | SPAREPARTS (HEAVY EQUIPMENT) | PEO-Motorpool | No | Direct Contracting | 2024-04-08 | 2024-04-15 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-05-17 | 2024-05-22 |  |  | 2024-06-18 | 2024-06-18 | Government of the Philipppiens | 118872.51 | 118872.51 |  | 118872.51 | 118872.51 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1753 | TONER CARTRIDGE | PAO | No | Direct Contracting | 2024-04-05 | 2024-04-15 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-05-13 | 2024-05-24 |  |  | 2024-05-28 | 2024-05-28 | Government of the Philipppiens | 4810 | 4810 |  | 4810 | 4810 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1306 | CTNL (TROPONIN) AND HEMOGLOBIN | PEEMO | No | Direct Contracting | N/A | 2024-04-03 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-05-20 | 2024-05-24 |  |  | 2024-06-13 | 2024-06-13 | Government of the Philipppiens | 120960 | 120960 |  | 120960 | 120960 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2191 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-04-15 |  | N/A | 2024-04-30 | 2024-04-30 |  | N/A | N/A | 2024-05-03 |  |  |  | N/A | 2024-05-13 | 2024-06-05 |  |  | 2024-06-05 | 2024-06-05 | Government of the Philipppiens | 18000 | 18000 |  | 18000 | 18000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2194 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-04-15 |  | N/A | 2024-04-30 | 2024-04-30 |  | N/A | N/A | 2024-05-03 |  |  |  | N/A | 2024-05-13 | 2024-06-04 |  |  | 2024-06-04 | 2024-06-04 | Government of the Philipppiens | 173850 | 173850 |  | 173580 | 173580 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2193 | SPAREPARTS (MOTORCYCLE) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-04-15 |  | N/A | 2024-04-30 | 2024-04-30 |  | N/A | N/A | 2024-05-03 |  |  |  | N/A | 2024-05-14 | 2024-06-05 |  |  | 2024-06-05 | 2024-06-05 | Government of the Philipppiens | 17030 | 17030 |  | 17030 | 17030 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1105 | OFFICE SUPPLIES | PHO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-04-08 |  | N/A | 2024-04-30 | 2024-04-30 |  | N/A | N/A | 2024-05-03 |  |  |  | 2024-05-06 | 2024-05-13 | 2024-05-21 |  |  | 2024-05-31 | 2024-05-31 | Government of the Philipppiens | 298649 | 298649 |  | 295661 | 295661 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1087 | CONSTRUCTION SUPPLIES | PENRO | No | NP-53.9 - Small Value Procurement | 2024-03-19 | 2024-04-03 |  | N/A | 2024-04-30 | 2024-04-30 |  | N/A | N/A | 2024-05-03 |  |  |  | 2024-05-09 | 2024-05-20 | 2024-05-23 |  |  | 2024-06-05 | 2024-06-05 | Government of the Philipppiens | 63191 |  | 63191 | 63091 |  | 63091 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1262 | CONSTRUCTION SUPPLIES | SEF | No | NP-53.9 - Small Value Procurement | 2024-04-02 | 2024-04-08 |  | N/A | 2024-04-30 | 2024-04-30 |  | N/A | N/A | 2024-05-03 |  |  |  | 2024-05-09 | 2024-05-20 | 2024-05-23 |  |  | 2024-06-05 | 2024-06-05 | Government of the Philipppiens | 116752.4 |  | 116752.4 | 116652.4 |  | 116652.4 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1632 | AIRCONDITION | PICTO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-08 |  | N/A | 2024-04-30 | 2024-04-30 |  | N/A | N/A | 2024-05-03 |  |  |  | N/A | 2024-05-13 | 2024-05-21 |  |  | 2024-05-29 | 2024-05-29 | Government of the Philipppiens | 30000 |  | 30000 | 28395 |  | 28395 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1740 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-02 | 2024-04-08 |  | N/A | 2024-04-30 | 2024-04-30 |  | N/A | N/A | 2024-05-03 |  |  |  | N/A | 2024-05-15 | 2024-06-05 |  |  | 2024-06-10 | 2024-06-10 | Government of the Philipppiens | 14000 | 14000 |  | 14000 | 14000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1213 | ABSORBENT GAUZE SPONGE, OXYGEN MASK, RESUSCITATOR, SURGICAL MASK | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-08 |  | N/A | 2024-04-30 | 2024-04-30 |  | N/A | N/A | 2024-05-03 |  |  |  | N/A | 2024-05-13 | 2024-05-24 |  |  | 2024-06-21 | 2024-06-21 | Government of the Philipppiens | 32420 |  | 32420 | 32338 |  | 32338 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1757 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-02 | 2024-04-08 |  | N/A | 2024-04-30 | 2024-04-30 |  | N/A | N/A | 2024-05-03 |  |  |  | N/A | 2024-05-14 | 2024-06-05 |  |  | 2024-06-10 | 2024-06-10 | Government of the Philipppiens | 3500 | 3500 |  | 3500 | 3500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1176 | COMPUTER SUPPLIES | PHO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-08 |  | N/A | 2024-04-30 | 2024-04-30 |  | N/A | N/A | 2024-05-03 |  |  |  | N/A | 2024-05-13 | 2024-05-22 |  |  | 2024-05-31 | 2024-05-31 | Government of the Philipppiens | 18424 |  | 18424 | 17970 |  | 17970 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1720 | SPAREPARTS (MOTORCYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-02 | 2024-04-08 |  | N/A | 2024-04-30 | 2024-04-30 |  | N/A | N/A | 2024-05-03 |  |  |  | N/A | 2024-05-15 | 2024-06-05 |  |  | 2024-06-10 | 2024-06-10 | Government of the Philipppiens | 6850 | 6850 |  | 6850 | 6850 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1898 | MEDICAL SUPPLIES | PGO | No | NP-53.9 - Small Value Procurement | 2024-04-08 | 2024-04-15 |  | N/A | 2024-04-30 | 2024-04-30 |  | N/A | N/A | 2024-05-03 |  |  |  | 2024-05-08 | 2024-05-13 | 2024-05-22 |  |  | 2024-05-29 | 2024-05-29 | Government of the Philipppiens | 115000 |  | 115000 | 84500 |  | 84500 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1263 | CONSTRUCTION SUPPLIES | PDRRMO | No | NP-53.9 - Small Value Procurement | 2024-04-16 | 2024-04-26 |  | N/A | 2024-04-30 | 2024-04-30 |  | N/A | N/A | 2024-05-03 |  |  |  | 2024-05-09 | 2024-05-13 | 2024-05-21 |  |  | 2024-06-10 | 2024-06-10 | Government of the Philipppiens | 86286 |  | 86286 | 86044 |  | 86044 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1151 | CONSTRUCTION SUPPLIES | PVGO | No | NP-53.9 - Small Value Procurement | 2024-04-16 | 2024-04-26 |  | N/A | 2024-04-30 | 2024-04-30 |  | N/A | N/A | 2024-05-03 |  |  |  | 2024-05-09 | 2024-05-31 | 2024-06-07 |  |  | 2024-06-25 | 2024-06-25 | Government of the Philipppiens | 64762 | 64762 |  | 63725 | 63725 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0761 | FEED INGREDIENTS | PAGRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-20 |  | N/A | 2024-04-30 | 2024-04-30 |  | N/A | N/A | 2024-05-03 |  |  |  | 2024-05-09 | 2024-05-13 | 2024-05-24 |  |  | 2024-05-30 | 2024-05-30 | Government of the Philipppiens | 96470 |  | 96470 | 96045 |  | 96045 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1921 | FOOD/CATERING SERVICES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-22 |  | N/A | 2024-04-30 | 2024-04-30 |  | N/A | N/A | 2024-05-03 |  |  |  | 2024-05-06 | 2024-05-13 | 2024-05-21 |  |  | 2024-05-28 | 2024-05-28 | Government of the Philipppiens | 375000 |  | 375000 | 375000 |  | 375000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1291 | OIL & LUBRICANTS | PEEMO | No | NP-53.9 - Small Value Procurement | 2024-04-02 | 2024-04-08 |  | N/A | 2024-04-30 | 2024-04-30 |  | N/A | N/A | 2024-05-03 |  |  |  | 2024-05-07 | 2024-05-13 | 2024-05-24 |  |  | 2024-06-05 | 2024-06-05 | Government of the Philipppiens | 155851.8 | 155851.8 |  | 155269 | 155269 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1867 | FEED INGREDIENTS | PAGRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-03 |  | N/A | 2024-04-30 | 2024-04-30 |  | N/A | N/A | 2024-05-03 |  |  |  | 2024-05-09 | 2024-05-13 | 2024-05-24 |  |  | 2024-05-30 | 2024-05-30 | Government of the Philipppiens | 82110 |  | 82110 | 81756 |  | 81756 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1321 | OFFICE SUPPLIES | PEEMO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2024-04-16 | 2024-04-22 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | N/A | 2024-05-23 | 2024-05-29 |  |  | 2024-06-11 | 2024-06-11 | Government of the Philipppiens | 49971 | 49971 |  | 49910 | 49910 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1715 | SPAREPARTS (MOTORCYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-02 | 2024-04-08 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | N/A | 2024-05-22 | 2024-06-11 |  |  | 2024-06-19 | 2024-06-19 | Government of the Philipppiens | 6370 | 6370 |  | 6370 | 6370 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1107 | DRY SEAL | PHO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-12 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | N/A | 2024-05-22 | 2024-06-03 |  |  | 2024-06-13 | 2024-06-13 | Government of the Philipppiens | 5500 | 5500 |  | 5500 | 5500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2388 | DAVAO DE ORO TOKEN | PHRMDO | No | NP-53.9 - Small Value Procurement | 2024-04-25 | 2024-04-30 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | 2024-05-15 | 2024-05-22 | 2024-06-03 |  |  | 2024-06-14 | 2024-06-14 | Government of the Philipppiens | 148500 |  | 148500 | 123750 |  | 123750 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2220 | SPAREPARTS (MOTORCYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-16 | 2024-04-22 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | N/A | 2024-05-22 | 2024-06-06 |  |  | 2024-06-10 | 2024-06-10 | Government of the Philipppiens | 2400 | 2400 |  | 2370 | 2370 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2228 | FOOD/CATERING SERVICES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-22 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | 2024-05-13 | 2024-05-22 | 2024-06-04 |  |  | 2024-06-18 | 2024-06-18 | Government of the Philipppiens | 66300 |  | 66300 | 66202.5 | 0 | 66202.5 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1275 | SPAREPARTS (MOTORCYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-16 | 2024-04-22 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | N/A | 2024-05-22 | 2024-06-06 |  |  | 2024-06-11 | 2024-06-11 | Government of the Philipppiens | 17911 | 17911 |  | 17595 | 17595 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1448 | DRONE | PGO | No | NP-53.9 - Small Value Procurement | 2024-04-08 | 2024-04-15 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | 2024-05-13 | 2024-05-23 | 2024-05-29 |  |  | 2024-05-31 | 2024-05-31 | Government of the Philipppiens | 50000 |  | 50000 | 49900 |  | 49900 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1330 | SPAREPARTS (MOTORCYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-16 | 2024-04-22 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | N/A | 2024-05-22 | 2024-06-06 |  |  | 2024-06-20 | 2024-06-20 | Government of the Philipppiens | 28352 | 12102 | 16250 | 12039 | 12039 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2183 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-16 | 2024-04-22 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | N/A | 2024-05-22 | 2024-06-07 |  |  | 2024-06-14 | 2024-06-14 | Government of the Philipppiens | 4730 | 4730 |  | 4300 | 4300 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2264 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-16 | 2024-04-22 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | N/A | 2024-05-22 | 2024-06-07 |  |  | 2024-06-18 | 2024-06-18 | Government of the Philipppiens | 14085 | 14085 |  | 12600 | 12600 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2282 | SPAREPARTS (MOTORCYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-16 | 2024-04-22 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | N/A | 2024-05-22 | 2024-06-06 |  |  | 2024-06-18 | 2024-06-18 | Government of the Philipppiens | 16250 | 16250 |  | 16086 | 16086 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2263 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-16 | 2024-04-22 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | N/A | 2024-05-22 | 2024-06-07 |  |  | 2024-06-18 | 2024-06-18 | Government of the Philipppiens | 49830 | 49830 |  | 42800 | 42800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2358 | COMPUTER SUPPLIES/SPAREPARTS | PTO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-22 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | N/A | 2024-05-27 | 2024-05-29 |  |  | 2024-05-31 | 2024-05-31 | Government of the Philipppiens | 11379 | 11379 |  | 11100 | 11100 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2328 | SPAREPARTS (MOTORCYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-25 | 2024-04-30 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | N/A | 2024-05-22 | 2024-06-11 |  |  | 2024-06-19 | 2024-06-19 | Government of the Philipppiens | 9200 | 9200 |  | 9200 | 9200 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2124 | SPAREPARTS (MOTORCYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-16 | 2024-04-22 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | N/A | 2024-05-22 | 2024-06-06 |  |  | 2024-06-18 | 2024-06-18 | Government of the Philipppiens | 1560 | 1560 |  | 1540 | 1540 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2150 | DOGFOOD | PGO | No | NP-53.9 - Small Value Procurement | 2024-04-02 | 2024-04-08 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | N/A | 2024-05-22 | 2024-06-03 |  |  | 2024-06-14 | 2024-06-14 | Government of the Philipppiens | 48840 |  | 48840 | 44400 |  | 44400 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1322 | DRUGS AND MEDICINES | PEEMO | No | NP-53.9 - Small Value Procurement | 2024-04-16 | 2024-04-22 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | 2024-05-14 | 2024-05-24 | 2024-05-29 |  |  | 2024-06-05 | 2024-06-05 | Government of the Philipppiens | 72000 | 72000 |  | 59937 | 59937 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2307 | SPAREPARTS (MOTORCYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-25 | 2024-04-30 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | N/A | 2024-05-22 | 2024-06-11 |  |  | 2024-06-19 | 2024-06-19 | Government of the Philipppiens | 8800 | 8800 |  | 8800 | 8800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2180 | MEDALS | PGO | No | NP-53.9 - Small Value Procurement | 2024-04-03 | 2024-04-04 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | N/A | 2024-05-22 | 2024-05-29 |  |  | 2024-06-13 | 2024-06-13 | Government of the Philipppiens | 22100 |  | 22100 | 22100 |  | 22100 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2367 | SPAREPARTS (MOTORCYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-25 | 2024-04-30 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | N/A | 2024-05-23 | 2024-06-11 |  |  | 2024-06-19 | 2024-06-19 | Government of the Philipppiens | 2600 | 2600 |  | 2600 | 2600 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1072 | OTHER SUPPLIES/MATERIALS (PRINTERS, COMPUTER SETS WITH COMPLETE ACCESSORIES | PAO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-22 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | 2024-05-14 | 2024-05-23 | 2024-05-29 |  |  | 2024-06-10 | 2024-06-10 | Government of the Philipppiens | 217138 | 217138 |  | 214232 | 214232 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1987 | HELMET | PVO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-22 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | 2024-05-13 | 2024-05-22 | 2024-05-29 |  |  | 2024-06-11 | 2024-06-11 | Government of the Philipppiens | 11000 | 11000 |  | 11000 | 11000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1302 | LAPTOP & COMPUTER SUPPLIES | PVO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-03 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | 2024-05-17 | 2024-05-22 | 2024-06-03 |  |  | 2024-06-07 | 2024-06-07 | Government of the Philipppiens | 90242 | 90242 |  | 74174 | 74174 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2339 | PICTURE FRAME | PHO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-22 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | N/A | 2024-05-22 | 2024-05-29 |  |  | 2024-06-07 | 2024-06-07 | Government of the Philipppiens | 29750 |  | 29750 | 29750 |  | 29750 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1300 | AGRICULTURAL SUPPLIES | PAGRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-22 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | 2024-05-16 | 2024-05-22 | 2024-06-05 |  |  | 2024-06-26 | 2024-06-26 | Government of the Philipppiens | 72764 |  | 72764 | 71680 |  | 71680 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1169 | KITCHENWARE & UTENSILS | PAO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-25 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | N/A | 2024-05-22 | 2024-05-29 |  |  | 2024-06-03 | 2024-06-03 | Government of the Philipppiens | 15575 | 15575 |  | 15508 | 15508 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2271 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-08 | 2024-04-15 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | N/A | 2024-05-22 | 2024-06-11 |  |  | 2024-06-19 | 2024-06-19 | Government of the Philipppiens | 45000 | 45000 |  | 45000 | 45000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1317 | DYNAMIC MICROPHONE & PORTABLE OUTDOOR SPEAKER | PVO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-22 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | N/A | 2024-05-22 | 2024-05-29 |  |  | 2024-06-13 | 2024-06-13 | Government of the Philipppiens | 15970 |  | 15970 | 15970 |  | 15970 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1312 | BATTERY | PEEMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-15 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | N/A | 2024-05-22 | 2024-06-03 |  |  | 2024-06-05 | 2024-06-05 | Government of the Philipppiens | 18150 | 18150 |  | 18150 | 18150 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1465 | FOLDING SINGLE CAPMING BED | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-22 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | N/A | 2024-05-24 | 2024-05-29 |  |  | 2024-06-11 | 2024-06-11 | Government of the Philipppiens | 30000 |  | 30000 | 30000 |  | 30000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-1322 | PORTABLE VACUUM CLEANER | PGSO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-25 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | N/A | 2024-05-22 | 2024-06-06 |  |  | 2024-06-20 | 2024-06-20 | Government of the Philipppiens | 10000 | 10000 |  | 9980 | 9980 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0855 | OFFICE EQUIPMENT | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-22 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | N/A | 2024-05-22 | 2024-06-05 |  |  | 2024-06-07 | 2024-06-07 | Government of the Philipppiens | 25000 |  | 25000 | 23775 |  | 23775 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1064 | CONSTRUCTION MATERIALS | PVO | No | Competitive Bidding | 2024-03-05 | 2024-03-25 |  | 2024-04-02 | 2024-04-16 | 2024-04-16 |  | 2024-04-16 | 2024-05-08 | 2024-05-13 |  |  |  | 2024-05-15 | 2024-05-23 | 2024-06-03 |  |  | 2024-06-11 | 2024-06-11 | Government of the Philipppiens | 3480267.69 |  | 3480267.69 | 3346546.13 |  | 3346546.13 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-01 | N/A | Completed
24-C1048 | CONSTRUCTION MATERIALS | PVO | No | Competitive Bidding | 2024-03-05 | 2024-04-08 |  | N/A | 2024-04-16 | 2024-04-16 |  | 2024-04-16 | 2024-05-08 | 2024-05-13 |  |  |  | 2024-05-15 | 2024-05-23 | 2024-06-05 |  |  | 2024-06-11 | 2024-06-11 | Government of the Philipppiens | 851428.35 |  | 851428.35 | 840828.15 |  | 840828.15 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-01 | N/A | Completed
24-C0933 | MEALS AND SNACKS WITH ACCOMMODATION | PPDO | No | Competitive Bidding | N/A | 2024-04-08 |  | N/A | 2024-04-16 | 2024-04-16 |  | 2024-04-16 | 2024-05-09 | 2024-05-13 |  |  |  | 2024-05-13 | 2024-05-15 | 2024-05-15 |  |  | 2024-06-18 | 2024-06-18 | Government of the Philipppiens | 596460 |  | 596460 | 596460 |  | 596460 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-01 | N/A | Completed
24-1732 | PAINT, SUICK DRY ENAMEL-WHITE FOR PAINTS | PGO-SEF | No | Competitive Bidding | N/A | 2024-04-01 |  | 2024-04-16 | 2024-04-30 | 2024-04-30 |  | 2024-04-30 | 2024-05-10 | 2024-05-16 |  |  |  | 2024-05-21 | 2024-05-22 | 2024-06-24 |  |  | 2024-06-25 | 2024-06-25 | Government of the Philipppiens | 1999872 | 1999872 |  | 1765512 | 1765512 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2024-04-11 | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2024-04-24 | N/A | Completed
24-C1285 | RICE (WELL MILLED) 50KG/SACK | PEEMO | No | Competitive Bidding | N/A | 2024-04-22 |  | N/A | 2024-04-30 | 2024-04-30 |  | 2024-04-30 | 2024-05-10 | 2024-05-16 |  |  |  | 2024-05-16 | 2024-05-22 | 2024-05-28 |  |  | 2024-05-30 | 2024-05-30 | Government of the Philipppiens | 996930 | 996930 |  | 954000 | 954000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2024-04-24 | N/A | Completed
24-C1296 | LABORATORY SUPPLIES | PEEMO | No | Competitive Bidding | 2024-04-02 | 2024-04-08 |  | N/A | 2024-04-16 | 2024-04-16 |  | 2024-04-16 | 2024-05-10 | 2024-05-16 |  |  |  | 2024-05-16 | 2024-05-22 | 2024-05-27 |  |  | 2024-05-28 | 2024-05-28 | Government of the Philipppiens | 884961 | 884961 |  | 620604 | 620604 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2024-04-24 | N/A | Completed
24-2144 | BRAND NEW, HYDRAULIC EXCVATOR, CRAWLER TYPE (MONO BOOM) | PEO | No | Competitive Bidding | 2024-03-22 | 2024-03-25 |  | 2024-04-02 | 2024-04-16 | 2024-04-16 |  | 2024-04-16 | 2024-05-10 | 2024-05-16 |  |  |  | 2024-05-16 | 2024-05-22 | 2024-05-27 |  |  | 2024-06-11 | 2024-06-11 | Government of the Philipppiens | 20000000 |  | 20000000 | 19992000 |  | 19992000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2024-04-01 | 2024-04-11 | 2024-04-11 | 2024-04-11 | 2024-04-11 | N/A | Completed
24-2463 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-05-03 |  | N/A | 2024-05-14 | 2024-05-14 |  | N/A | N/A | 2024-05-16 |  |  |  | N/A | 2024-06-04 | 2024-06-06 |  |  | 2024-06-06 | 2024-06-06 | Government of the Philipppiens | 7050 | 7050 |  | 7050 | 7050 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2466 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-05-03 |  | N/A | 2024-05-14 | 2024-05-14 |  | N/A | N/A | 2024-05-16 |  |  |  | N/A | 2024-05-22 | 2024-06-07 |  |  | 2024-06-07 | 2024-06-07 | Government of the Philipppiens | 7450 | 7450 |  | 7450 | 7450 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2462 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-05-03 |  | N/A | 2024-05-14 | 2024-05-14 |  | N/A | N/A | 2024-05-16 |  |  |  | N/A | 2024-05-22 | 2024-06-06 |  |  | 2024-06-06 | 2024-06-06 | Government of the Philipppiens | 47000 | 47000 |  | 47000 | 47000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2473 | SPAREPARTS (MOTORCYCLE) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-05-03 |  | N/A | 2024-05-14 | 2024-05-14 |  | N/A | N/A | 2024-05-16 |  |  |  | N/A | 2024-05-22 | 2024-06-11 |  |  | 2024-06-19 | 2024-06-19 | Government of the Philipppiens | 6060 | 6060 |  | 6060 | 6060 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2467 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-05-03 |  | N/A | 2024-05-14 | 2024-05-14 |  | N/A | N/A | 2024-05-16 |  |  |  | N/A | 2024-05-23 | 2024-06-07 |  |  | 2024-06-07 | 2024-06-07 | Government of the Philipppiens | 23100 | 23100 |  | 23100 | 23100 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2556 | SPAREPARTS (HEAVY EQUIPT) | PDRRMO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-05-06 |  | N/A | 2024-05-14 | 2024-05-14 |  | N/A | N/A | 2024-05-16 |  |  |  | N/A | 2024-05-23 | 2024-06-03 |  |  | 2024-06-03 | 2024-06-03 | Government of the Philipppiens | 33900 | 33900 |  | 33900 | 33900 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1047 | SPAREPARTS (LIGHT VEHICLES) | PEO-Motorpool | No | Direct Contracting | N/A | 2024-05-10 |  | N/A | 2024-05-14 | 2024-05-14 |  | N/A | N/A | 2024-05-16 |  |  |  | N/A | 2024-05-22 | 2024-05-28 |  |  | 2024-06-10 | 2024-06-10 | Government of the Philipppiens | 2039316.05 | 2039316.05 |  | 2031333 | 2031333 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1168 | FOOD/CATERING SERVICES | PVO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-22 |  | N/A | 2024-05-14 | 2024-05-14 |  | N/A | N/A | 2024-05-16 |  |  |  | 2024-05-16 | 2024-05-21 | 2024-06-04 |  |  | 2024-06-11 | 2024-06-11 | Government of the Philipppiens | 167820 | 167820 |  | 166868 | 166868 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1353 | FLOWERS & DECORATION | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-05-10 |  | N/A | 2024-05-14 | 2024-05-14 |  | N/A | N/A | 2024-05-16 |  |  |  | N/A | 2024-05-23 | 2024-05-24 |  |  | 2024-06-06 | 2024-06-06 | Government of the Philipppiens | 49950 |  | 49950 | 49910 |  | 49910 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2525 | SAFETY PINS & THUMBSTACKS | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-05-10 |  | N/A | 2024-05-14 | 2024-05-14 |  | N/A | N/A | 2024-05-16 |  |  |  | N/A | 2024-05-23 | 2024-05-24 |  |  | 2024-05-28 | 2024-05-28 | Government of the Philipppiens | 540 |  | 540 | 520 |  | 520 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2528 | CLOTH,PONGEE | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-30 |  | N/A | 2024-05-14 | 2024-05-14 |  | N/A | N/A | 2024-05-16 |  |  |  | N/A | 2024-05-24 | 2024-05-24 |  |  | 2024-05-28 | 2024-05-28 | Government of the Philipppiens | 5700 |  | 5700 | 5694 |  | 5694 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1326 | PLUMBING SUPPLIES | PEEMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-15 |  | N/A | 2024-05-14 | 2024-05-14 |  | N/A | N/A | 2024-05-16 |  |  |  | N/A | 2024-05-24 | 2024-05-28 |  |  | 2024-06-11 | 2024-06-11 | Government of the Philipppiens | 44979 | 44979 |  | 44891 | 44891 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2562 | COMPUTER SET & PRINTER | PENRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-05-06 |  | N/A | 2024-05-14 | 2024-05-14 |  | N/A | N/A | 2024-05-16 |  |  |  | 2024-05-16 | 2024-05-22 | 2024-05-29 |  |  | 2024-06-10 | 2024-06-10 | Government of the Philipppiens | 58420 | 58420 |  | 58200 | 58200 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2538 | MEDALS | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-05-10 |  | N/A | 2024-05-14 | 2024-05-14 |  | N/A | N/A | 2024-05-16 |  |  |  | 2024-05-16 | 2024-05-21 | 2024-05-22 |  |  | 2024-05-27 | 2024-05-27 | Government of the Philipppiens | 330750 | 330750 |  | 330277.5 | 330277.5 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2363 | SPAREPARTS (MOTORCYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-25 | 2024-04-30 |  | N/A | 2024-05-14 | 2024-05-14 |  | N/A | N/A | 2024-05-16 |  |  |  | N/A | 2024-05-23 | 2024-06-06 |  |  | 2024-06-10 | 2024-06-10 | Government of the Philipppiens | 13650 | 13650 |  | 13597 | 13597 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2327 | SPAREPARTS (MOTORCYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-25 | 2024-04-30 |  | N/A | 2024-05-14 | 2024-05-14 |  | N/A | N/A | 2024-05-16 |  |  |  | N/A | 2024-05-23 | 2024-06-06 |  |  | 2024-06-20 | 2024-06-20 | Government of the Philipppiens | 5568 | 5568 |  | 5530 | 5530 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2323 | SPAREPARTS (MOTORCYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-25 | 2024-04-30 |  | N/A | 2024-05-14 | 2024-05-14 |  | N/A | N/A | 2024-05-16 |  |  |  | N/A | 2024-05-23 | 2024-06-06 |  |  | 2024-06-11 | 2024-06-11 | Government of the Philipppiens | 12835 | 12835 |  | 12731 | 12731 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2324 | SPAREPARTS (MOTORCYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-25 | 2024-04-30 |  | N/A | 2024-05-14 | 2024-05-14 |  | N/A | N/A | 2024-05-16 |  |  |  | N/A | 2024-05-22 | 2024-06-06 |  |  | 2024-06-20 | 2024-06-20 | Government of the Philipppiens | 10500 | 10500 |  | 10461 | 10461 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2221 | SPAREPARTS (MOTORCYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-25 | 2024-04-30 |  | N/A | 2024-05-14 | 2024-05-14 |  | N/A | N/A | 2024-05-16 |  |  |  | N/A | 2024-05-22 | 2024-06-06 |  |  | 2024-06-21 | 2024-06-21 | Government of the Philipppiens | 17131 | 17131 |  | 17026 | 17026 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-0424 | PLAQUES/TROPHIES/MEDAL | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-05-06 |  | N/A | 2024-05-14 | 2024-05-14 |  | N/A | N/A | 2024-05-16 |  |  |  | N/A | 2024-05-22 | 2024-06-03 |  |  | 2024-06-19 | 2024-06-19 | Government of the Philipppiens | 32000 |  | 32000 | 30950 |  | 30950 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2564 | FOOD/CATERING SERVICES | PBO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-27 |  | N/A | 2024-05-14 | 2024-05-14 |  | N/A | N/A | 2024-05-16 |  |  |  | 2024-05-16 | 2024-05-22 | 2024-05-29 |  |  | 2024-06-10 | 2024-06-10 | Government of the Philipppiens | 51900 | 51900 |  | 51120 | 51120 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2529 | FOOD SUPPLIES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-30 |  | N/A | 2024-05-14 | 2024-05-14 |  | N/A | N/A | 2024-05-16 |  |  |  | N/A | 2024-05-23 | 2024-06-03 |  |  | 2024-06-11 | 2024-06-11 | Government of the Philipppiens | 26355 |  | 26355 | 26250 |  | 26250 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1258 | FOOD/CATERING SERVICES | PGO | No | NP-53.1 Two Failed Biddings | N/A | 2024-05-10 |  | N/A | 2024-05-14 | 2024-05-14 |  | N/A | N/A | 2024-05-16 |  |  |  | 2024-05-16 | 2024-05-16 | 2024-05-30 |  |  | 2024-06-14 | 2024-06-14 | Government of the Philipppiens | 680690 |  | 680690 | 680690 |  | 680690 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2933 | RICE (WELL MILLED) | PDRRMO | No | NP-53.2 Emergency Cases | N/A | 2024-05-24 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | 2024-05-29 | 2024-05-29 | 2024-06-04 |  |  | 2024-06-10 | 2024-06-10 | Government of the Philipppiens | 150000 |  | 150000 | 150000 |  | 150000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1374 | JANITORIAL SUPPLIES | PDRRMO | No | NP-53.2 Emergency Cases | N/A | 2024-05-24 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | 2024-05-29 | 2024-05-29 | 2024-06-04 |  |  | 2024-06-06 | 2024-06-06 | Government of the Philipppiens | 522300 |  | 522300 | 500250 |  | 500250 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-C1376 | FOOD SUPPLIES | PDRRMO | No | NP-53.2 Emergency Cases | N/A | 2024-05-24 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | 2024-05-29 | 2024-05-29 | 2024-06-03 |  |  | 2024-06-05 | 2024-06-05 | Government of the Philipppiens | 196218 |  | 196218 | 194481 |  | 194481 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
24-2547 | DIGITAL BLACK & WHITE MULTI FUNCTION COPIER/PRINTER/COLOR SCANNER | COA | No | NP-53.9 - Small Value Procurement | 2024-04-30 | 2024-05-02 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | 2024-05-31 | 2024-06-13 | 2024-06-24 |  |  | 2024-06-24 | 2024-06-24 | Government of the Philipppiens | 93500 |  | 93500 | 81000 |  | 81000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0803 LOT 1 | FOOD/CATERING SERVICES | PAGRO |  | NP-53.1 Two Failed Biddings | N/A | 2024-02-09 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | 2024-03-25 | 2024-04-19 | 2024-04-23 |  |  | 2024-04-29 | 2024-04-29 | Government of the Philipppiens | 351500 |  | 351500 | 316750 |  | 316750 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
23-C0803 LOT 2 | MEALS AND SNACKS | PAGRO |  | Competitive Bidding | 2024-11-07 | 2024-01-08 |  | 2024-01-23 | 2024-02-06 | 2024-02-06 |  | 2024-02-06 | 2024-02-12 | 2024-02-14 |  |  |  | 2024-02-16 | 2024-02-29 | 2024-02-29 |  |  | 2024-02-29 | 2024-02-29 | Government of the Philipppiens | 663460 |  | 663460 | 631095 |  | 631095 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2024-01-22 | 2024-02-02 | 2024-02-02 | 2024-02-02 | 2024-02-02 | N/A | Completed
23-5452 | SPAREPARTS | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2023-12-05 | 2023-12-12 |  | N/A | 2024-01-09 | 2024-01-09 |  | N/A | N/A | 2024-01-11 |  |  |  | N/A | 2024-02-06 | 2024-02-13 |  |  | 2024-02-13 | 2024-02-13 | Government of the Philipppiens | 92800 |  | 92800 | 92800 |  | 92800 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Completed
[25 empty] | Total Allotted Budget of Procurement Activities | 160861639.62 | 57761871.94 | 103099767.68 |  |  |  | 7.511%
[25 empty] | Total Contract Price of Procurement Activities Conducted |  |  |  | 148778961.98 | 47671780.61 | 101107181.37
[25 empty] | Total Savings (Total Allotted Budget - Total Contract Price) | 12082677.64 | [14 empty] | 2023-06-30
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13 | Column14 | Column15 | Column16 | Column17 | Column18 | Column19 | Column20 | Column21 | Column22 | Column23 | Column24 | Column25 | Column26 | Column27 | Column28 | Column29 | Column30 | Column31 | Column32 | Column33 | Column34 | Column35 | Column36 | Column37 | Column38 | Column39 | Column40 | Column41 | Column42
Code (PAP) | Procurement Project | PMO/End-User | Is this an Early Procurement Activity? | Mode of Procurement | Pre-Proc Conference | Ads/Post of IB | Ave. No. of Days to Commence Procurement (Pre-Proc to Posting of IB) (i.3) | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Average No. of Days to open bid proposals (Posting of IB to Opening of Bids) (i.4) | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Accumulated Days in Evaluation of Bids (Opening of Bids to Post Qua) | Average Number of Days to Recommend Award (Opening of Bids to Recommend Award) (i.5) | Average Number of Days to Conclude Procurement (IB to BAC Reso) (i.6) | Notice of Award | Contract Signing | Notice to Proceed | Average Number of Days to Issue Notice to Proceed (NOA to NTP) (i.7) | Average Days from (Posting of IB to NTP) (i.8) | Delivery/ Completion | Inspection & Acceptance | Source of Funds | Total | MOOE | CO | Total2 | MOOE2 | CO3 | % Variance | List of Invited Observers | Pre-bid Conf4 | Eligibility Check5 | Sub/Open of Bids6 | Bid Evaluation7 | Post Qual8 | Delivery/ Completion/ Acceptance (If applicable) | Remarks (Explaining changes from the APP) | Column42
ONGOING PROCUREMENT ACTIVITIES | [31 empty] | -
24-C1106 | SUPPLY AND DELIVERY OF MEALS AND SNACKS | PAGRO | No | Competitive Bidding | N/A | 2024-03-11 | #N/A | N/A | 2024-03-19 | 2024-03-19 | 8 | 2024-03-19 | 2024-04-01 | 2024-04-04 | 13 | 16 | 24 | 2024-04-04 | 2024-04-23 | 2024-04-25 | 21 | 45 |  |  | Government of the Philipppiens | 663580 | 663580 |  | 653602 | 653602 |  | 0.015037 | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-03-15 | 2024-03-15 | 2024-03-15 | N/A | N/A | Partial Delivery | 0
24-1540 | FURNITURE & FIXTURES | PAO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-20 |  | N/A | 2024-04-05 | 2024-04-05 | 16 | N/A | N/A | 2024-04-12 |  | 7 | 23 | 2024-04-19 | 2024-04-23 | 2024-05-06 | 17 | 47 |  |  | Government of the Philipppiens | 87300 | 87300 |  | 87292 | 87292 |  | 0.009164% | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Partial Delivery | 0
24-0131 | SUPPLY AND DELIVERY OF MEALS AND SNACKS | PGO | No | Competitive Bidding | N/A | 2024-01-29 |  | 2024-02-06 | 2024-02-20 | 2024-02-20 | 22 | 2024-02-20 | 2024-02-27 | 2024-03-06 | 7 | 15 | 37 | 2024-03-06 | 2024-03-06 | 2024-03-07 | 1 | 38 |  |  | Government of the Philipppiens | 1185000 |  | 1185000 | 1173000 |  | 1173000 | 1.013% | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2024-02-05 | 2024-02-19 | 2024-02-19 | 2024-02-19 | N/A | N/A | Partial Delivery | 0
24-0956 | PACKED MEALS | PDRRMO | No | NP-53.2 Emergency Cases | N/A | 2024-02-07 |  | N/A | 2024-02-08 | 2024-02-08 | 1 | N/A | N/A | 2024-02-08 |  | 0 | 1 | 2024-02-08 | 2024-02-08 | 2024-02-16 | 8 | 9 |  |  | Government of the Philipppiens | 595000 |  | 595000 | 595000 |  | 595000 | 0 | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Partial Delivery | 0
24-C1054 | FOOD CATERING/SERVICES | PHO | No | NP-53.9 - Small Value Procurement | 2024-03-19 | 2024-03-25 | 6 | N/A | 2024-04-03 | 2024-04-03 | 9 | N/A | N/A | 2024-04-04 |  | 1 | 10 | 2024-04-04 | 2024-04-24 | 2024-04-29 | 25 | 35 |  |  | Government of the Philipppiens | 398530 |  | 398530 | 383530 |  | 383530 | 0.037638 | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Partial Delivery | 0
23-4647 | TANDEM REMOTE WEATHER STATION | PDRRMO | No | Competitive Bidding | Actual Procurement Activities | 2023-11-13 |  | 2023-11-21 | 2023-12-05 | 2023-12-05 | 22 | 2023-12-05 | 2023-12-18 | 2024-01-11 | 13 | 37 | 59 | 2024-01-12 | 2024-02-06 | 2024-02-06 | 25 | 85 |  |  | Government of the Philipppiens | 1965565.38 |  | 1965565.38 | 1899000 |  | 1899000 | 0.033866 | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | Date of Receipt of Invitation | 2023-12-01 | 2023-12-01 | N/A | N/A | N/A | For Delivery | 0
24-0085 | MEMO PADS | PBO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-02-02 |  | N/A | 2024-02-20 | 2024-02-20 |  | N/A | N/A | 2024-02-22 |  |  |  | N/A | 2024-02-29 | 2024-03-01 |  |  |  |  | Government of the Philipppiens | 5000 | 5000 |  | 5000 | 5000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-0461 | PRINTING | PEO | No | NP-53.9 - Small Value Procurement | 2024-02-08 | 2024-02-13 |  | N/A | 2024-02-20 | 2024-02-20 |  | N/A | N/A | 2024-02-22 |  |  |  | N/A | 2024-03-04 | 2024-03-06 |  |  |  |  | Government of the Philipppiens | 1792 |  | 1792 | 1792 |  | 1792 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-0560 | FOOD/CATERING SERVICES | PIAO | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-02 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-19 | 2024-03-25 |  |  |  |  | Government of the Philipppiens | 13600 | 13600 |  | 13440 | 13440 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-0813 | WATER | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-09 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-21 | 2024-03-26 |  |  |  |  | Government of the Philipppiens | 9963 |  | 9963 | 9720 |  | 9720 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-C0946 | MINERAL WATER | PEEMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-16 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | 2024-03-06 | 2024-03-21 | 2024-03-26 |  |  |  |  | Government of the Philipppiens | 50430 | 50430 |  | 49200 | 49200 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-0901 | FOOD/CATERING SERVICES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-22 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | 2024-03-06 | 2024-03-13 | 2024-03-13 |  |  |  |  | Government of the Philipppiens | 150000 |  | 150000 | 149908.8 |  | 149908.8 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-C0995 | TARPAULIN | PHRMDO | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-22 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-15 | 2024-03-19 |  |  |  |  | Government of the Philipppiens | 49840 |  | 49840 | 48060 |  | 48060 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-0434 | AGRICULTURAL SUPPLIES | PENRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-22 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-21 | 2024-03-22 |  |  |  |  | Government of the Philipppiens | 6348 |  | 6348 | 6320 |  | 6320 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-0878 | WATER | SPO | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-15 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-21 | 2024-05-08 |  |  |  |  | Government of the Philipppiens | 4961 | 4961 |  | 4840 | 4840 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-C1005 | OFFICE SUPPLIES | COA | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2024-02-08 | 2024-02-13 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-04-03 | 2024-04-02 |  |  |  |  | Government of the Philipppiens | 25130 | 25130 |  | 25130 | 25130 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-0599 | GAS | PEO-GA | No | Direct Contracting | 2024-02-13 | 2024-02-15 |  | N/A | 2024-03-05 | 2024-03-05 |  | N/A | N/A | 2024-03-06 |  |  |  | N/A | 2024-03-25 | 2024-04-03 |  |  |  |  | Government of the Philipppiens | 36060 | 36060 |  | 36060 | 36060 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1294 | SPAREPARTS (MOTORCYCLE) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-01 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-25 | 2024-04-30 |  |  |  |  | Government of the Philipppiens | 14985 | 14985 |  | 14985 | 14985 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1201 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-03-01 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-23 | 2024-04-25 |  |  |  |  | Government of the Philipppiens | 11000 | 11000 |  | 11000 | 11000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-C1083 | SPAREPARTS (LIGHT VEHICLES) | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | 2024-03-05 | 2024-03-08 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-06-24 | 2024-06-03 |  |  |  |  | Government of the Philipppiens | 55150 | 55150 |  | 55150 | 55150 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1390 | FOOD/CATERING SERVICES | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-01 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | 2024-03-27 | 2024-04-04 | 2024-04-12 |  |  |  |  | Government of the Philipppiens | 55000 |  | 55000 | 53900 |  | 53900 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-0480 | ELECTRICAL SUPPLIES | PEO-Motorpool | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-01 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-12 | 2024-04-30 |  |  |  |  | Government of the Philipppiens | 15280 | 15280 |  | 15260 | 15260 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1246 | FOOD/CATERING SERVICES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-01 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-05 | 2024-04-15 |  |  |  |  | Government of the Philipppiens | 32500 |  | 32500 | 32435 |  | 32435 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1238 | FOOD/CATERING SERVICES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-01 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | 2024-03-25 | 2024-04-04 | 2024-04-15 |  |  |  |  | Government of the Philipppiens | 129000 |  | 129000 | 128625 |  | 128625 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1245 | FOOD/CATERING SERVICES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-01 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-04 | 2024-04-15 |  |  |  |  | Government of the Philipppiens | 16350 |  | 16350 | 16329.75 |  | 16329.75 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1247 | FOOD/CATERING SERVICES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-01 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-05 | 2024-04-15 |  |  |  |  | Government of the Philipppiens | 39520 |  | 39520 | 39460 |  | 39460 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-0077 | TARPAULIN | PBO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-01 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-08 | 2024-04-12 |  |  |  |  | Government of the Philipppiens | 2800 | 2800 |  | 2800 | 2800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-0530 | PLAQUE/TROPHIES/MEDAL | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-01 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-05 | 2024-04-12 |  |  |  |  | Government of the Philipppiens | 26400 | 26400 |  | 26400 | 26400 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1303 | FOOD/CATERING SERVICES | PICTO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-01 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-05 | 2024-04-11 |  |  |  |  | Government of the Philipppiens | 23400 | 23400 |  | 22980 | 22980 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1342 | WATER | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-01 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-04 | 2024-04-11 |  |  |  |  | Government of the Philipppiens | 10575 | 10575 |  | 10000 | 10000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-0907 | SPAREPARTS (LIGHT VEHICLES) | PVGO | No | NP-53.9 - Small Value Procurement | 2024-02-20 | 2024-02-22 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-05-27 | 2024-06-04 |  |  |  |  | Government of the Philipppiens | 21880 | 21880 |  | 21600 | 21600 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1451 | WATER | PLO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-08 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-05 | 2024-04-11 |  |  |  |  | Government of the Philipppiens | 2870 | 2870 |  | 2800 | 2800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-C0947 | MINERAL WATER | PGO | No | NP-53.9 - Small Value Procurement | 2024-03-05 | 2024-03-08 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | 2024-03-25 | 2024-04-23 | 2024-04-30 |  |  |  |  | Government of the Philipppiens | 160802 | 160802 |  | 156880 | 156880 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-0924 | FOOD/CATERING SERVICES | PGSO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-08 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-25 | 2024-05-02 |  |  |  |  | Government of the Philipppiens | 7500 |  | 7500 | 7200 |  | 7200 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1406 | FOOD/CATERING SERVICES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-08 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-04 | 2024-04-08 |  |  |  |  | Government of the Philipppiens | 4500 |  | 4500 | 4477.5 |  | 4477.5 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1381 | FOOD CATERING/SERVICES | PGO | No | NP-53.9 - Small Value Procurement | 2024-03-05 | 2024-03-08 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | 2024-04-03 | 2024-04-04 | 2024-04-15 |  |  |  |  | Government of the Philipppiens | 52000 |  | 52000 | 51920 |  | 51920 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-0676 | FOOD CATERING/SERVICES | PHRMDO | No | NP-53.9 - Small Value Procurement | 2024-03-05 | 2024-03-08 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | 2024-03-25 | 2024-03-27 | 2024-04-02 |  |  |  |  | Government of the Philipppiens | 115800 |  | 115800 | 111360 |  | 111360 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1053 | FOOD/CATERING SERVICES | PHO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-08 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-04-05 | 2024-04-12 |  |  |  |  | Government of the Philipppiens | 35000 |  | 35000 | 32500 |  | 32500 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-0250 | FOOD/CATERING SERVICES | PPDO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-08 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | 2024-03-25 | 2024-04-08 | 2024-04-12 |  |  |  |  | Government of the Philipppiens | 52500 |  | 52500 | 52500 |  | 52500 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-C1179 | TARPAULIN | PHO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-20 |  | N/A | 2024-04-03 | 2024-04-03 |  | N/A | N/A | 2024-04-04 |  |  |  | 2024-04-11 | 2024-04-11 | 2024-05-10 |  |  |  |  | Government of the Philipppiens | 71288 |  | 71288 | 68232.8 |  | 68232.8 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-0781 | PRINTED FORMS | PTO | No | NP-53.5 Agency-to-Agency | 2024-02-20 | 2024-03-01 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | 2024-04-01 | 2024-04-08 | 2024-04-30 |  |  |  |  | Government of the Philipppiens | 3635000 |  | 3635000 | 3070000 |  | 3070000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-0887 | OFFICE SUPPLIES | PVGO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-02-22 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | N/A | 2024-05-30 | 2024-06-03 |  |  |  |  | Government of the Philipppiens | 39995 | 39995 |  | 39995 | 39995 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-C1170 | COMPUTER SUPPLIES | PAO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-12 |  | N/A | 2024-03-22 | 2024-03-22 |  | N/A | N/A | 2024-03-25 |  |  |  | N/A | 2024-04-11 | 2024-04-15 |  |  |  |  | Government of the Philipppiens | 13740 |  | 13740 | 13690 |  | 13690 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-C1138 | MINERAL WATER | PSWDO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-12 |  | N/A | 2024-03-22 | 2024-03-22 |  | N/A | N/A | 2024-03-25 |  |  |  | N/A | 2024-04-11 | 2024-04-15 |  |  |  |  | Government of the Philipppiens | 8979 | 8979 |  | 8760 | 8760 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1466 | WATER | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-12 |  | N/A | 2024-03-22 | 2024-03-22 |  | N/A | N/A | 2024-03-25 |  |  |  | N/A | 2024-04-05 | 2024-04-11 |  |  |  |  | Government of the Philipppiens | 1845 |  | 1845 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1454 | GEMELINA LUMBER | PEO-GA | No | NP-53.9 - Small Value Procurement | 2024-03-05 | 2024-03-08 |  | N/A | 2024-03-22 | 2024-03-22 |  | N/A | N/A | 2024-03-25 |  |  |  | N/A | 2024-04-12 | 2024-04-25 |  |  |  |  | Government of the Philipppiens | 2256 |  | 2256 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1698 | PRINTING | PAO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-20 |  | N/A | 2024-04-02 | 2024-04-02 |  | N/A | N/A | 2024-04-04 |  |  |  | 2024-04-05 | 2024-04-24 | 2024-05-10 |  |  |  |  | Government of the Philipppiens | 120000 |  | 120000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-0987 | PLAQUE/TROPHIES/MEDAL | PAGRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-20 |  | N/A | 2024-04-02 | 2024-04-02 |  | N/A | N/A | 2024-04-04 |  |  |  | N/A | 2024-04-24 | 2024-04-30 |  |  |  |  | Government of the Philipppiens | 8250 |  | 8250 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-0997 | PRINTING | PAGRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-20 |  | N/A | 2024-04-02 | 2024-04-02 |  | N/A | N/A | 2024-04-04 |  |  |  | N/A | 2024-04-24 | 2024-04-30 |  |  |  |  | Government of the Philipppiens | 3500 |  | 3500 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-C0965 | FOOD/CATERING SERVICES | PASSO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-20 |  | N/A | 2024-04-02 | 2024-04-02 |  | N/A | N/A | 2024-04-04 |  |  |  | N/A | 2024-04-29 | 2024-05-03 |  |  |  |  | Government of the Philipppiens | 36250 |  | 36250 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
23-C0787 | MATERIAL TESTING APPARATUS/EQUIPMENT | PEO | No | NP-53.1 Two Failed Biddings | N/A | 2024-01-18 |  | N/A | 2024-04-02 | 2024-04-02 |  | N/A | N/A | 2024-04-04 |  |  |  | 2024-04-05 | 2024-04-19 | 2024-06-20 |  |  |  |  | Government of the Philipppiens | 471715 |  | 471715 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-C1074 | SUPPLY AND DELIVERY OF SEEDLINGS FOR THE USE OF PENRO | PENRO | No | Competitive Bidding | N/A | 2024-02-26 |  | N/A | 2024-03-05 | 2024-03-05 |  | 2024-03-05 | 2024-04-01 | 2024-04-04 |  |  |  | 2024-04-04 | 2024-04-24 | 2024-05-13 |  |  |  |  | Government of the Philipppiens | 879990 |  | 879990 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-03-01 | 2024-03-01 | 2024-03-01 | N/A | N/A | For Delivery
23-5532 | JOB ORDER (LABOR & MATERIALS) | DDOPH-Montevista | No | NP-53.1 Two Failed Biddings | 2023-12-19 | 2024-03-08 |  | N/A | 2024-04-05 | 2024-04-05 |  | N/A | N/A | 2024-04-12 |  |  |  | 2024-04-12 | 2024-04-17 | 2024-05-24 |  |  |  |  | Government of the Philipppiens | 1500000 |  | 1500000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-0862 | TARPAULIN | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-25 |  | N/A | 2024-04-05 | 2024-04-05 |  | N/A | N/A | 2024-04-12 |  |  |  | N/A | 2024-04-23 | 2024-04-25 |  |  |  |  | Government of the Philipppiens | 4480 |  | 4480 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-C1193 | FUEL, OIL, AND LUBRICANTS | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-20 |  | N/A | 2024-04-05 | 2024-04-05 |  | N/A | N/A | 2024-04-12 |  |  |  | N/A | 2024-04-23 | 2024-05-08 |  |  |  |  | Government of the Philipppiens | 11253.2 |  | 11253.2 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1538 | WATER | PAO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-20 |  | N/A | 2024-04-05 | 2024-04-05 |  | N/A | N/A | 2024-04-12 |  |  |  | N/A | 2024-04-24 | 2024-04-30 |  |  |  |  | Government of the Philipppiens | 18860 | 18860 |  | 18400 | 18400 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1643 | WATER | PAO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-20 |  | N/A | 2024-04-05 | 2024-04-05 |  | N/A | N/A | 2024-04-12 |  |  |  | N/A | 2024-04-24 | 2024-04-30 |  |  |  |  | Government of the Philipppiens | 18860 | 18860 |  | 18400 | 18400 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-0964 | FABRICATION AND INSTALLATION OF BILLBOARD | PDRRMO | No | NP-53.9 - Small Value Procurement | 2024-03-05 | 2024-03-11 |  | N/A | 2024-04-05 | 2024-04-05 |  | N/A | N/A | 2024-04-12 |  |  |  | 2024-04-18 | 2024-04-23 | 2024-05-10 |  |  |  |  | Government of the Philipppiens | 272250 |  | 272250 | 261800 |  | 261800 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1476 | TARPAULIN | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-02 |  | N/A | 2024-04-05 | 2024-04-05 |  | N/A | N/A | 2024-04-12 |  |  |  | N/A | 2024-04-19 | 2024-05-14 |  |  |  |  | Government of the Philipppiens | 5600 |  | 5600 | 5600 |  | 5600 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1273 | TARPAULIN | SEF | No | NP-53.9 - Small Value Procurement | 2024-03-22 | 2024-04-02 |  | N/A | 2024-04-05 | 2024-04-05 |  | N/A | N/A | 2024-04-12 |  |  |  | N/A | 2024-04-26 | 2024-05-08 |  |  |  |  | Government of the Philipppiens | 1792 |  | 1792 | 1792 |  | 1792 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-C1073 | TARPAULIN | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-12 |  | N/A | 2024-04-05 | 2024-04-05 |  | N/A | N/A | 2024-04-12 |  |  |  | N/A | 2024-04-23 | 2024-05-08 |  |  |  |  | Government of the Philipppiens | 27580 |  | 27580 | 27383 |  | 27383 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-C1198 | MAGAZINE PRINTING & POCKET BROCHURE | PAO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-25 |  | N/A | 2024-04-08 | 2024-04-08 |  | N/A | N/A | 2024-04-12 |  |  |  | 2024-04-16 | 2024-04-23 | 2024-05-08 |  |  |  |  | Government of the Philipppiens | 90160 |  | 90160 | 82025 |  | 82025 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1726 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-03-22 | 2024-04-02 |  | N/A | 2024-04-08 | 2024-04-08 |  | N/A | N/A | 2024-04-12 |  |  |  | N/A | 2024-04-23 | 2024-05-08 |  |  |  |  | Government of the Philipppiens | 5400 | 5400 |  | 5000 | 5000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1040 | FOOD/CATERING SERVICES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-25 |  | N/A | 2024-04-08 | 2024-04-08 |  | N/A | N/A | 2024-04-12 |  |  |  | N/A | 2024-04-23 | 2024-05-07 |  |  |  |  | Government of the Philipppiens | 46200 |  | 46200 | 45430 |  | 45430 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1122 | PLAQUE/TROPHIES/MEDAL | PHO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-25 |  | N/A | 2024-04-08 | 2024-04-08 |  | N/A | N/A | 2024-04-12 |  |  |  | N/A | 2024-04-23 | 2024-05-08 |  |  |  |  | Government of the Philipppiens | 25000 |  | 25000 | 23000 |  | 23000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1349 | FOOD/CATERING SERVICES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-02 |  | N/A | 2024-04-08 | 2024-04-08 |  | N/A | N/A | 2024-04-12 |  |  |  | N/A | 2024-04-19 | 2024-05-10 |  |  |  |  | Government of the Philipppiens | 19960 |  | 19960 | 19736 |  | 19736 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1446 | FOOD/CATERING SERVICES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-02 |  | N/A | 2024-04-08 | 2024-04-08 |  | N/A | N/A | 2024-04-12 |  |  |  | 2024-04-12 | 2024-04-23 | 2024-05-03 |  |  |  |  | Government of the Philipppiens | 89960 |  | 89960 | 89960 |  | 89960 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-0771 | ACETYLENE REFILL AND INDUSTRIAL OXYGEN REFILL | PDRRMO | No | Direct Contracting | 2024-03-19 | 2024-03-25 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-23 |  |  |  | N/A | 2024-05-09 | 2024-05-22 |  |  |  |  | Government of the Philipppiens | 22275 |  | 22275 | 11425 |  | 11425 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-C1299 | MEDICAL OXYGEN REFILL | PEEMO | No | Direct Contracting | N/A | 2024-04-03 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-23 |  |  |  | N/A | 2024-04-30 | 2024-05-20 |  |  |  |  | Government of the Philipppiens | 2886000 | 2886000 |  | 2886000 | 2886000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1746 | OFFICE SUPPLIES | PAO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2024-03-22 | 2024-04-02 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-23 |  |  |  | N/A | 2024-05-20 | 2024-05-21 |  |  |  |  | Government of the Philipppiens | 19865 | 19865 |  | 19689 | 19689 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1350 | GARMENTS | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-02 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-23 |  |  |  | N/A | 2024-04-25 | 2024-05-14 |  |  |  |  | Government of the Philipppiens | 15000 |  | 15000 | 14850 |  | 14850 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1948 | LIQUID NITROGEN | PVO | No | NP-53.9 - Small Value Procurement | 2024-03-22 | 2024-04-02 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-23 |  |  |  | N/A | 2024-04-30 | 2024-05-10 |  |  |  |  | Government of the Philipppiens | 26400 |  | 26400 | 26080 |  | 26080 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-0865 | EXTERNAL HDD | PAGRO | No | NP-53.9 - Small Value Procurement | 2024-03-22 | 2024-04-02 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-23 |  |  |  | N/A | 2024-04-23 | 2024-05-06 |  |  |  |  | Government of the Philipppiens | 6000 |  | 6000 | 5985 |  | 5985 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1692 | MAGAZINE PRINTING | PAO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-03 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-23 |  |  |  | N/A | 2024-04-29 | 2024-05-22 |  |  |  |  | Government of the Philipppiens | 120000 |  | 120000 | 112500 |  | 112500 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1581 | CELLOPHANE | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-12 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-23 |  |  |  | N/A | 2024-04-25 | 2024-05-08 |  |  |  |  | Government of the Philipppiens | 29000 |  | 29000 | 29000 |  | 29000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-2080 | PLAQUES/TROPHIES/MEDAL | PHRMDO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-25 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-23 |  |  |  | 2024-04-23 | 2024-05-17 | 2024-05-21 |  |  |  |  | Government of the Philipppiens | 146050 |  | 146050 | 146050 |  | 146050 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1553 | TROLLEY SPEAKER, PORTABLE | PAGRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-20 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-23 |  |  |  | N/A | 2024-04-25 | 2024-05-08 |  |  |  |  | Government of the Philipppiens | 33600 | 33600 |  | 33600 | 33600 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-C1259 | BOOKBINDING AND PRINTING | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-02 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-23 |  |  |  | N/A | 2024-04-25 | 2024-05-14 |  |  |  |  | Government of the Philipppiens | 12770 |  | 12770 | 12770 |  | 12770 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-2705 | INSTALLATION OF 100FT MONOPOLE ANTENNA TOWER AND VHF DIGITAL REPEATER | PDRRMO | No | NP-53.1 Two Failed Biddings | 2023-12-05 | 2024-03-25 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-23 |  |  |  | 2024-04-24 | 2024-05-09 | 2024-05-24 |  |  |  |  | Government of the Philipppiens | 688750 |  | 688750 | 680000 |  | 680000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-C1010 | DRUGS AND MEDICINES | PEEMO | No | Competitive Bidding | 2024-02-20 | 2024-02-26 |  | 2024-03-05 | 2024-03-19 | 2024-03-19 |  | 2024-03-19 | 2024-04-17 | 2024-04-29 |  |  |  | 2024-05-08 | 2024-05-20 | 2024-05-27 |  |  |  |  | Government of the Philipppiens | 1445395.4 | 1445395.4 |  | 1445395.4 | 1445395.4 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2024-03-01 | 2024-03-15 | 2024-03-15 | 2024-03-15 | N/A | N/A | For Delivery
24-0651 | COMMUNICATION EQUIPMENT | PICTO | No | Competitive Bidding | 2024-02-20 | 2024-03-04 |  | 2024-03-19 | 2024-04-02 | 2024-04-02 |  | 2024-04-02 | 2024-04-23 | 2024-04-29 |  |  |  | 2024-05-07 | 2024-05-13 | 2024-05-24 |  |  |  |  | Government of the Philipppiens | 2949999 |  | 2949999 | 2948814 |  | 2948814 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2024-03-15 | 2024-04-01 | 2024-04-01 | 2024-04-01 | N/A | N/A | For Delivery
24-C1094 | MEALS AND SNACKS WITH ACCOMMODATION | PSWDO | No | Competitive Bidding | 2024-03-05 | 2024-03-25 |  | N/A | 2024-04-02 | 2024-04-02 |  | 2024-04-02 | 2024-04-17 | 2024-04-29 |  |  |  | 2024-05-06 | 2024-05-13 | 2024-05-23 |  |  |  |  | Government of the Philipppiens | 324000 |  | 324000 | 323595 |  | 323595 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-04-01 | 2024-04-01 | 2024-04-01 | N/A | N/A | For Delivery
24-1348 | LANDRACE HYBRID PIGLET | PVO | No | Competitive Bidding | 2024-03-19 | 2024-03-25 |  | N/A | 2024-04-02 | 2024-04-02 |  | 2024-04-02 | 2024-04-18 | 2024-04-29 |  |  |  | 2024-05-06 | 2024-05-20 | 2024-06-03 |  |  |  |  | Government of the Philipppiens | 240000 |  | 240000 | 239980 |  | 239980 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-04-01 | 2024-04-01 | 2024-04-01 | N/A | N/A | For Delivery
24-C1084 | SEEDLINGS | PENRO | No | Competitive Bidding | N/A | 2024-02-26 |  | N/A | 2024-04-02 | 2024-04-02 |  | 2024-04-02 | 2024-04-19 | 2024-04-29 |  |  |  | 2024-05-07 | 2024-05-22 | 2024-06-20 |  |  |  |  | Government of the Philipppiens | 879990 |  | 879990 | 844726 |  | 844726 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-04-01 | 2024-04-01 | 2024-04-01 | N/A | N/A | For Delivery
24-C1071 | OFFICE SUPPLIES | PAO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-03-25 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | 2024-05-07 | 2024-05-13 | 2024-06-03 |  |  |  |  | Government of the Philipppiens | 227776.5 | 227776.5 |  | 221394.1 | 221394.1 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1773 | FOOD/CATERING SERVICES | PGO | No | NP-53.9 - Small Value Procurement | 2024-03-22 | 2024-04-02 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | 2024-05-07 | 2024-05-13 | 2024-05-23 |  |  |  |  | Government of the Philipppiens | 68000 | 68000 |  | 67600 | 67600 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1334 | SPAREPARTS (AIRCONDITION) | PGSO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-25 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | 2024-05-06 | 2024-05-13 | 2024-06-05 |  |  |  |  | Government of the Philipppiens | 173316 | 173316 |  | 153764 | 153764 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1943 | FOOD/CATERING SERVICES | PAGRO | No | NP-53.9 - Small Value Procurement | 2024-04-02 | 2024-04-08 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-05-20 | 2024-05-23 |  |  |  |  | Government of the Philipppiens | 46000 |  | 46000 | 46000 |  | 46000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-0036 | CARD, TAX | PTO | No | NP-53.9 - Small Value Procurement | 2024-03-19 | 2024-03-25 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-05-17 | 2024-05-21 |  |  |  |  | Government of the Philipppiens | 5500 | 5500 |  | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-2076 | TARPAULIN | PHRMDO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-03 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-05-20 | 2024-05-23 |  |  |  |  | Government of the Philipppiens | 14140 |  | 14140 | 14140 |  | 14140 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-C1295 | FOOD AND CATERING SERVICES | PGO | No | NP-53.9 - Small Value Procurement | 2024-04-02 | 2024-04-08 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | 2024-05-06 | 2024-05-21 | 2024-05-23 |  |  |  |  | Government of the Philipppiens | 70140 |  | 70140 | 70015 |  | 70015 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1697 | POSTER, CALENDAR | PAO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-03 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-05-13 | 2024-05-21 |  |  |  |  | Government of the Philipppiens | 21978 |  | 21978 | 21978 |  | 21978 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-C1293 | FOOD/CATERING SERVICES | PAGRO | No | NP-53.9 - Small Value Procurement | 2024-04-02 | 2024-04-08 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | 2024-05-07 | 2024-05-21 | 2024-05-23 |  |  |  |  | Government of the Philipppiens | 174820 |  | 174820 | 174820 |  | 174820 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1790 | PROJECTOR | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-03 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-05-15 | 2024-06-07 |  |  |  |  | Government of the Philipppiens | 49500 |  | 49500 | 37939 |  | 37939 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-C1152 | REPAIR MATERIALS | PGSO | No | NP-53.9 - Small Value Procurement | 2024-03-22 | 2024-04-02 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-05-13 | 2024-06-05 |  |  |  |  | Government of the Philipppiens | 46511.56 | 46511.56 |  | 46506 | 46506 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1567 | JOB OUT | PGSO | No | NP-53.9 - Small Value Procurement | 2024-03-19 | 2024-03-25 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-05-13 | 0 |  |  |  |  | Government of the Philipppiens | 20500 | 20500 |  | 20000 | 20000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1872 | MONOBLOC PLASTIC CHAIR | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-25 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | 2024-05-07 | 2024-05-17 | 2024-06-03 |  |  |  |  | Government of the Philipppiens | 133500 |  | 133500 | 132500 |  | 132500 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-2072 | FOOD/CATERING SERVICES | PHRMDO | No | NP-53.9 - Small Value Procurement | 2024-04-02 | 2024-04-08 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-05-17 | 2024-05-21 |  |  |  |  | Government of the Philipppiens | 33140 | 33140 |  | 32822 | 32822 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-C1184 | COMMUNICATION SUPPLIES & EQUIPMENT | PICTO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-03 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | 2024-05-06 | 2024-05-13 | 2024-05-21 |  |  |  |  | Government of the Philipppiens | 154054 | 154054 |  | 154054 | 154054 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-2353 | STICKER | PTO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-15 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | 2024-05-08 | 2024-05-20 | 2024-05-22 |  |  |  |  | Government of the Philipppiens | 98000 | 98000 |  | 87500 | 87500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-0848 | GARMENTS | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-08 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-05-13 | 2024-05-23 |  |  |  |  | Government of the Philipppiens | 26400 |  | 26400 | 26400 |  | 26400 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-C1215 | AGRICULTURAL SUPPLIES | PVO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-08 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | 2024-05-06 | 2024-05-13 | 2024-05-23 |  |  |  |  | Government of the Philipppiens | 249835 |  | 249835 | 248050 |  | 248050 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-C1066 | TARPAULIN | PVO | No | NP-53.9 - Small Value Procurement | 2024-04-02 | 2024-04-08 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-05-15 | 2024-05-21 |  |  |  |  | Government of the Philipppiens | 3584 |  | 3584 | 3584 |  | 3584 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-0514 | OTHER MACHINERIES AND EQUIPMENT | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-08 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | 2024-05-06 | 2024-05-17 | 2024-06-20 |  |  |  |  | Government of the Philipppiens | 62535 |  | 62535 | 61400 |  | 61400 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1327 | PADLOCK & VARNISH | PGSO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-15 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-05-15 | 2024-06-03 |  |  |  |  | Government of the Philipppiens | 2785 | 2785 |  | 2785 | 2785 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1960 | TARPAULIN | PHO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-15 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-05-17 | 2024-05-21 |  |  |  |  | Government of the Philipppiens | 5628 |  | 5628 | 5628 |  | 5628 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-2020 | COMPUTER PRINTER | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-08 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-05-17 | 2024-05-21 |  |  |  |  | Government of the Philipppiens | 10000 |  | 10000 | 9323 |  | 9323 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-2037 | TARPAULIN | SEF | No | NP-53.9 - Small Value Procurement | 2024-04-08 | 2024-04-15 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | 2024-05-02 | 2024-05-20 | 2024-05-23 |  |  |  |  | Government of the Philipppiens | 1792 |  | 1792 | 1792 |  | 1792 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-C1308 | ELECTROLYTES ANALYZER | PEEMO | No | Direct Contracting | N/A | 2024-04-03 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-05-13 | 2024-05-24 |  |  |  |  | Government of the Philipppiens | 630375 | 630375 |  | 630375 | 630375 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1847 | GAS | PEO-Motorpool | No | Direct Contracting | 2024-04-05 | 2024-04-15 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-05-13 | 2024-05-22 |  |  |  |  | Government of the Philipppiens | 47140 | 47140 |  | 47140 | 47140 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1959 | PLAQUE | PHO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-15 |  | N/A | 2024-04-30 | 2024-04-30 |  | N/A | N/A | 0 |  |  |  | N/A | 2024-05-13 | 2024-05-21 |  |  |  |  | Government of the Philipppiens | 9500 |  | 9500 | 9500 |  | 9500 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-C1324 | MINERAL WATER | PEEMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-15 |  | N/A | 2024-04-30 | 2024-04-30 |  | N/A | N/A | 0 |  |  |  | N/A | 2024-05-13 | 2024-06-04 |  |  |  |  | Government of the Philipppiens | 49200 | 49200 |  | 48000 | 48000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1916 | FOOD/CATERING SERVICES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-22 |  | N/A | 2024-04-30 | 2024-04-30 |  | N/A | N/A | 2024-05-13 |  |  |  | 2024-05-06 | 2024-05-13 | 2024-05-23 |  |  |  |  | Government of the Philipppiens | 375000 |  | 375000 | 375000 |  | 375000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-C1315 | TIRES | PEEMO | No | NP-53.9 - Small Value Procurement | 2024-04-16 | 2024-04-22 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | 2024-05-17 | 2024-05-24 | 2024-05-28 |  |  |  |  | Government of the Philipppiens | 199352 | 199352 |  | 173912 | 173912 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-C1257 | FOOD/CATERING SERVICES | PGO | No | NP-53.9 - Small Value Procurement | 2024-04-16 | 2024-04-22 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | 2024-05-14 | 2024-05-30 | 2024-06-04 |  |  |  |  | Government of the Philipppiens | 99820 |  | 99820 | 99655 |  | 99655 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-C1333 | FOOD/CATERING SERVICES | PGSO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-22 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | N/A | 2024-05-22 | 2024-06-06 |  |  |  |  | Government of the Philipppiens | 20000 |  | 20000 | 19680 |  | 19680 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-2351 | FOOD/CATERING SERVICES | PTO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-15 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | N/A | 2024-05-22 | 2024-05-31 |  |  |  |  | Government of the Philipppiens | 21000 | 21000 |  | 20850 | 20850 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-C1264 | TARPAULIN | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-22 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | N/A | 2024-05-22 | 2024-06-03 |  |  |  |  | Government of the Philipppiens | 9184 |  | 9184 | 9184 |  | 9184 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-C1255 | MINERAL WATER | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-22 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | 2024-05-15 | 2024-05-22 | 2024-06-04 |  |  |  |  | Government of the Philipppiens | 67650 | 67650 |  | 66000 | 66000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-C1190 | TARPAULIN | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-22 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | N/A | 2024-05-23 | 2024-06-03 |  |  |  |  | Government of the Philipppiens | 14980 |  | 14980 | 14980 |  | 14980 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-2317 | JOB ORDER (LABOR & MATERIALS) ELECTRIC SUBMERSIBLE PUMP | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-03 | 2024-04-30 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | 2024-05-17 | 2024-05-22 | 2024-06-11 |  |  |  |  | Government of the Philipppiens | 220000 | 220000 |  | 220000 | 220000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-0772 | SCUBA DIVING BOOTS | PAGRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-15 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | N/A | 2024-05-22 | 2024-06-03 |  |  |  |  | Government of the Philipppiens | 25000 |  | 25000 | 25000 |  | 25000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-C1141 | JANITORIAL SUPPLIES/HOUSEKEEPING | PENRO | No | NP-53.9 - Small Value Procurement | 2024-03-19 | 2024-03-25 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | N/A | 2024-05-22 | 2024-06-03 |  |  |  |  | Government of the Philipppiens | 16185 |  | 16185 | 16185 |  | 16185 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-2274 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-08 | 2024-04-15 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | N/A | 2024-05-22 | 2024-06-11 |  |  |  |  | Government of the Philipppiens | 45500 | 45500 |  | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-C1104 | LABORATOTY SUPPLIES | PENRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-08 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | 2024-05-13 | 2024-05-22 | 2024-06-03 |  |  |  |  | Government of the Philipppiens | 401221 |  | 401221 | 40121 |  | 40121 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-C1337 | FOOD SUPPLIES | PAO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-22 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | N/A | 2024-05-22 | 2024-06-03 |  |  |  |  | Government of the Philipppiens | 24771 |  | 24771 | 24771 |  | 24771 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-2273 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-16 | 2024-04-22 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | N/A | 2024-05-22 | 2024-06-06 |  |  |  |  | Government of the Philipppiens | 9075 | 9075 |  | 9050 | 9050 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-2265 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-16 | 2024-04-22 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | N/A | 2024-05-22 | 2024-06-06 |  |  |  |  | Government of the Philipppiens | 7950 | 7950 |  | 7930 | 7930 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-C1327 | CONSTRUCTION SUPPLIES | PEEMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-15 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | N/A | 2024-05-22 | 2024-06-11 |  |  |  |  | Government of the Philipppiens | 34753 | 34753 |  | 34753 | 34753 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-C1336 | DOCUMENT SCANNER | PICTO | No | NP-53.9 - Small Value Procurement | 2024-04-16 | 2024-04-22 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | 2024-05-13 | 2024-05-22 | 2024-05-28 |  |  |  |  | Government of the Philipppiens | 176995 |  | 176995 | 175500 |  | 175500 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-C1191 | MEALS AND SNACKS WITH VENUE | PDRRMO | No | Competitive Bidding | N/A | 2024-04-08 |  | N/A | 2024-04-16 | 2024-04-16 |  | 2024-04-16 | 2024-05-09 | 2024-05-13 |  |  |  | 2024-05-13 | 2024-05-27 | 2024-06-04 |  |  |  |  | Government of the Philipppiens | 373430 |  | 373430 | 373430 |  | 373430 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-04-11 | 2024-04-11 | 2024-04-11 | N/A | N/A | For Delivery
24-1163 | MEALS AND SNACKS WITH VENUE | PGO-DILG | No | Competitive Bidding | N/A | 2024-04-08 |  | N/A | 2024-04-16 | 2024-04-16 |  | 2024-04-16 | 2024-05-09 | 2024-05-13 |  |  |  | 2024-05-13 | 2024-05-13 | 2024-05-14 |  |  |  |  | Government of the Philipppiens | 455000 |  | 455000 | 455000 |  | 455000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-04-11 | 2024-04-11 | 2024-04-11 | N/A | N/A | For Delivery
24-0585 | PLASTIC MOLDER SET (6 UNITS/SET) AND PLASTIC SHREDDING MACHINE | PENRO | No | Competitive Bidding | 2024-02-08 | 2024-03-04 |  | N/A | 2024-03-19 | 2024-03-19 |  | 2024-03-19 | 2024-04-17 | 2024-03-15 |  |  |  | 2024-05-15 | 2024-05-27 | 2024-05-30 |  |  |  |  | Government of the Philipppiens | 795000 |  | 795000 | 777000 |  | 777000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-03-15 | 2024-03-15 | 2024-03-15 | N/A | N/A | For Delivery
24-0012 | INSTALLATION OF 22 TO 25KW HYBRID SOLAR POWER SYSTEM, FOR TUNNEL VENTILATED SWINE BREEDING CENTER MULTIPLIER | PVO | No | Competitive Bidding | 2024-03-05 | 2024-04-01 |  | 2024-04-16 | 2024-04-30 | 2024-04-30 |  | 2024-04-30 | 2024-05-10 | 2024-05-16 |  |  |  | 2024-05-17 | 2024-05-22 | 2024-06-03 |  |  |  |  | Government of the Philipppiens | 2000000 |  | 2000000 | 1980000 |  | 1980000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2024-04-11 | 2024-04-24 | 2024-04-24 | 2024-04-24 | N/A | N/A | For Delivery
24-C1165 | CONSTRUCTION MATERIALS | PDRRMO | No | Competitive Bidding | 2024-04-02 | 2024-04-08 |  | 2024-04-16 | 2024-04-30 | 2024-04-30 |  | 2024-04-30 | 2024-05-10 | 2024-05-16 |  |  |  | 2024-05-21 | 2024-05-22 | 2024-06-07 |  |  |  |  | Government of the Philipppiens | 1499916 |  | 1499916 | 1129890 |  | 1129890 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2024-04-11 | 2024-04-24 | 2024-04-24 | 2024-04-24 | N/A | N/A | For Delivery
24-C1210 | VERTERINARY DRUGS AND BIOLOGICS | PVO | No | Competitive Bidding | N/A | 2024-04-08 |  | 2024-04-16 | 2024-04-30 | 2024-04-30 |  | 2024-04-30 | 2024-05-10 | 2024-05-16 |  |  |  | 2024-05-16 | 2024-05-22 | 2024-06-13 |  |  |  |  | Government of the Philipppiens | 1237684 |  | 1237684 | 1105674 |  | 1105674 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2024-04-11 | 2024-04-24 | 2024-04-24 | 2024-04-24 | N/A | N/A | For Delivery
24-2465 | SPAREPARTS (MOTORCYCLE) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-05-03 |  | N/A | 2024-05-14 | 2024-05-14 |  | N/A | N/A | 2024-05-16 |  |  |  | N/A | 2024-05-22 | 2024-06-07 |  |  |  |  | Government of the Philipppiens | 13020 | 13020 |  | 13020 | 13020 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1433 | SERVICES | PDRRMO | No | Direct Contracting | 2024-03-05 | 2024-05-06 |  | N/A | 2024-05-14 | 2024-05-14 |  | N/A | N/A | 2024-05-16 |  |  |  | N/A | 2024-05-27 | 2024-06-13 |  |  |  |  | Government of the Philipppiens | 29880 |  | 29880 | 29880 |  | 29880 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-C1049 | SPAREPARTS (HEAVY EQUIPT) | PEO-Motorpool | No | Direct Contracting | N/A | 2024-05-10 |  | N/A | 2024-05-14 | 2024-05-14 |  | N/A | N/A | 2024-05-16 |  |  |  | N/A | 2024-05-24 | 2024-05-28 |  |  |  |  | Government of the Philipppiens | 2666830.2 | 2666830.2 |  | 2666830.2 | 2666830.2 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1324 | CLOTH,PONGEE | PGSO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-25 |  | N/A | 2024-05-14 | 2024-05-14 |  | N/A | N/A | 2024-05-16 |  |  |  | N/A | 2024-05-22 | 2024-06-06 |  |  |  |  | Government of the Philipppiens | 25000 | 25000 |  | 24975 | 24975 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-2441 | SPAREPARTS (LIGHT VEHICLES) | PDRRMO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-05-13 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-13 | 2024-06-27 |  |  |  |  | Government of the Philipppiens | 4800 | 4800 |  | 4800 | 4800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-2507 | SPAREPARTS (LIGHT VEHICLES) | PDRRMO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-05-13 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-13 | 2024-06-27 |  |  |  |  | Government of the Philipppiens | 2250 | 2250 |  | 2250 | 2250 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-2505 | SPAREPARTS (LIGHT VEHICLES) | PDRRMO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-05-13 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-13 | 2024-06-27 |  |  |  |  | Government of the Philipppiens | 9800 | 9800 |  | 9800 | 9800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-2522 | SPAREPARTS (LIGHT VEHICLES) | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-05-13 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-05 | 2024-06-20 |  |  |  |  | Government of the Philipppiens | 13500 | 13500 |  | 13500 | 13500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-2508 | SPAREPARTS (LIGHT VEHICLES) | PDRRMO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-05-13 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-10 | 2024-06-27 |  |  |  |  | Government of the Philipppiens | 32400 | 32400 |  | 32400 | 32400 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-2570 | SPAREPARTS (LIGHT VEHICLES) | PDRRMO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-05-17 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-13 | 2024-06-27 |  |  |  |  | Government of the Philipppiens | 19080 | 19080 |  | 19080 | 19080 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-2572 | SPAREPARTS (LIGHT VEHICLES) | PDRRMO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-05-17 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-11 | 2024-06-27 |  |  |  |  | Government of the Philipppiens | 18100 | 18100 |  | 18100 | 18100 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-2510 | SPAREPARTS (LIGHT VEHICLES) | PDRRMO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-05-22 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-11 | 2024-06-27 |  |  |  |  | Government of the Philipppiens | 11800 | 11800 |  | 11800 | 11800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-2545 | SPAREPARTS (LIGHT VEHICLES) | DDOPH-Montevista | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-05-22 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-07 | 2024-06-27 |  |  |  |  | Government of the Philipppiens | 9800 | 9800 |  | 9800 | 9800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-0876 | SPAREPARTS (GENERATOR ENGINE) | SPO | No | NP-53.9 - Small Value Procurement | N/A | 2024-02-13 |  | N/A | 2024-02-20 | 2024-02-20 |  | N/A | N/A | 2024-02-22 |  |  |  | N/A | 2024-03-21 | 2024-03-22 |  |  |  |  | Government of the Philipppiens | 31860 | 31860 |  | 31660 | 31660 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1243 | TARPAULIN | PAGRO | No | NP-53.9 - Small Value Procurement | [7 empty] | N/A | N/A | 2024-04-12 |  |  |  | N/A | 2024-04-23 | 2024-05-14 |  |  |  |  | Government of the Philipppiens | 31860 | 31860 |  | 31660 | 31660 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-0231 | POSTAGE AND DELIVERIES | PAO-ADMIN | No | NP-53.9 - Small Value Procurement | 2024-01-31 | 2024-02-02 |  | N/A | 2024-02-20 | 2024-02-20 |  | N/A | N/A | 2024-02-22 |  |  |  | N/A | 2024-02-29 | 2024-03-07 |  |  |  |  | Government of the Philipppiens | 2550 | 2550 |  | 2550 | 2550 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1566 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-03-19 | 2024-03-25 |  | N/A | 2024-04-08 | 2024-04-08 |  | N/A | N/A | 2024-04-12 |  |  |  | N/A | 2024-04-23 | 2024-05-14 |  |  |  |  | Government of the Philipppiens | 58000 | 58000 |  | 56800 | 56800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1158 | FOOD/CATERING SERVICES | PGO | No | NP-53.9 - Small Value Procurement | 2024-03-22 | 2024-04-02 |  | N/A | 2024-04-08 | 2024-04-08 |  | N/A | N/A | 2024-04-12 |  |  |  | N/A | 2024-04-17 | 2024-05-07 |  |  |  |  | Government of the Philipppiens | 479000 |  | 479000 | 474400 |  | 474400 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1979 | DRUGS AND MEDICINES | PHO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-03 |  | N/A | 2024-04-30 | 2024-04-30 |  | N/A | N/A | 2024-05-03 |  |  |  | N/A | 2024-05-13 | 2024-05-23 |  |  |  |  | Government of the Philipppiens | 74256 |  | 74256 | 36283 |  | 36283 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-1793 | FOOD/CATERING SERVICES | PGO |  | NP-53.9 - Small Value Procurement | N/A | 2024-04-22 |  | N/A | 2024-05-14 | 2024-05-14 |  | N/A | N/A | 2024-05-16 |  |  |  | N/A | 2024-06-05 | 2024-06-13 |  |  |  |  | Government of the Philipppiens | 280000 |  | 280000 | 279000 |  | 279000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-2530 | FOOD/CATERING SERVICES | PGO |  | NP-53.9 - Small Value Procurement | N/A | 2024-05-10 |  | N/A | 2024-05-14 | 2024-05-14 |  | N/A | N/A | 2024-05-16 |  |  |  | N/A | 2024-05-23 | 2024-05-24 |  |  |  |  | Government of the Philipppiens | 190000 |  | 190000 | 184500 |  | 184500 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-0863 | INTERNET SUBSCRIPTION | SPO | No | Direct Contracting | N/A | 2024-02-13 |  | N/A | 2024-02-20 | 2024-02-20 |  | N/A | N/A | 2024-02-22 |  |  |  | N/A | 2024-05-13 | [5 empty] | Government of the Philipppiens | 360000 | 360000 |  | 248640 | 248640 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2025 | OFFICE SUPPLIES | PGO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-03-25 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-23 |  |  |  | N/A | 2024-05-10 | [5 empty] | Government of the Philipppiens | 2040 |  | 2040 | 2040 |  | 2040 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-1699 | SPAREPARTS (MOTORCYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-03-19 | 2024-03-25 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-23 |  |  |  | N/A | 2024-04-25 | [5 empty] | Government of the Philipppiens | 4200 | 4200 |  | 4200 | 4200 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-0428 | T-SHIRT WITH PRINT | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-15 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | 2024-05-02 | 2024-05-12 | [5 empty] | Government of the Philipppiens | 13475 |  | 13475 | 13475 |  | 13475 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-1568 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-03-19 | 2024-03-25 |  | N/A | 2024-04-08 | 2024-04-08 |  | N/A | N/A | 2024-04-12 |  |  |  | N/A | 2024-04-23 | [5 empty] | Government of the Philipppiens | 9650 | 9650 |  | 9500 | 9500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
23-5484 | OFFICE EQUIPMENT | SEF | No | Competitive Bidding | 2024-02-20 | 2024-02-26 |  | 2024-03-05 | 2024-03-19 | 2024-03-19 |  | 2024-03-19 | 2024-04-23 | 2024-04-29 |  |  |  | 2024-05-08 | 2024-05-16 | [5 empty] | Government of the Philipppiens | 4250000 |  | 4250000 | 2068707.77 |  | 2068707.77 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2024-03-01 | 2024-03-15 | 2024-03-15 | 2024-03-15 | N/A | N/A | For NTP
24-0466 | GARMENTS | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-08 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-05-13 | [5 empty] | Government of the Philipppiens | 28000 |  | 28000 | 28000 |  | 28000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-1237 | FREON | SPO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-08 |  | N/A | 2024-04-25 | 2024-04-25 |  | N/A | N/A | 2024-04-29 |  |  |  | N/A | 2024-06-06 | [5 empty] | Government of the Philipppiens | 9300 | 9300 |  | 9150 | 9150 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2321 | SPAREPARTS (LIGHT VEHICLES) | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-04-15 |  | N/A | 2024-04-30 | 2024-04-30 |  | N/A | N/A | 0 |  |  |  | N/A | 2024-06-06 | [5 empty] | Government of the Philipppiens | 29900 | 29900 |  | 29900 | 29900 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2192 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-04-22 |  | N/A | 2024-04-30 | 2024-04-30 |  | N/A | N/A | 0 |  |  |  | N/A | 2024-05-15 | [5 empty] | Government of the Philipppiens | 1950 | 1950 |  | 1950 | 1950 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-1759 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-02 | 2024-04-08 |  | N/A | 2024-04-30 | 2024-04-30 |  | N/A | N/A | 2024-05-03 |  |  |  | N/A | 2024-06-10 | [5 empty] | Government of the Philipppiens | 1950 | 1950 |  | 1950 | 1950 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-1750 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-02 | 2024-04-08 |  | N/A | 2024-04-30 | 2024-04-30 |  | N/A | N/A | 2024-05-03 |  |  |  | N/A | 2024-05-14 | [5 empty] | Government of the Philipppiens | 5300 | 5300 |  | 5300 | 5300 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-C1132 | PAINTING MATERIALS | PEO-Motorpool | No | NP-53.9 - Small Value Procurement | 2024-04-02 | 2024-04-08 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | 2024-05-16 | 2024-05-23 | [5 empty] | Government of the Philipppiens | 274632 | 274632 |  | 271008 | 271008 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2366 | SPAREPARTS (MOTORCYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-25 | 2024-04-30 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | N/A | 2024-05-23 | [5 empty] | Government of the Philipppiens | 23000 | 23000 |  | 23000 | 23000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-1240 | INSTALLATION OF THREE PHASE ELECTRICAL TRANSMISSION LINE | PAGRO | No | Competitive Bidding | 2024-04-02 | 2024-04-08 |  | 2024-04-16 | 2024-04-30 | 2024-04-30 |  | 2024-04-30 | 2024-05-10 | 2024-05-16 |  |  |  | 2024-05-16 | 2024-05-22 | [5 empty] | Government of the Philipppiens | 3937264.26 |  | 3937264.26 | 3936264.26 |  | 3936264.26 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2024-04-11 | 2024-04-24 | 2024-04-24 | 2024-04-24 | N/A | N/A | For NTP
24-1742 | JOB OUT: TIRE CHANGING & VULCANIZING | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-04-22 |  | N/A | 2024-05-14 | 2024-05-14 |  | N/A | N/A | 2024-05-16 |  |  |  | N/A | 2024-05-22 | [5 empty] | Government of the Philipppiens | 700 | 700 |  | 700 | 700 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2174 | OFFICE SUPPLIES | PGO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2024-04-08 | 2024-04-15 |  | N/A | 2024-05-14 | 2024-05-14 |  | N/A | N/A | 2024-05-16 |  |  |  | 2024-05-16 | 2024-05-22 | [5 empty] | Government of the Philipppiens | 53678 |  | 53678 | 53678 |  | 53678 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2589 | DUPLICATING PRODUCTS/SPAREPARTS | SPO | No | Direct Contracting | N/A | 2024-05-10 |  | N/A | 2024-05-14 | 2024-05-14 |  | N/A | N/A | 2024-05-16 |  |  |  | N/A | 2024-06-24 | [5 empty] | Government of the Philipppiens | 44301 | 44301 |  | 42261 | 42261 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2325 | SPAREPARTS (MOTORCYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-25 | 2024-04-30 |  | N/A | 2024-05-14 | 2024-05-14 |  | N/A | N/A | 2024-05-16 |  |  |  | N/A | 2024-05-23 | [5 empty] | Government of the Philipppiens | 9200 | 9200 |  | 9166 | 9166 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2039 | MEDICAL KIT | SEF | No | NP-53.9 - Small Value Procurement | 2024-04-08 | 2024-04-15 |  | N/A | 2024-05-14 | 2024-05-14 |  | N/A | N/A | 2024-05-16 |  |  |  | N/A | 2024-05-22 | [5 empty] | Government of the Philipppiens | 1925 |  | 1925 | 1920 |  | 1920 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-C1267 | AGRICULTURAL SUPPLIES | PDRRMO | No | NP-53.1 Two Failed Biddings | N/A | 2024-04-22 |  | N/A | 2024-05-14 | 2024-05-14 |  | N/A | N/A | 2024-05-16 |  |  |  | 2024-05-16 | 2024-05-22 | [5 empty] | Government of the Philipppiens | 381472 |  | 381472 | 379255 |  | 379255 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-1082 | INTERNET FIREWALL SUBSCRIPTION | PICTO | No | Direct Contracting | N/A | 2024-05-13 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-11 | [5 empty] | Government of the Philipppiens | 395000 | 395000 |  | 395000 | 395000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-C1329 | SPAREPARTS ( HOSPITAL EQUIPMENT ) BATTERY PACK, LB 1-A & UD CONT 2002X | PEEMO | No | Direct Contracting | 2024-04-16 | 2024-04-22 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-11 | [5 empty] | Government of the Philipppiens | 428510 | 428510 |  | 428510 | 428510 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-1079 | CLOUD SERVER SUBSCRIPTION | PICTO | No | Direct Contracting | N/A | 2024-05-13 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-10 | [5 empty] | Government of the Philipppiens | 513190.86 | 513190.86 |  | 513190.86 | 513190.86 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2475 | SPAREPARTS (MOTOR CYCLE) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-05-03 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-07 | [5 empty] | Government of the Philipppiens | 7550 | 7550 |  | 7550 | 7550 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-C1345 | SPAREPARTS (HEAVY EQUIPT) | PDRRMO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-05-13 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-10 | [5 empty] | Government of the Philipppiens | 23690 | 23690 |  | 23690 | 23690 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2502 | SPAREPARTS (HEAVY EQUIPT) | PDRRMO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-05-13 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-10 | [5 empty] | Government of the Philipppiens | 12000 | 12000 |  | 12000 | 12000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2509 | SPAREPARTS (LIGHT VEHICLES) | PDRRMO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-05-13 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-11 | [5 empty] | Government of the Philipppiens | 39000 | 39000 |  | 39000 | 39000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2492 | SPAREPARTS (LIGHT VEHICLES) | PDRRMO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-05-13 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-10 | [5 empty] | Government of the Philipppiens | 4500 |  | 4500 | 4500 |  | 4500 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2390 | JOB ORDER(LABOR & | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-05-13 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-11 | [5 empty] | Government of the Philipppiens | 3560 | 3560 |  | 3560 | 3560 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2521 | SPAREPARTS (LIGHT VEHICLES) | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-05-13 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-07 | [5 empty] | Government of the Philipppiens | 45400 | 45400 |  | 45400 | 45400 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2485 | JOB ORDER(LABOR & MATERIALS) | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-05-13 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-10 | [5 empty] | Government of the Philipppiens | 2000 | 2000 |  | 2000 | 2000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2610 | SPAREPARTS (LIGHT VEHICLES) | PDRRMO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-05-13 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-10 | [5 empty] | Government of the Philipppiens | 13500 | 13500 |  | 13500 | 13500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2609 | SPAREPARTS (LIGHT VEHICLES) | PDRRMO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-05-13 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-10 | [5 empty] | Government of the Philipppiens | 1500 | 1500 |  | 1500 | 1500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2392 | SPAREPARTS (MOTOR CYCLE) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-05-17 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-11 | [5 empty] | Government of the Philipppiens | 3320 | 3320 |  | 3320 | 3320 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2623 | SPAREPARTS (MOTOR CYCLE) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-05-22 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-07 | [5 empty] | Government of the Philipppiens | 10600 | 10600 |  | 10600 | 10600 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2622 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-05-22 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-07 | [5 empty] | Government of the Philipppiens | 9400 | 9400 |  | 9400 | 9400 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2624 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-05-22 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-07 | [5 empty] | Government of the Philipppiens | 12000 | 12000 |  | 12000 | 12000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2626 | SPAREPARTS (MOTOR CYCLE) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-05-22 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-07 | [5 empty] | Government of the Philipppiens | 12570 | 12570 |  | 12570 | 12570 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2845 | SPAREPARTS (LIGHT VEHICLES) | PDRRMO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-05-13 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-07 | [5 empty] | Government of the Philipppiens | 1500 | 1500 |  | 1500 | 1500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-1741 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2024-04-16 | 2024-04-22 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-13 | [5 empty] | Government of the Philipppiens | 1850 | 1850 |  | 1850 | 1850 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2162 | OFFICE SUPPLIES | PAO-IPRD | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2024-04-25 | 2024-04-30 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-10 | [5 empty] | Government of the Philipppiens | 7449 | 7449 |  | 7116 | 7116 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2114 | OFFICE SUPPLIES (COLLATERAL FOLDER WITH SAMPLE DESIGN) | PAO-IPRD | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2024-04-25 | 2024-04-30 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-11 | [5 empty] | Government of the Philipppiens | 5500 | 5500 |  | 5500 | 5500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2397 | OFFICE SUPPLIES | PAO-ADMIN | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-05-10 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-11 | [5 empty] | Government of the Philipppiens | 7868 | 7868 |  | 7860 | 7860 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-C1287 | OFFICE SUPPLIES | PDRRMO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-04-30 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-11 | [5 empty] | Government of the Philipppiens | 18262 |  | 18262 | 17973 |  | 17973 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-C1082 | FURNITURES & FIXTURES | PAO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-25 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-10 | [5 empty] | Government of the Philipppiens | 35110 | 35110 |  | 34690 | 34690 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-1724 | JOB ORDER (REPAIR OF 1 UNIT VHF COMMUNICATION REPEATER) | PAO | No | NP-53.9 - Small Value Procurement | 2024-04-30 | 2024-05-02 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-10 | [5 empty] | Government of the Philipppiens | 10000 | 10000 |  | 9800 | 9800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2326 | SPAREPARTS (MOTOR CYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-25 | 2024-04-30 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-10 | [5 empty] | Government of the Philipppiens | 8442 | 8442 |  | 8385 | 8385 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2283 | SPAREPARTS (MOTOR CYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-25 | 2024-04-30 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-10 | [5 empty] | Government of the Philipppiens | 17930 | 17930 |  | 17930 | 17930 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2310 | SPAREPARTS (MOTOR CYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-25 | 2024-04-30 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-11 | [5 empty] | Government of the Philipppiens | 1880 |  | 1880 | 1880 |  | 1880 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-1709 | JANITORIAL SUPPLIES / HOUSEKEEPING | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-12 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-13 | [5 empty] | Government of the Philipppiens | 983 |  | 983 | 950 |  | 950 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2364 | SPAREPARTS (MOTOR CYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-25 | 2024-04-30 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-10 | [5 empty] | Government of the Philipppiens | 2930 | 2930 |  | 2930 | 2930 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2385 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-30 | 2024-05-02 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-10 | [5 empty] | Government of the Philipppiens | 40630 | 40630 |  | 40390 | 40390 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2362 | SPAREPARTS (MOTOR CYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-30 | 2024-05-02 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-13 | [5 empty] | Government of the Philipppiens | 20794 | 20794 |  | 20794 | 20794 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2371 | SPAREPARTS (MOTOR CYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-30 | 2024-05-02 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-13 | [5 empty] | Government of the Philipppiens | 5135 | 5135 |  | 5130 | 5130 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2272 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-16 | 2024-04-22 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-10 | [5 empty] | Government of the Philipppiens | 22150 | 22150 |  | 21960 | 21960 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-1670 | ANDROID CELLPHONE | PAO-IPRD | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-30 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-10 | [5 empty] | Government of the Philipppiens | 14000 |  | 14000 | 12717.88 |  | 12717.88 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2519 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-05-09 | 2024-05-13 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-10 | [5 empty] | Government of the Philipppiens | 17250 | 17250 |  | 17100 | 17100 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2498 | COLORED PRINTER | PAO-ADMIN | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-30 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-11 | [5 empty] | Government of the Philipppiens | 12200 |  | 12200 | 9323 |  | 9323 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2415 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-05-09 | 2024-05-13 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-11 | [5 empty] | Government of the Philipppiens | 1050 | 1050 |  | 1000 | 1000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2548 | COMPUTER LAPTOP | COA | No | NP-53.9 - Small Value Procurement | 2024-04-30 | 2024-05-02 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | 2024-05-30 | 2024-06-10 | [5 empty] | Government of the Philipppiens | 66547 |  | 66547 | 63693 |  | 63693 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2421 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-05-09 | 2024-05-13 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-11 | [5 empty] | Government of the Philipppiens | 3900 | 3900 |  | 3750 | 3750 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2427 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | NP-53.9 - Small Value Procurement | N/A | 2024-05-13 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | 2024-06-03 | 2024-06-13 | [5 empty] | Government of the Philipppiens | 82140 | 82140 |  | 75900 | 75900 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-1529 | MOTHERBOARD GIGABYTE | PAO-PESO | No | NP-53.9 - Small Value Procurement | 2024-04-25 | 2024-04-30 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-10 | [5 empty] | Government of the Philipppiens | 16100 | 16100 |  | 15254 | 15254 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2070 | JANITORIAL SUPPLIES / HOUSEKEEPING | PHRMDO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-25 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-13 | [5 empty] | Government of the Philipppiens | 43101.5 | 43101.5 |  | 43046 | 43046 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2409 | TARPAULIN CONSTRUCTION OF TEACHERS' | SEF | No | NP-53.9 - Small Value Procurement | 2024-05-09 | 2024-05-13 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-11 | [5 empty] | Government of the Philipppiens | 1792 |  | 1792 | 1792 |  | 1792 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-C1303 | CONSTRUCTION SUPPLIES | PVO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-03 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-11 | [5 empty] | Government of the Philipppiens | 36070 | 36070 |  | 36029 | 36029 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2555 | TARPAULIN | PDRRMO | No | NP-53.9 - Small Value Procurement | 2024-05-09 | 2024-05-13 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-10 | [5 empty] | Government of the Philipppiens | 1792 | 1792 |  | 1792 | 1792 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2584 | TARPAULIN | PEO | No | NP-53.9 - Small Value Procurement | 2024-05-09 | 2024-05-13 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-11 | [5 empty] | Government of the Philipppiens | 1792 |  | 1792 | 1792 |  | 1792 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-1969 | JANITORIAL SUPPLIES / HOUSEKEEPING | PVO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-03 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-13 | [5 empty] | Government of the Philipppiens | 14523 | 14523 |  | 14445 | 14445 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2370 | COMPUTER SUPPLIES / SPAREPARTS | PAO-ADMIN | No | NP-53.9 - Small Value Procurement | 2024-05-09 | 2024-05-13 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-13 | [5 empty] | Government of the Philipppiens | 22960 | 22960 |  | 22800 | 22800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-C1305 | KITCHENWARE & UTENSILS | PVO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-03 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-13 | [5 empty] | Government of the Philipppiens | 12706 | 12706 |  | 12570 | 12570 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-1586 | CONSTRUCTION SUPPLIES | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-25 | 2024-04-30 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-11 | [5 empty] | Government of the Philipppiens | 18800 | 18800 |  | 18720 | 18720 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-C1266 | SPAREPARTS ( FARM MACHINERIES AND EQUIPMENT ) | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-05-02 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | 2024-06-05 | 2024-06-13 | [5 empty] | Government of the Philipppiens | 57183.1 |  | 57183.1 | 56052 |  | 56052 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-1902 | TARPAULIN | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-05-10 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-10 | [5 empty] | Government of the Philipppiens | 5600 |  | 5600 | 5600 |  | 5600 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-1919 | PRINTING (PROGRAMS) | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-05-10 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-11 | [5 empty] | Government of the Philipppiens | 9880 |  | 9880 | 9880 |  | 9880 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2481 | WATER | SPO | No | NP-53.9 - Small Value Procurement | N/A | 2024-05-10 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-26 | [5 empty] | Government of the Philipppiens | 25010 | 25010 |  | 24400 | 24400 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2494 | TARPAULIN | SEF | No | NP-53.9 - Small Value Procurement | 2024-05-14 | 2024-05-17 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-10 | [5 empty] | Government of the Philipppiens | 1792 |  | 1792 | 1792 |  | 1792 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-C1144 | CONSTRUCTION SUPPLIES | PVO | No | NP-53.9 - Small Value Procurement | 2024-04-25 | 2024-05-17 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | 2024-05-13 | 2024-06-18 | [5 empty] | Government of the Philipppiens | 243840.7 |  | 243840.7 | 242725.22 |  | 242725.22 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-1428 | T-SHIRT JERSEY | PAO-ADMIN | No | NP-53.9 - Small Value Procurement | 2024-03-19 | 2024-03-25 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-10 | [5 empty] | Government of the Philipppiens | 21700 |  | 21700 | 21700 |  | 21700 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2535 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-05-09 | 2024-05-13 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-11 | [5 empty] | Government of the Philipppiens | 28000 | 28000 |  | 27580 | 27580 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-1329 | ELECTRICAL SUPPLIES | PGSO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-25 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | 2024-06-03 | 2024-06-11 | [5 empty] | Government of the Philipppiens | 160104 | 160104 |  | 155750 | 155750 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2540 | SPAREPARTS (MOTOR CYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-05-09 | 2024-05-13 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-13 | [5 empty] | Government of the Philipppiens | 1560 | 1560 |  | 1500 | 1500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2532 | SPAREPARTS (MOTOR CYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-05-09 | 2024-05-13 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-13 | [5 empty] | Government of the Philipppiens | 3740 | 3740 |  | 3696 | 3696 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2428 | SPAREPARTS (MOTOR CYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-05-09 | 2024-05-13 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-11 | [5 empty] | Government of the Philipppiens | 6925 | 6925 |  | 6860 | 6860 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2551 | SPAREPARTS (MOTOR CYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-05-09 | 2024-05-13 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-13 | [5 empty] | Government of the Philipppiens | 9140 | 9140 |  | 9115 | 9115 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2539 | SPAREPARTS (MOTOR CYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-05-09 | 2024-05-13 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-11 | [5 empty] | Government of the Philipppiens | 3750 | 3750 |  | 3704 | 3704 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2414 | SPAREPARTS (MOTOR CYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-05-09 | 2024-05-13 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-10 | [5 empty] | Government of the Philipppiens | 6080 | 6080 |  | 6020 | 6020 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2425 | SPAREPARTS (MOTOR CYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | N/A | 2024-05-13 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-11 | [5 empty] | Government of the Philipppiens | 9200 | 9200 |  | 9070 | 9070 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2423 | SPAREPARTS (MOTOR CYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-05-09 | 2024-05-13 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-13 | [5 empty] | Government of the Philipppiens | 9200 | 9200 |  | 9070 | 9070 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2543 | SPAREPARTS (MOTOR CYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-05-09 | 2024-05-13 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-11 | [5 empty] | Government of the Philipppiens | 3850 | 3850 |  | 3810 | 3810 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2426 | SPAREPARTS (MOTOR CYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-05-09 | 2024-05-13 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-11 | [5 empty] | Government of the Philipppiens | 18273 | 18273 |  | 17920 | 17920 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-C1013 | CONSTRUCTION SUPPLIES | PEEMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-30 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-13 | [5 empty] | Government of the Philipppiens | 43752 | 43752 |  | 43385 | 43385 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2583 | CONSTRUCTION MATERIALS | PEO | No | NP-53.9 - Small Value Procurement | 2024-05-09 | 2024-05-13 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-10 | [5 empty] | Government of the Philipppiens | 5206 |  | 5206 | 5150 |  | 5150 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-1242 | CONSTRUCTION SUPPLIES | PAGRO | No | NP-53.9 - Small Value Procurement | 2024-04-16 | 2024-04-22 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-10 | [5 empty] | Government of the Philipppiens | 2058 |  | 2058 | 1975 |  | 1975 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2439 | GENSET ENGINE THERMOSTAT | PGSO | No | NP-53.9 - Small Value Procurement | 2024-05-09 | 2024-05-13 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | 2024-06-11 | [5 empty] | Government of the Philipppiens | 14036.66 | 14036.66 |  | 10521.28 | 10521.28 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-C1265 | FOOD/CATERING SERVICES | PDRRMO | No | NP-53.1 Two Failed Biddings | N/A | 2024-05-10 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | 2024-05-31 | 2024-06-10 | [5 empty] | Government of the Philipppiens | 297980 |  | 297980 | 297980 |  | 297980 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-1892 | UTILITY VEHICLE | PAO-ADMIN | No | NP-53.1 Two Failed Biddings | N/A | 2024-05-17 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | 2024-06-03 | 2024-06-11 | [5 empty] | Government of the Philipppiens | 1300000 |  | 1300000 | 1298000 |  | 1298000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-C1307 | SPAREPARTS ( FARM MACHINERIES AND EQUIPMENT ) | PAGRO | No | NP-53.1 Two Failed Biddings | 2024-04-08 | 2024-05-17 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | 2024-06-05 | 2024-06-10 | [5 empty] | Government of the Philipppiens | 508835.8 |  | 508835.8 | 500920 |  | 500920 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-C1310 | CONSTRUCTION SUPPLIES | PAGRO | No | NP-53.1 Two Failed Biddings | 2024-04-16 | 2024-05-17 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | 2024-06-05 | 2024-06-10 | [5 empty] | Government of the Philipppiens | 338328 | 338328 |  | 335722.5 | 335722.5 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-1884 | FOOD/CATERING SERVICES | PGO | No | NP-53.1 Two Failed Biddings | N/A | 2024-05-17 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | 2024-06-01 | 2024-06-10 | [5 empty] | Government of the Philipppiens | 1185000 |  | 1185000 | 1132500 |  | 1132500 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2523 | SPAREPARTS (LIGHT VEHICLES) | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-05-13 |  | N/A | 2024-06-03 | 2024-06-03 |  | N/A | N/A | 2024-06-07 |  |  |  | N/A | 2024-07-02 | [5 empty] | Government of the Philipppiens | 3500 | 3500 |  | 3500 | 3500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2520 | SPAREPARTS (LIGHT VEHICLES) | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-05-13 |  | N/A | 2024-06-03 | 2024-06-03 |  | N/A | N/A | 2024-06-07 |  |  |  | N/A | 2024-06-11 | [5 empty] | Government of the Philipppiens | 3300 | 3300 |  | 3300 | 3300 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-C1155 | CLOUD SERVICE SUBSCRIPTION, CODE REPOSITORY & WEB HOSTING PACKAGE | PICTO | No | NP-53.1 Two Failed Biddings | 2024-04-08 | 2024-05-17 |  | N/A | 2024-06-03 | 2024-06-03 |  | N/A | N/A | 2024-06-07 |  |  |  | 2024-06-09 | 2024-06-11 | [5 empty] | Government of the Philipppiens | 350000 | 350000 |  | 350000 | 350000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2341 | OFFICE EQUIPMENT | PTO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-30 |  | N/A | 2024-06-03 | 2024-06-03 |  | N/A | N/A | 2024-06-07 |  |  |  | N/A | 2024-06-13 | [5 empty] | Government of the Philipppiens | 30000 | 30000 |  | 30000 | 30000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2365 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-25 | 2024-04-30 |  | N/A | 2024-06-03 | 2024-06-03 |  | N/A | N/A | 2024-06-07 |  |  |  | N/A | 2024-06-11 | [5 empty] | Government of the Philipppiens | 1950 | 1950 |  | 1850 | 1850 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-C1160 | CONSTRUCTION MATERIALS | PDRRMO | No | NP-53.9 - Small Value Procurement | 2024-04-25 | 2024-04-30 |  | N/A | 2024-06-03 | 2024-06-03 |  | N/A | N/A | 2024-06-07 |  |  |  | N/A | 2024-06-13 | [5 empty] | Government of the Philipppiens | 10902 |  | 10902 | 10858 |  | 10858 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-C1256 | NURSERY NET & PLASTIC SPRAYER | PAGRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-05-22 |  | N/A | 2024-06-03 | 2024-06-03 |  | N/A | N/A | 2024-06-07 |  |  |  | N/A | 2024-06-11 | [5 empty] | Government of the Philipppiens | 14920 |  | 14920 | 14880 |  | 14880 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2379 | PLAQUE, FIBER GLASS | SEF | No | NP-53.9 - Small Value Procurement | N/A | 2024-05-22 |  | N/A | 2024-06-03 | 2024-06-03 |  | N/A | N/A | 2024-06-07 |  |  |  | N/A | 2024-06-11 | [5 empty] | Government of the Philipppiens | 9000 |  | 9000 | 9000 |  | 9000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2275 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-08 | 2024-04-15 |  | N/A | 2024-06-03 | 2024-06-03 |  | N/A | N/A | 2024-06-07 |  |  |  | 2024-06-10 | 2024-06-11 | [5 empty] | Government of the Philipppiens | 73090 | 73090 |  | 73090 | 73090 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-C1325 | ELECTRICAL SUPPLIES | PEEMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-15 |  | N/A | 2024-06-03 | 2024-06-03 |  | N/A | N/A | 2024-06-07 |  |  |  | 2024-06-06 | 2024-06-11 | [5 empty] | Government of the Philipppiens | 67485 | 67485 |  | 61250 | 61250 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-0870 | TROLLEY SPEAKER, PORTABLE | PAGRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-15 |  | N/A | 2024-06-03 | 2024-06-03 |  | N/A | N/A | 2024-06-07 |  |  |  | N/A | 2024-06-11 | [5 empty] | Government of the Philipppiens | 33600 |  | 33600 | 33600 |  | 33600 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-1462 | JOB ORDER: LABOR, MATERIALS & INSTALLATION OFFICE NAMEPLATE | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-03 |  | N/A | 2024-06-03 | 2024-06-03 |  | N/A | N/A | 2024-06-07 |  |  |  | N/A | 2024-06-11 | [5 empty] | Government of the Philipppiens | 45000 |  | 45000 | 45000 |  | 45000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2416 | TARPAULIN | PAO-ADMIN | No | NP-53.9 - Small Value Procurement | N/A | 2024-05-24 |  | N/A | 2024-06-03 | 2024-06-03 |  | N/A | N/A | 2024-06-07 |  |  |  | N/A | 2024-06-11 | [5 empty] | Government of the Philipppiens | 7476 | 7476 |  | 7476 | 7476 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2607 | SPAREPARTS (LIGHT VEHICLES) | DDOPH-Montevista | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-05-30 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-21 |  |  |  | N/A | 2024-06-20 | [5 empty] | Government of the Philipppiens | 23600 | 23600 |  | 23600 | 23600 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-3051 | SPAREPARTS (MOTOR CYCLE) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-06-05 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-21 |  |  |  | N/A | 2024-06-20 | [5 empty] | Government of the Philipppiens | 2750 | 2750 |  | 2750 | 2750 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2344 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-25 | 2024-04-30 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-21 |  |  |  | N/A | 2024-06-20 | [5 empty] | Government of the Philipppiens | 20800 | 20800 |  | 20800 | 20800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-C1269 | OFFICE SUPPLIES | PHO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-04-15 |  | N/A | 2024-06-03 | 2024-06-03 |  | N/A | N/A | 2024-06-07 |  |  |  | 2024-06-07 | 2024-06-11 | [5 empty] | Government of the Philipppiens | 25448 |  | 25448 | 25448 |  | 25448 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2946 | OFFICE SUPPLIES | PGO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-05-30 |  | N/A | 2024-06-03 | 2024-06-03 |  | N/A | N/A | 2024-06-07 |  |  |  | 2024-06-21 | 2024-06-11 | [5 empty] | Government of the Philipppiens | 2958 | 2958 |  | 2905 | 2905 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-1453 | PORTABLE SOUND SYSTEM | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-03-25 |  | N/A | 2024-04-16 | 2024-04-16 |  | N/A | N/A | 2024-04-23 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 31518 | 31518 |  | 31500 | 31500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-2417 | FOOD/CATERING SERVICES | PAO-ADMIN | No | NP-53.9 - Small Value Procurement | N/A | 2024-05-30 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-20 |  |  |  | 2024-06-24 | 2024-06-20 | 2024-06-28 |  |  |  |  | Government of the Philipppiens | 100000 | 100000 |  | 98858 | 98858 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For Delivery
24-2984 | MONOBLOCK PLASTIC CHAIR | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-05-30 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-20 |  |  |  | 2024-06-21 | [6 empty] | Government of the Philipppiens | 277680 |  | 277680 | 275600 |  | 275600 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-2868 | BATTERY & SELF INKING STAMP WITH ATTACHED SAMPLE | PTO | No | NP-53.9 - Small Value Procurement | N/A | 2024-05-30 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | 2024-06-20 | [5 empty] | Government of the Philipppiens | 5040 | 5040 |  | 5040 | 5040 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2869 | AIRPOT | PTO | No | NP-53.9 - Small Value Procurement | N/A | 2024-05-30 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | 2024-06-20 | [5 empty] | Government of the Philipppiens | 3500 | 3500 |  | 3500 | 3500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2998 | CONSTRUCTION SUPPLIES | PDRRMO | No | NP-53.9 - Small Value Procurement | 2024-05-28 | 2024-05-30 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-20 |  |  |  | 2024-06-21 | 2024-06-20 | [5 empty] | Government of the Philipppiens | 115928 |  | 115928 | 115612 |  | 115612 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2730 | BARCODE SCANNER | PACCO | No | NP-53.9 - Small Value Procurement | N/A | 2024-05-30 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | 2024-06-20 | [5 empty] | Government of the Philipppiens | 1792 |  | 1792 | 1792 |  | 1792 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2514 | TARPAULIN | SEF | No | NP-53.9 - Small Value Procurement | 2024-05-28 | 2024-05-30 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | 2024-06-20 | [5 empty] | Government of the Philipppiens | 1792 |  | 1792 | 1792 |  | 1792 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2992 | TARPAULIN | PEO | No | NP-53.9 - Small Value Procurement | 2024-05-28 | 2024-05-30 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | 2024-06-20 | [5 empty] | Government of the Philipppiens | 1792 |  | 1792 | 1792 |  | 1792 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2419 | FOOD/CATERING SERVICES | PAO-ADMIN | No | NP-53.9 - Small Value Procurement | N/A | 2024-05-30 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-20 |  |  |  | 2024-06-24 | 2024-06-20 | [5 empty] | Government of the Philipppiens | 230000 | 230000 |  | 230000 | 230000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2542 | FOOD/CATERING SERVICES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-05-30 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | 2024-06-20 | [5 empty] | Government of the Philipppiens | 12480 | 12480 |  | 12366 | 12366 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-3000 | TARPAULIN | PDRRMO | No | NP-53.9 - Small Value Procurement | 2024-05-28 | 2024-05-30 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | 2024-06-20 | [5 empty] | Government of the Philipppiens | 1792 |  | 1792 | 1792 |  | 1792 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-1883 | POSTER CALENDAR | PAO-ADMIN | No | NP-53.9 - Small Value Procurement | N/A | 2024-05-30 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | 2024-06-20 | [5 empty] | Government of the Philipppiens | 24981 |  | 24981 | 23467 |  | 23467 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2605 | TARPAULIN | PAO-ADMIN | No | NP-53.9 - Small Value Procurement | N/A | 2024-05-30 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | 2024-06-20 | [5 empty] | Government of the Philipppiens | 28000 | 28000 |  | 28000 | 28000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-C1372 | COMPUTER SUPPLIES & PRINTER | PBO | No | NP-53.9 - Small Value Procurement | N/A | 2024-05-30 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | 2024-06-20 | [5 empty] | Government of the Philipppiens | 25137 | 25137 |  | 21111 | 21111 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2713 | PUBLICATION OF ORDINANCES | SPO | No | NP-53.9 - Small Value Procurement | 2024-05-28 | 2024-05-30 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-20 |  |  |  | 2024-06-21 | 2024-06-20 | [5 empty] | Government of the Philipppiens | 180000 | 180000 |  | 150000 | 150000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2928 | FOOD/CATERING SERVICES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-05-30 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-20 |  |  |  | 2024-06-21 | 2024-06-20 | [5 empty] | Government of the Philipppiens | 74460 |  | 74460 | 73584 |  | 73584 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2319 | CHB | PEO | No | NP-53.9 - Small Value Procurement | 2024-04-25 | 2024-05-30 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | 2024-06-20 | [5 empty] | Government of the Philipppiens | 6270 |  | 6270 | 6270 |  | 6270 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-1910 | WATER | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-15 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | 2024-06-20 | [5 empty] | Government of the Philipppiens | 1640 |  | 1640 | 1600 |  | 1600 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2320 | CHB | PEO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-15 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | 2024-06-20 | [5 empty] | Government of the Philipppiens | 6270 |  | 6270 | 6270 |  | 6270 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2064 | CONSTRUCTION MATERIALS | SEF | No | NP-53.9 - Small Value Procurement | 2024-04-05 | 2024-04-15 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-20 |  |  |  | 2024-06-20 | 2024-06-21 | [5 empty] | Government of the Philipppiens | 224734.8 |  | 224734.8 | 224325 |  | 224325 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2377 | POWER TOOLS TIRE WRENCE | PDRRMO | No | NP-53.9 - Small Value Procurement | 2024-05-28 | 2024-05-30 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | 2024-06-20 | [5 empty] | Government of the Philipppiens | 18700 |  | 18700 | 18696 |  | 18696 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2862 | INDUSTRIAL FLOOR FAN | PGSO | No | NP-53.9 - Small Value Procurement | N/A | 2024-05-30 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | 2024-06-20 | [5 empty] | Government of the Philipppiens | 20850 | 20850 |  | 20844 | 20844 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-C1340 | COMPUTER SUPPLIES | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-30 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | 2024-06-20 | [5 empty] | Government of the Philipppiens | 24400 |  | 24400 | 24370 |  | 24370 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2867 | RECHARGEABLE BATTERY & BATTERY CHARGER | PTO | No | NP-53.9 - Small Value Procurement | N/A | 2024-05-30 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | 2024-06-20 | [5 empty] | Government of the Philipppiens | 2360 | 2360 |  | 2360 | 2360 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2672 | HEAVY DUTY HYDRAULIC JACK | PDRRMO | No | NP-53.9 - Small Value Procurement | 2024-05-28 | 2024-05-30 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | 2024-06-20 | [5 empty] | Government of the Philipppiens | 14800 |  | 14800 | 14799 |  | 14799 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2934 | PIPE WRENCH | PDRRMO | No | NP-53.9 - Small Value Procurement | 2024-05-28 | 2024-05-30 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | 2024-06-20 | [5 empty] | Government of the Philipppiens | 5200 |  | 5200 | 5198 |  | 5198 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-1241 | JOB ORDER: SUPPLY AND INSTALLATION OF 3 UNITS OF 50KVA DISTRIBUTION TRANSFER | PAGRO | No | Competitive Bidding | 2024-04-16 | 2024-04-29 |  | 2024-05-09 | 2024-05-28 | 2024-05-28 |  | 2024-05-28 | 2024-06-14 | 2024-06-20 |  |  |  | 2024-06-21 | 2024-06-28 | [5 empty] | Government of the Philipppiens | 794859 |  | 794859 | 750000 |  | 750000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2024-05-07 | 2024-05-27 | 2024-05-27 | 2024-05-27 | N/A | N/A | For NTP
23-4953 | SUPPLY AND DELIVERY OF LAPTOP (MIDRANGE) | SEF | No | Competitive Bidding | 2024-05-09 | 2024-05-13 |  | N/A | 2024-05-28 | 2024-05-28 |  | 2024-05-28 | 2024-06-14 | 2024-06-20 |  |  |  | 2024-06-21 | 2024-06-28 | [5 empty] | Government of the Philipppiens | 165000 |  | 165000 | 157200 |  | 157200 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-05-27 | 2024-05-27 | 2024-05-27 | N/A | N/A | For NTP
24-2803 | TONER | PBO | No | Direct Contracting | N/A | 2024-06-05 |  | N/A | 2024-06-18 | 2024-06-18 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | 2024-07-02 | [5 empty] | Government of the Philipppiens | 6023 | 6023 |  | 6023 | 6023 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2881 | SPAREPARTS (LIGHT VEHICLES) | PDRRMO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-06-14 |  | N/A | 2024-06-18 | 2024-06-18 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | 2024-06-26 | [5 empty] | Government of the Philipppiens | 85000 | 85000 |  | 85000 | 85000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-3381 | JOB ORDER(LABOR & MATERIALS) | VGO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-06-14 |  | N/A | 2024-06-18 | 2024-06-18 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | 2024-07-01 | [5 empty] | Government of the Philipppiens | 3500 | 3500 |  | 3500 | 3500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2692 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2024-05-28 | 2024-05-30 |  | N/A | 2024-06-18 | 2024-06-18 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | 2024-07-01 | [5 empty] | Government of the Philipppiens | 63050 | 63050 |  | 43150 | 43150 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2853 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-05-30 |  | N/A | 2024-06-18 | 2024-06-18 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | 2024-06-26 | [5 empty] | Government of the Philipppiens | 56580 | 56580 |  | 51130 | 51130 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2681 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2024-05-28 | 2024-05-30 |  | N/A | 2024-06-18 | 2024-06-18 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | 2024-06-26 | [5 empty] | Government of the Philipppiens | 5500 | 5500 |  | 4800 | 4800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2721 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2024-05-28 | 2024-05-30 |  | N/A | 2024-06-18 | 2024-06-18 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | 2024-06-26 | [5 empty] | Government of the Philipppiens | 31650 | 31650 |  | 29630 | 29630 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2574 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2024-05-28 | 2024-05-30 |  | N/A | 2024-06-18 | 2024-06-18 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | 2024-07-01 | [5 empty] | Government of the Philipppiens | 5500 | 5500 |  | 4800 | 4800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2674 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2024-05-28 | 2024-05-30 |  | N/A | 2024-06-18 | 2024-06-18 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | 2024-06-26 | [5 empty] | Government of the Philipppiens | 15700 | 15700 |  | 15300 | 15300 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2851 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-05-30 |  | N/A | 2024-06-18 | 2024-06-18 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | 2024-06-26 | [5 empty] | Government of the Philipppiens | 20500 | 20500 |  | 19500 | 19500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-2680 | SPAREPARTS (MOTOR | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2024-05-28 | 2024-05-30 |  | N/A | 2024-06-18 | 2024-06-18 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | 2024-06-26 | [5 empty] | Government of the Philipppiens | 12740 | 12740 |  | 12671 | 12671 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For NTP
24-3017 | CONSTRUCTION SUPPLIES | PEO | No | Competitive Bidding | 2024-05-28 | 2024-06-03 |  | N/A | 2024-06-11 | 2024-06-11 |  | 2024-06-11 | 2024-06-14 | 2024-06-26 |  |  |  | 2024-06-27 | [6 empty] | Government of the Philipppiens | 675042 |  | 675042 | 574974 |  | 574974 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-06-07 | 2024-06-07 | 2024-06-07 | N/A | N/A | For PO Approval
24-2361 | SPAREPARTS (MOTORCYCLE) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-25 | 2024-04-30 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 900 | 900 |  | 900 | 900 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-2546 | WATER DISPENSER | PENRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-05-06 |  | N/A | 2024-05-14 | 2024-05-14 |  | N/A | N/A | 2024-05-16 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 13200 | 13200 |  | 13150 | 13150 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-2553 | PICTURE FRAME | SPO | No | NP-53.9 - Small Value Procurement | N/A | 2024-05-06 |  | N/A | 2024-05-14 | 2024-05-14 |  | N/A | N/A | 2024-05-16 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 6600 | 6600 |  | 6580 | 6580 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-2486 | SPAREPARTS (LIGHT VEHICLES) | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-05-24 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 9075 | 9075 |  | 9075 | 9075 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-2474 | DOORSIGN & TABLESIGN | SPO | No | NP-53.9 - Small Value Procurement | N/A | 2024-05-06 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 16000 | 16000 |  | 16000 | 16000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-0864 | MONTHLY INTERNET SUBSCRIPTION | SPO | No | NP-53.1 Two Failed Biddings | N/A | 2024-05-10 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | 2024-05-30 | [6 empty] | Government of the Philipppiens | 403200 | 403200 |  | 403200 | 403200 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-2219 | SPAREPARTS (LIGHT VEHICLES) | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-05-13 |  | N/A | 2024-06-03 | 2024-06-03 |  | N/A | N/A | 2024-06-07 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 7000 | 7000 |  | 7000 | 7000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-2606 | SPAREPARTS (LIGHT VEHICLES) | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-05-13 |  | N/A | 2024-06-03 | 2024-06-03 |  | N/A | N/A | 2024-06-07 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 24150 | 24150 |  | 24150 | 24150 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-C1313 | ACETYLENE REFILL | PAGRO | No | Direct Contracting | 2024-04-16 | 2024-04-22 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-21 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 48620 | 48620 |  | 24540 | 24540 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-2141 | TONER FOR MP 2555SP- GESTETNER | SEF | No | Direct Contracting | 2024-05-28 | 2024-05-30 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-21 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 6023 | 6023 |  | 6023 | 6023 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-2854 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-05-30 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-21 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 69300 | 69300 |  | 69300 | 69300 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-2855 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-05-30 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-21 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 36200 | 36200 |  | 36200 | 36200 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-3050 | SPAREPARTS (MOTOR CYCLE) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-06-05 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-21 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 3150 | 3150 |  | 3150 | 3150 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-3092 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-06-05 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-21 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 101250 | 101250 |  | 101250 | 101250 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-3049 | SPAREPARTS (MOTOR CYCLE) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-06-05 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-21 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 5850 | 5850 |  | 5850 | 5850 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-2308 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | NP-53.9 - Small Value Procurement | 2024-04-25 | 2024-04-30 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-21 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 1100 | 1100 |  | 1100 | 1100 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-1422 | CONSTRUCTION MATERIALS | PEO | No | NP-53.9 - Small Value Procurement | N/A | 2024-05-17 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-21 |  |  |  | 2024-06-24 | [6 empty] | Government of the Philipppiens | 434704.27 |  | 434704.27 | 432438 |  | 432438 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-C1201 | CONSTRUCTION MATERIALS | PEO | No | NP-53.9 - Small Value Procurement | N/A | 2024-05-22 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-21 |  |  |  | 2024-06-21 | [6 empty] | Government of the Philipppiens | 716536.59 |  | 716536.59 | 714454 |  | 714454 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-C1274 | CONSTRUCTION MATERIALS | PEO | No | NP-53.9 - Small Value Procurement | N/A | 2024-05-22 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-21 |  |  |  | 2024-06-21 | [6 empty] | Government of the Philipppiens | 399962 |  | 399962 | 391957 |  | 391957 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-1674 | CONSTRUCTION MATERIALS | PEO | No | NP-53.9 - Small Value Procurement | N/A | 2024-05-22 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-21 |  |  |  | 2024-06-21 | [6 empty] | Government of the Philipppiens | 496028.3 |  | 496028.3 | 493840 |  | 493840 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-C1290 | CONSTRUCTION MATERIALS | PEO | No | NP-53.9 - Small Value Procurement | N/A | 2024-05-22 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-21 |  |  |  | 2024-06-24 | [6 empty] | Government of the Philipppiens | 399962 |  | 399962 | 397277 |  | 397277 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-2850 | TARPAULIN | PEO | No | NP-53.9 - Small Value Procurement | 2024-05-28 | 2024-05-30 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 1792 |  | 1792 | 1792 |  | 1792 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-2988 | TARPAULIN | PEO | No | NP-53.9 - Small Value Procurement | 2024-05-28 | 2024-05-30 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 1792 |  | 1792 | 1792 |  | 1792 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-3020 | TARPAULIN | PEO | No | NP-53.9 - Small Value Procurement | 2024-05-28 | 2024-05-30 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 1792 |  | 1792 | 1792 |  | 1792 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-2715 | TARPAULIN | SPO | No | NP-53.9 - Small Value Procurement | 2024-05-28 | 2024-05-30 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 14000 | 14000 |  | 14000 | 14000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-C1363 | COLORED PRINTER & POWER SUPPLY | SPO | No | NP-53.9 - Small Value Procurement | N/A | 2024-05-24 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-20 |  |  |  | 2024-06-21 | [6 empty] | Government of the Philipppiens | 55280 | 55280 |  | 55000 | 55000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-2360 | ACCOUNTABLE FORMS | PTO | No | NP-53.5 Agency-to-Agency | 2024-04-16 | 2024-04-22 |  | N/A | 2024-06-18 | 2024-06-18 |  | N/A | N/A | 2024-06-20 |  |  |  | 2024-06-21 | [6 empty] | Government of the Philipppiens | 1899865 | 1899865 |  | 1545568.25 | 1545568.25 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-2725 | SPAREPARTS (MOTOR CYCLE) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2024-05-28 | 2024-05-30 |  | N/A | 2024-06-18 | 2024-06-18 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 1700 | 1700 |  | 1675 | 1675 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-2678 | SPAREPARTS (MOTOR CYCLE) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2024-05-28 | 2024-05-30 |  | N/A | 2024-06-18 | 2024-06-18 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 5850 | 5850 |  | 5845 | 5845 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-2852 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-05-30 |  | N/A | 2024-06-18 | 2024-06-18 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 9450 | 9450 |  | 8500 | 8500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-2728 | SPAREPARTS (MOTOR CYCLE) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2024-05-28 | 2024-05-30 |  | N/A | 2024-06-18 | 2024-06-18 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 10150 | 10150 |  | 10120 | 10120 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-2732 | SPAREPARTS (MOTOR CYCLE) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2024-05-28 | 2024-05-30 |  | N/A | 2024-06-18 | 2024-06-18 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 15750 | 15750 |  | 15695 | 15695 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-2677 | SPAREPARTS (LIGHT | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2024-05-28 | 2024-05-30 |  | N/A | 2024-06-18 | 2024-06-18 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 1300 | 1300 |  | 1200 | 1200 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-2673 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2024-05-28 | 2024-05-30 |  | N/A | 2024-06-18 | 2024-06-18 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 8250 | 8250 |  | 7300 | 7300 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-1267 | LUMBER | SEF | No | NP-53.9 - Small Value Procurement | 2024-03-19 | 2024-03-25 |  | N/A | 2024-06-18 | 2024-06-18 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 7347.51 |  | 7347.51 | 7269.34 |  | 7269.34 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-1426 | LUMBER | PEO | No | NP-53.9 - Small Value Procurement | 2024-03-19 | 2024-03-25 |  | N/A | 2024-06-18 | 2024-06-18 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 43616 |  | 43616 | 43152 |  | 43152 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-1809 | LUMBER | PEO | No | NP-53.9 - Small Value Procurement | 2024-03-19 | 2024-03-25 |  | N/A | 2024-06-18 | 2024-06-18 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 20601.51 |  | 20601.51 | 20382.34 |  | 20382.34 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-2190 | LUMBER | PEO | No | NP-53.9 - Small Value Procurement | 2024-04-02 | 2024-04-08 |  | N/A | 2024-06-18 | 2024-06-18 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 21071.51 |  | 21071.51 | 20847.34 |  | 20847.34 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-1258 | LUMBER | PAGRO | No | NP-53.9 - Small Value Procurement | 2024-04-02 | 2024-04-08 |  | N/A | 2024-06-18 | 2024-06-18 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 2256 |  | 2256 | 2208 |  | 2208 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-2393 | BINDER AND SELF INKING PAD W/ SAMPLE | PTO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-22 |  | N/A | 2024-06-18 | 2024-06-18 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 6090 | 6090 |  | 5880 | 5880 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-C1342 | SPAREPARTS (LIGHT VEHICLES) | SPO | No | NP-53.9 - Small Value Procurement | 2024-05-09 | 2024-05-13 |  | N/A | 2024-06-18 | 2024-06-18 |  | N/A | N/A | 2024-06-20 |  |  |  | 2024-06-21 | [6 empty] | Government of the Philipppiens | 389756 | 389756 |  | 377675 | 377675 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-2799 | UTILITY BOX | PBO | No | NP-53.9 - Small Value Procurement | N/A | 2024-05-30 |  | N/A | 2024-06-18 | 2024-06-18 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 6000 | 6000 |  | 5916 | 5916 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-2036 | LUMBER | SEF | No | NP-53.9 - Small Value Procurement | 2024-04-05 | 2024-04-15 |  | N/A | 2024-06-18 | 2024-06-18 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 7347.51 |  | 7347.51 | 7269.34 |  | 7269.34 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-1363 | LUMBER | PVGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-04-30 |  | N/A | 2024-06-18 | 2024-06-18 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 4136 | 4136 |  | 4092 | 4092 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-C1347 | LUMBER | PDRRMO | No | NP-53.9 - Small Value Procurement | 2024-05-09 | 2024-05-13 |  | N/A | 2024-06-18 | 2024-06-18 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 21693.08 | 21693.08 |  | 21515.58 | 21515.58 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-2408 | LUMBER | SEF | No | NP-53.9 - Small Value Procurement | 2024-05-09 | 2024-05-13 |  | N/A | 2024-06-18 | 2024-06-18 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 20082.51 |  | 20082.51 | 20011.84 |  | 20011.84 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-2581 | LUMBER | PEO | No | NP-53.9 - Small Value Procurement | 2024-05-09 | 2024-05-13 |  | N/A | 2024-06-18 | 2024-06-18 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 2256 |  | 2256 | 2232 |  | 2232 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-2767 | CLOTH & STREAMERS | PDRRMO | No | NP-53.9 - Small Value Procurement | 2024-05-28 | 2024-05-30 |  | N/A | 2024-06-18 | 2024-06-18 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 8800 |  | 8800 | 8800 |  | 8800 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-2515 | MEDICAL KIT | SEF | No | NP-53.9 - Small Value Procurement | 2024-05-28 | 2024-05-30 |  | N/A | 2024-06-18 | 2024-06-18 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 1925 |  | 1925 | 1920 |  | 1920 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-3082 | OIL, PENETRATING | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-05 |  | N/A | 2024-06-18 | 2024-06-18 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 3750 |  | 3750 | 3720 |  | 3720 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-3215 | FOOD/CATERING SERVICES FOR | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-05 |  | N/A | 2024-06-18 | 2024-06-18 |  | N/A | N/A | 2024-06-20 |  |  |  | 2024-06-24 | [6 empty] | Government of the Philipppiens | 80500 |  | 80500 | 80237.5 |  | 80237.5 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-2919 | FOOD/CATERING SERVICES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-05 |  | N/A | 2024-06-18 | 2024-06-18 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 4500 |  | 4500 | 4485 |  | 4485 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-2991 | MEDICAL KIT | PDRRMO | No | NP-53.9 - Small Value Procurement | 2024-06-03 | 2024-06-05 |  | N/A | 2024-06-18 | 2024-06-18 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 1925 |  | 1925 | 1920 |  | 1920 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-3073 | CONSTRUCTION MATERIALS | PDRRMO | No | NP-53.9 - Small Value Procurement | 2024-06-03 | 2024-06-05 |  | N/A | 2024-06-18 | 2024-06-18 |  | N/A | N/A | 2024-06-20 |  |  |  | 2024-06-24 | [6 empty] | Government of the Philipppiens | 173317 |  | 173317 | 173312 |  | 173312 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-C1408 | MACHINE MAINTENANCE SUPPLIES | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-05 |  | N/A | 2024-06-18 | 2024-06-18 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 17323.8 |  | 17323.8 | 17261 |  | 17261 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-C1362 | MEDICAL SUPPLIES | PDRRMO | No | NP-53.9 - Small Value Procurement | 2024-06-03 | 2024-06-05 |  | N/A | 2024-06-18 | 2024-06-18 |  | N/A | N/A | 2024-06-20 |  |  |  | 2024-06-21 | [6 empty] | Government of the Philipppiens | 287715 |  | 287715 | 118400 |  | 118400 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-2806 | SPAREPARTS (LIGHT VEHICLES) | PDRRMO | No | NP-53.9 - Small Value Procurement | 2024-06-03 | 2024-06-05 |  | N/A | 2024-06-18 | 2024-06-18 |  | N/A | N/A | 2024-06-20 |  |  |  | 2024-06-22 | [6 empty] | Government of the Philipppiens | 141295 | 141295 |  | 110500 | 110500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-1165 | SPAREPARTS (LIGHT VEHICLES) | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-05 |  | N/A | 2024-06-18 | 2024-06-18 |  | N/A | N/A | 2024-06-20 |  |  |  | 2024-06-22 | [6 empty] | Government of the Philipppiens | 73776 |  | 73776 | 66000 |  | 66000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-3595 | PLAQUE | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-18 |  | N/A | 2024-06-18 | 2024-06-18 |  | N/A | N/A | 2024-06-20 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 3000 |  | 3000 | 2996 |  | 2996 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-3108 | ACCOUNTABLE FORMS | PTO | No | NP-53.5 Agency-to-Agency | N/A | 2024-06-05 |  | N/A | 2024-06-25 | 2024-06-25 |  | N/A | N/A | 2024-06-26 |  |  |  | 2024-06-28 | [6 empty] | Government of the Philipppiens | 562500 |  | 562500 | 355472 |  | 355472 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-2878 | SPAREPARTS (LIGHT VEHICLES) | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-06-20 |  | N/A | 2024-06-25 | 2024-06-25 |  | N/A | N/A | 2024-06-26 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 5800 | 5800 |  | 5800 | 5800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-C1361 | JOB ORDER: REIMBURSEMENT | SPO | No | Shopping 52.1(a) - Unforeseen Contingency | 2024-06-18 | 2024-06-20 |  | N/A | 2024-06-25 | 2024-06-25 |  | N/A | N/A | 2024-06-26 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 8900 | 8900 |  | 8900 | 8900 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-3057 | SPAREPARTS (MOTOR CYCLE) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-06-20 |  | N/A | 2024-06-25 | 2024-06-25 |  | N/A | N/A | 2024-06-26 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 4000 | 4000 |  | 4000 | 4000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-3562 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-06-20 |  | N/A | 2024-06-25 | 2024-06-25 |  | N/A | N/A | 2024-06-26 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 26050 | 26050 |  | 26050 | 26050 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-2884 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-06-14 |  | N/A | 2024-06-25 | 2024-06-25 |  | N/A | N/A | 2024-06-26 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 8570 | 8570 |  | 8500 | 8500 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-2793 | SPAREPARTS (HEAVY EQUIPT) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-06-14 |  | N/A | 2024-06-25 | 2024-06-25 |  | N/A | N/A | 2024-06-26 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 52000 | 52000 |  | 49850 | 49850 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-2842 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-06-14 |  | N/A | 2024-06-25 | 2024-06-25 |  | N/A | N/A | 2024-06-26 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 9750 | 9750 |  | 9700 | 9700 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-2843 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-06-14 |  | N/A | 2024-06-25 | 2024-06-25 |  | N/A | N/A | 2024-06-26 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 22000 | 22000 |  | 21800 | 21800 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-2813 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-06-14 |  | N/A | 2024-06-25 | 2024-06-25 |  | N/A | N/A | 2024-06-26 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 22000 | 22000 |  | 22000 | 22000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-2917 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-06-14 |  | N/A | 2024-06-25 | 2024-06-25 |  | N/A | N/A | 2024-06-26 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 29500 | 29500 |  | 29400 | 29400 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-2726 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2024-05-28 | 2024-05-30 |  | N/A | 2024-06-25 | 2024-06-25 |  | N/A | N/A | 2024-06-26 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 2450 | 2450 |  | 2300 | 2300 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-2513 | CIRCUIT BOARD | PGSO | No | NP-53.9 - Small Value Procurement | N/A | 2024-05-03 |  | N/A | 2024-06-25 | 2024-06-25 |  | N/A | N/A | 2024-06-26 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 57566.74 | 57566.74 |  | 53000 | 53000 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-2632 | ELECTRONIC MULTI- PURPOSE ULTRASONIC PEST REPELLER | SPO | No | NP-53.9 - Small Value Procurement | N/A | 2024-05-17 |  | N/A | 2024-06-25 | 2024-06-25 |  | N/A | N/A | 2024-06-26 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 4000 | 4000 |  | 3700 | 3700 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-2587 | MEDICAL KIT | PEO | No | NP-53.9 - Small Value Procurement | 2024-05-14 | 2024-05-17 |  | N/A | 2024-06-25 | 2024-06-25 |  | N/A | N/A | 2024-06-26 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 1925 |  | 1925 | 1920 |  | 1920 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-C1373 | JANITORIAL SUPPLIES | PAGRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-05 |  | N/A | 2024-06-25 | 2024-06-25 |  | N/A | N/A | 2024-06-26 |  |  |  | 2024-06-26 | [6 empty] | Government of the Philipppiens | 101290 |  | 101290 | 100580 |  | 100580 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-2496 | MEDICAL KIT | SEF | No | NP-53.9 - Small Value Procurement | 2024-05-14 | 2024-05-17 |  | N/A | 2024-06-25 | 2024-06-25 |  | N/A | N/A | 2024-06-26 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 1925 |  | 1925 | 1920 |  | 1920 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-3676 | GEAR OIL AND PENETRATING OIL | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-14 |  | N/A | 2024-06-25 | 2024-06-25 |  | N/A | N/A | 2024-06-26 |  |  |  | N/A | [6 empty] | Government of the Philipppiens | 4961.2 |  | 4961.2 | 4950 |  | 4950 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-2938 | SPAREPARTS (LIGHT VEHICLES) | PVGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-14 |  | N/A | 2024-06-25 | 2024-06-25 |  | N/A | N/A | 2024-06-26 |  |  |  | 2024-06-27 | [6 empty] | Government of the Philipppiens | 233720 | 233720 |  | 143200 | 143200 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | For PO Approval
24-C1161 | DRUGS AND MEDICINES | PHO | No | Competitive Bidding | 2024-04-25 | 2024-04-29 |  | 2024-05-09 | 2024-05-28 | 2024-05-28 |  | 2024-05-28 | 2024-06-14 | 2024-06-26 |  |  |  | 2024-06-27 | [6 empty] | Government of the Philipppiens | 1244516 |  | 1244516 | 1029353.4 |  | 1029353.4 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2024-05-07 | 2024-05-27 | 2024-05-27 | 2024-05-27 | N/A | N/A | For PO Approval
24-2565 | MEALS AND SNACKS A | PSWDO | No | Competitive Bidding | 2024-05-09 | 2024-05-13 |  | N/A | 2024-06-11 | 2024-06-11 |  | 2024-06-11 | 2024-06-14 | 2024-06-26 |  |  |  | 2024-06-26 | [6 empty] | Government of the Philipppiens | 2040000 |  | 2040000 | 2016000 |  | 2016000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-06-07 | 2024-06-07 | 2024-06-07 | N/A | N/A | For PO Approval
24-C1272 | CONSTRUCTION MATERIALS | PEO | No | Competitive Bidding | N/A | 2024-04-29 |  | 2024-05-09 | 2024-05-28 | 2024-05-28 |  | 2024-05-28 | 2024-06-14 | 2024-06-26 |  |  |  | 2024-06-27 | [6 empty] | Government of the Philipppiens | 1195435 | 1195435 |  | 675931 | 675931 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2024-05-07 | 2024-05-27 | 2024-05-27 | 2024-05-27 | N/A | N/A | For PO Approval
24-2407 | CONSTRUCTION MATERIALS | PEO | No | Competitive Bidding | 2024-05-09 | 2024-05-13 |  | N/A | 2024-05-28 | 2024-05-28 |  | 2024-05-28 | 2024-06-14 | 2024-06-26 |  |  |  | 2024-06-27 | [6 empty] | Government of the Philipppiens | 757981.85 |  | 757981.85 | 756182 |  | 756182 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-05-27 | 2024-05-27 | 2024-05-27 | N/A | N/A | For PO Approval
24-2549 | CONSTRUCTION MATERIALS | PEO | No | Competitive Bidding | N/A | 2024-05-20 |  | N/A | 2024-05-28 | 2024-05-28 |  | 2024-05-28 | 2024-06-14 | 2024-06-26 |  |  |  | 2024-06-27 | [6 empty] | Government of the Philipppiens | 370815 | 370815 |  | 370768 | 370768 |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-05-27 | 2024-05-27 | 2024-05-27 | N/A | N/A | For PO Approval
24-2512 | CONSTRUCTION SUPPLIES | PEO | No | Competitive Bidding | 2024-05-28 | 2024-06-03 |  | N/A | 2024-05-28 | 2024-05-28 |  | 2024-05-28 | 2024-06-14 | 2024-06-26 |  |  |  | 2024-06-27 | [6 empty] | Government of the Philipppiens | 262375.72 |  | 262375.72 | 231022.5 |  | 231022.5 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-05-27 | 2024-05-27 | 2024-05-27 | N/A | N/A | For PO Approval
24-2847 | CONSTRUCTION SUPPLIES | PEO | No | Competitive Bidding | 2024-05-28 | 2024-06-03 |  | N/A | 2024-06-11 | 2024-06-11 |  | 2024-06-11 | 2024-06-14 | 2024-06-26 |  |  |  | 2024-06-27 | [6 empty] | Government of the Philipppiens | 631681 |  | 631681 | 539934 |  | 539934 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-06-07 | 2024-06-07 | 2024-06-07 | N/A | N/A | For PO Approval
24-2989 | CONSTRUCTION SUPPLIES | PEO | No | Competitive Bidding | 2024-05-28 | 2024-06-03 |  | N/A | 2024-06-11 | 2024-06-11 |  | 2024-06-11 | 2024-06-14 | 2024-06-26 |  |  |  | 2024-06-27 | [6 empty] | Government of the Philipppiens | 317776 |  | 317776 | 257378 |  | 257378 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-06-07 | 2024-06-07 | 2024-06-07 | N/A | N/A | For PO Approval
24-2493 | CONSTRUCTION SUPPLIES | PEO | No | Competitive Bidding | 2024-05-28 | 2024-06-03 |  | N/A | 2024-06-11 | 2024-06-11 |  | 2024-06-11 | 2024-06-14 | 2024-06-26 |  |  |  | 2024-06-27 | [6 empty] | Government of the Philipppiens | 275019.82 |  | 275019.82 | 259141 |  | 259141 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-06-07 | 2024-06-07 | 2024-06-07 | N/A | N/A | For PO Approval
24-C1335 | STAINLESS STEEL CYLINDRICAL WATER STORAGE TANK (HORIZONTAL), 20, 000 LTRS CAPACITY, | PEO | No | Competitive Bidding | 2024-04-30 | 2024-05-06 |  | 2024-05-14 | 2024-05-28 | 2024-05-28 |  | 2024-05-28 | 2024-06-14 | 2024-06-26 | [10 empty] | Government of the Philipppiens | 1119678 |  | 1119678 | 993000 |  | 993000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2024-05-09 | 2024-05-27 | 2024-05-27 | 2024-05-27 | N/A | N/A | Ongoing Procurement Process
24-2559 | GLASS | PGSO | No | Competitive Bidding | 2024-05-09 | 2024-05-13 |  | N/A | 2024-05-28 | 2024-05-28 |  | 2024-05-28 | 2024-06-14 | 2024-06-26 | [10 empty] | Government of the Philipppiens | 191698.04 |  | 191698.04 | 190800 |  | 190800 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-05-27 | 2024-05-27 | 2024-05-27 | N/A | N/A | Ongoing Procurement Process
24-C1268 | MEALS AND SNACKS WITH ACCOMMODATION | PGO | No | Competitive Bidding | 2024-05-20 | 2024-05-28 |  | N/A | 2024-06-11 | 2024-06-11 |  | 2024-06-11 | 2024-06-19 | 2024-06-26 | [10 empty] | Government of the Philipppiens | 1320000 |  | 1320000 | 1320000 |  | 1320000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-06-07 | 2024-06-07 | 2024-06-07 | N/A | N/A | Ongoing Procurement Process
24-2586 | INSTALLATION OF TRANSFORMER FOR THE IMPROVEMENT OF BAHAY PANGARAP FACILITY | PEO | No | Competitive Bidding | 2024-05-28 | 2024-06-03 |  | N/A | 2024-06-11 | 2024-06-11 |  | 2024-06-11 | 2024-06-19 | 2024-06-26 | [10 empty] | Government of the Philipppiens | 270858 |  | 270858 | 230000 |  | 230000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-06-07 | 2024-06-07 | 2024-06-07 | N/A | N/A | Ongoing Procurement Process
24-2560 | INSTALLATION OF GAS | PGSO | No | Competitive Bidding | 2024-05-28 | 2024-06-03 |  | N/A | 2024-06-11 | 2024-06-11 |  | 2024-06-11 | 2024-06-19 | 2024-06-26 | [10 empty] | Government of the Philipppiens | 532396.25 |  | 532396.25 | 520100 |  | 520100 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-06-07 | 2024-06-07 | 2024-06-07 | N/A | N/A | Ongoing Procurement Process
24-2396 | COMPLETION OF GYM, STAGE, AGUINALDO NATIONAL LAAK, DAVAO DE ORO | SEF | No | Competitive Bidding | 2024-04-25 | 2024-05-20 |  | 2024-05-28 | 2024-06-11 | 2024-06-11 |  | 2024-06-11 | 2024-06-20 | 2024-06-26 | [10 empty] | Government of the Philipppiens | 1543162.09 |  | 1543162.09 | 1493354.44 |  | 1493354.44 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2024-05-27 | 2024-06-07 | 2024-06-07 | 2024-06-07 | N/A | N/A | Ongoing Procurement Process
24-2518 | IMPROVEMENT OF DAVAO DE ORO PROVINCIAL HOSPITAL, MONTEVISTA | PEO | No | Competitive Bidding | 2024-05-09 | 2024-05-21 |  | N/A | 2024-06-11 | 2024-06-11 |  | 2024-06-11 | 2024-06-20 | 2024-06-26 | [10 empty] | Government of the Philipppiens | 272577.49 |  | 272577.49 | 270512.29 |  | 270512.29 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-06-07 | 2024-06-07 | 2024-06-07 | N/A | N/A | Ongoing Procurement Process
24-0101 (REBID) | SUPPLY AND DELIVERY OF SHALLOW TUBE WELL PUMP SET 8HP WITH COMPLETE ACCESSORIES | PAGRO | No | Competitive Bidding | 2024-04-02 | 2024-04-08 |  | 2024-04-16 | 2024-04-30 | 2024-04-30 |  | 2024-04-30 | 2024-05-30 | 2024-06-21 |  |  |  | 2024-06-21 | 2024-06-21 | [5 empty] | Government of the Philipppiens | 3893000 |  | 3893000 | 3842000 |  | 3842000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2024-04-11 | 2024-04-24 | 2024-04-24 | 2024-04-24 | N/A | N/A | Ongoing Procurement Process
24-C1279 | SUPPLY AND DELIVERY OF OFFICE EQUIPMENTS | PEO | No | Competitive Bidding | 2024-03-19 | 2024-04-22 |  | 2024-04-30 | 2024-05-14 | 2024-05-14 |  | 2024-05-14 | 2024-05-21 | 2024-05-29 |  |  |  | 2024-05-30 | 2024-06-07 | [5 empty] | Government of the Philipppiens | 4022098.4 |  | 4022098.4 | 3973499 |  | 3973499 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2024-04-24 | 2024-05-09 | 2024-05-09 | 2024-05-09 | N/A | N/A | Ongoing Procurement Process
24-C1140 | SUPPLY AND DELIVERY OF SPAREPARTS | PEO-MOTORPOOL | No | NP-53.1 Two Failed Biddings | 2024-03-05 | 2024-05-10 |  | N/A | 2024-06-03 | 2024-06-03 |  | N/A | N/A | 2024-06-05 |  |  |  | 2024-06-05 | 2024-06-11 | [5 empty] | Government of the Philipppiens | 1979215 |  | 1979215 | 783066 |  | 783066 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-4950 | MEALS AND SNACKS | PDRRMO | No | NP-53.1 Two Failed Biddings | N/A | 2024-03-01 |  | N/A | 2024-03-19 | 2024-03-19 |  | N/A | N/A | 2024-03-21 |  |  |  | 2024-03-25 | 2024-04-04 | 2024-04-11 |  |  |  |  | Government of the Philipppiens | 500000 |  | 500000 | 500000 |  | 500000 |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
23-0340 | CONSTRUCTION OF SCHOOL FACILITY BUILDING (SCIENCE LABORATORY) AT PANGI NATIONAL HIGH SCHOOL, PANGI, MACO, DAVAO DE ORO | PEO | No | Competitive Bidding | 2024-02-20 | 2024-06-10 |  | 2024-06-18 | [16 empty] | Government of the Philipppiens | 2808471.79 |  | 2808471.79 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2024-06-14 | [5 empty] | Ongoing Procurement Process
24-0891 | CONSTRUCTION OF ONE (1) STOREY-TWO (2) CLASSROOMS SCHOOL BUILDING WITH TOILET ATTACHED AT MANURIGAO IS, NEW BATAAN, DAVAO DE ORO | PEO | No | Competitive Bidding | 2024-02-20 | 2024-05-27 |  | 2024-06-11 | 2024-06-25 | 2024-06-25 |  | 2024-06-25 | [12 empty] | Government of the Philipppiens | 3864022.63 |  | 3864022.63 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2024-06-07 | 2024-06-20 | 2024-06-20 | 2024-06-20 |  |  | Ongoing Procurement Process
24-0886 | CONSTRUCTION OF ONE (1) STOREY-TWO (2) CLASSROOMS SCHOOL BUILDING WITH TOILET ATTACHED AT PANGI NHS, MACO, DAVAO DE ORO | SEF | No | Competitive Bidding | 2024-02-20 | 2024-05-27 |  | 2024-06-11 | 2024-06-25 | 2024-06-25 |  | 2024-06-25 | [12 empty] | Government of the Philipppiens | 3293744.24 |  | 3293744.24 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2024-06-07 | 2024-06-20 | 2024-06-20 | 2024-06-20 |  |  | Ongoing Procurement Process
24-0339 | CONSTRUCTION OF CENTER ISLAND WITH SOLAR LIGHTS AT MAWAB, DAVAO DE ORO | PEO | No | Competitive Bidding | 2024-05-28 | [19 empty] | Government of the Philipppiens | 2872872.67 |  | 2872872.67 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2386 | CONSTRUCTION OF MULTI-PURPOSE HALL , CORAZON ES , BRGY. OSMENA , COMPOSTELA , DAVAO DE ORO | SEF | No | Competitive Bidding | 2024-04-25 | 2024-05-27 |  | 2024-06-11 | 2024-06-25 | 2024-06-25 |  | 2024-06-25 | [12 empty] | Government of the Philipppiens | 6096583.28 |  | 6096583.28 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2024-06-07 | 2024-06-20 | 2024-06-20 | 2024-06-20 |  |  | Ongoing Procurement Process
24-2537 | CONSTRUCTION OF DOUBLE BARREL BOX CULVERT CULVERT AT BRGY. DUMLAN MACO (KKMP), DAVAO DE ORO | PDRRMO | No | Competitive Bidding | 2024-05-09 | 2024-06-10 |  | 2024-06-18 | [16 empty] | Government of the Philipppiens | 4900246.12 |  | 4900246.12 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2024-06-14 | [5 empty] | Ongoing Procurement Process
24-1333 | CONSTRUCTION OF ONE (1) STOREY-TWO (2) CLASSROOMS SCHOOL BUILDING WITH TOILET ATTACHED AT BIASONG ES, PANTUKAN | SEF | No | Competitive Bidding | 2024-05-28 | 2024-06-10 |  | 2024-06-18 | [16 empty] | Government of the Philipppiens | 3974858.79 |  | 3974858.79 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2024-06-14 | [5 empty] | Ongoing Procurement Process
24-2561 | CONSTRUCTION OF BLEACHERS AND STAGE, BRGY. SAOSAO, MAWAB, DAVAO DE ORO (CONSTRUCTION OF 42 IN.M. BLEACHERS) | PEO | No | Competitive Bidding | 2024-05-28 | 2024-06-10 |  | 2024-06-18 | [16 empty] | Government of the Philipppiens | 2357503.25 |  | 2357503.25 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2024-06-14 | [5 empty] | Ongoing Procurement Process
24-2708 | CONSTRUCTION OF BLEACHERS AND STAGE, BRGY. KIDAWA, LAAK, DAVAO DE ORO (CONSTRUCTION OF 1 BAY COVERED COURT WITH STAGE AND 1 BAY BLEACHERS) | PEO | No | Competitive Bidding | 2024-05-28 | 2024-06-10 |  | 2024-06-18 | [16 empty] | Government of the Philipppiens | 2411434.42 |  | 2411434.42 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2024-06-14 | [5 empty] | Ongoing Procurement Process
24-3002 | CONSTRUCTION OF BLEACHER AND CR, ANDILI ELEMENTARY SCHOOL GYM, MAWAB (CONSTRUCTION OF 21 IN.M. BLEACHERS) | PEO | No | Competitive Bidding | 2024-05-28 | 2024-06-10 |  | 2024-06-18 | [16 empty] | Government of the Philipppiens | 1420177.63 |  | 1420177.63 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2024-06-14 | [5 empty] | Ongoing Procurement Process
24-3001 | CONSTRUCTION OF FOOT BRIDGE, PRK. 13, MAINIT, GOLDEN VALLEY, MABINI [CONSTRUCTION OF 35 IN.M. FOOT BRIDGE WITH 8 IN.M. CONCRETE FLOOR SLAB (APPROACH SLAB) BOTH SIDE] | PEO | No | Competitive Bidding | 2024-05-28 | [19 empty] | Government of the Philipppiens | 3304923.16 |  | 3304923.16 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2996 | CONSTRUCTION OF STAGE AND BLEACHERS, BRGY. CONCEPTION, LAAK, (CONSTRUCTION OF 1 BAY COVERED COURT WITH STAGE AND 1 BAY BLEACHERS) | PEO | No | Competitive Bidding | 2024-05-28 | 2024-06-10 |  | 2024-06-18 | [16 empty] | Government of the Philipppiens | 2402829.1 |  | 2402829.1 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3025 | CONSTRUCTION OF BRGY. HALL, BRGY. INCAYAN, LAAK, [CONSTRUCTION OF 142 IN.M. (1 STOREY) BRGY. HALL) | PEO | No | Competitive Bidding | 2024-05-28 | [19 empty] | Government of the Philipppiens | 4832890.94 |  | 4832890.94 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3022 | CONSTRUCTION OF BLEACHERS (GYM), BRGY. NUEVA VISAYAS, MAWAB, (CONSTRUCTION OF 36 IN.M. BLEACHERS) | PEO | No | Competitive Bidding | 2024-05-28 | [19 empty] | Government of the Philipppiens | 1930060.79 |  | 1930060.79 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3024 | CONSTRUCTION OF FOOT BRIDGE, PRK. 2, MANTUNGA, GOLDEN VALLEY, MABINI [CONSTRUCTION OF 43 IN.M. FOOT BRIDGE WITH 8 IN.M. CONCRETE FLOOR SLAB (APPROACH SLAB) BOTH SIDES] | PEO | No | Competitive Bidding | 2024-05-28 | [19 empty] | Government of the Philipppiens | 3761348.05 |  | 3761348.05 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3023 | CONSTRUCTION OF BLEAHERS AND STAGE, BAWANI GYM, MAWAB (CONSTRUCTION OF 1 BAY COVARED COURT WITH STAGE AND 48 IN.M. BLEACHERS | PEO | No | Competitive Bidding | 2024-06-03 | [19 empty] | Government of the Philipppiens | 3861823.28 |  | 3861823.28 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2997 | CONSTRUCTION OF MULTIPURPOSE BUILDING (MUSLIM COMMUNITY), BRGY. BANBANON, LAAK [CONSTRUCTION OF FOUR (4) BAYS MULTIPURPOSE BUILDING] | PEO | No | Competitive Bidding | 2024-05-28 | 2024-06-10 |  | 2024-06-18 | [16 empty] | Government of the Philipppiens | 1586283.43 |  | 1586283.43 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | 2024-06-14 | [5 empty] | Ongoing Procurement Process
24-2706 | CONSTRUCTION OF STAGE, BAWANI GYM, MAWAB | PEO | No | Competitive Bidding | 2024-05-28 | 2024-06-12 |  | N/A | [16 empty] | Government of the Philipppiens | 959629.38 |  | 959629.38 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3085 | CONSTRUCTION OF RETAINING WALL AT PUROK 2-A, BRGY. PINDASAN, MABINI | PEO | No | Competitive Bidding | 2024-06-11 | [19 empty] | Government of the Philipppiens | 3758574.21 |  | 3758574.21 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3221 | REHABILITATION OF NEW-VISAYAS-BANAGBANAG, MONTEVISTA TO MAGADING | PEO | No | Competitive Bidding | 2024-06-11 | 2024-06-18 | [18 empty] | Government of the Philipppiens | 279838000 |  | 279838000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3083 | CONSTRUCTION OF BARANGAY HEALTH STATION (BHS) AT PUROK 1, BARANGAY MANURIGAO, NEW BATAAN (CONSTRUCTION OF 75.3SQ.M. BRGY. HEALTH STATION WITH BIRTHING) | PEO | No | Competitive Bidding | 2024-06-11 | [19 empty] | Government of the Philipppiens | 2380209.14 |  | 2380209.14 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-1261 | PLUMBING SUPPLIES | PGSO | No | NP-53.1 Two Failed Biddings | N/A | 2024-04-22 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | 2024-05-19 | 2024-05-22 | [5 empty] | Government of the Philipppiens | 307229.5 |  | 307229.5 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
24-1127 | RICE 50KGS (WELL MILLED RICE) WITH IRON FORTIFIED | PHO | No | NP-53.1 Two Failed Biddings | 2024-03-19 | 2024-04-22 |  | N/A | 2024-05-09 | 2024-05-09 |  | N/A | N/A | 2024-05-13 |  |  |  | 2024-05-16 | 2024-05-22 | [5 empty] | Government of the Philipppiens | 726000 |  | 726000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
24-C1065 | LUMBER | PVO | No | NP-53.1 Two Failed Biddings | 2024-03-05 | 2024-04-22 |  | N/A | 2024-06-11 | 2024-06-11 |  | N/A | N/A | 2024-06-21 |  |  |  | 2024-06-21 | [6 empty] | Government of the Philipppiens | 298788.49 |  | 298788.49 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
24-C1102 | AGRICULTURAL SUPPLIES | PAGRO | No | NP-53.1 Two Failed Biddings | 2024-03-19 | 2024-04-22 |  | N/A | 2024-05-28 | 2024-05-28 |  | N/A | N/A | 2024-05-29 |  |  |  | 2024-05-29 | 2024-06-11 | [5 empty] | Government of the Philipppiens | 618838 |  | 618838 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | N/A | N/A | N/A | N/A | N/A | Ongoing Procurement Process
24-2229 | MEALS AND SNACKS WITH ACCOMMODATION | PSWDO | No | NP-53.1 Two Failed Biddings | 2024-04-02 | 2024-06-11 |  | N/A | N/A | [15 empty] | Government of the Philipppiens | 862500 |  | 862500 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1139 | MEALS AND SNACKS WITH VENUE AND ACCOMMODATION | PGO | No | NP-53.1 Two Failed Biddings | N/A | 2024-06-14 |  | N/A | N/A | [15 empty] | Government of the Philipppiens | 1770000 |  | 1770000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1314 | MEALS AND SNACKS WITH ACCOMMODATION | PHO | No | NP-53.1 Two Failed Biddings | N/A | 2024-06-14 |  | N/A | N/A | [15 empty] | Government of the Philipppiens | 172500 |  | 172500 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1123 | CONSTRUCTION MATERIALS | PGSO | No | Competitive Bidding | 2024-06-18 | 2024-06-24 |  | N/A | N/A | 2024-07-02 | [14 empty] | Government of the Philipppiens | 969925.06 |  | 969925.06 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-0132 | MOBILE MULTIMEDIA CONTROLLER | PICTO | No | NP-53.1 Two Failed Biddings | N/A | 2024-05-17 | [18 empty] | Government of the Philipppiens | 380000 |  | 380000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1212 | MEALS AND SNACKS | PHO | No | NP-53.1 Two Failed Biddings | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 493880 |  | 493880 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-1027 | INTERNET SUBSCRIPTION B | PICTO | No | Competitive Bidding | 2024-04-08 | 2024-05-20 |  | 2024-05-28 | 2024-06-11 | 2024-06-11 |  | 2024-06-11 | [12 empty] | Government of the Philipppiens | 1137576 |  | 1137576 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2499 | MEALS AND SNACKS | SEF | No | Competitive Bidding | N/A | 2024-06-12 |  | N/A | 2024-06-25 | 2024-06-25 | [14 empty] | Government of the Philipppiens | 400000 |  | 400000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2985 | CONSTRUCTION MATERIALS | PEO | No | Competitive Bidding | 2024-05-28 | 2024-06-03 |  | 2024-06-11 | 2024-06-25 | 2024-06-25 | [14 empty] | Government of the Philipppiens | 5121025.16 |  | 5121025.16 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-1774 | AIRCON, 5.0TR FLOOR MOUNTED SPLIT TYPE WITH INSTALLATION | PAO | No | Competitive Bidding | 2024-05-28 | 2024-06-19 |  | N/A | [16 empty] | Government of the Philipppiens | 107168 |  | 107168 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1368 | MOTORCYCLE (125 CC) | PDRRMO | No | Competitive Bidding | 2024-05-28 | 2024-06-19 |  | N/A | [16 empty] | Government of the Philipppiens | 160000 |  | 160000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1400 | X-RAY MACHINE WITH DIGITAL RADIOGRAPHY | PEEMO | No | Competitive Bidding | 2024-05-28 | 2024-06-03 |  | 2024-06-11 | 2024-06-25 | [15 empty] | Government of the Philipppiens | 18600000 |  | 18600000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-1755 | CONTAINER VAN CLASS B, 20 FTR PAINTED, W/ PLY-BOARD FLOORING | PENRO | No | Competitive Bidding | N/A | 2024-06-19 | [18 empty] | Government of the Philipppiens | 360000 |  | 360000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1417 | MEALS AND SNACKS WITH ACCOMOODARION NOTE: W/ PREBID | PDRRMO | No | Competitive Bidding | 2024-06-03 | 2024-06-18 |  | N/A | [16 empty] | Government of the Philipppiens | 287715 |  | 287715 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1433 | MEALS AND SNACKS | PDRRMO | No | Competitive Bidding | 2024-06-03 | 2024-06-12 | [18 empty] | Government of the Philipppiens | 990960 |  | 990960 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1364 | AGRICULTURAL SUPPLIES | PAGRO | No | Competitive Bidding | N/A | 2024-05-27 |  | 2024-06-11 | 2024-06-25 | [15 empty] | Government of the Philipppiens | 1156325 |  | 1156325 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1481 | DRUGS AND MEDICINES | PDRRMO | No | Competitive Bidding | 2024-06-11 | 2024-06-19 |  | N/A | [16 empty] | Government of the Philipppiens | 714902.08 |  | 714902.08 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1393 | CONSTRUCTION MATERIALS | PGO | No | Competitive Bidding | 2024-06-11 | 2024-06-24 |  | N/A | [16 empty] | Government of the Philipppiens | 880620 |  | 880620 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3037 | CONSTRUCTION MATERIALS | PEO | No | Competitive Bidding | 2024-06-11 | 2024-06-19 |  | N/A | [16 empty] | Government of the Philipppiens | 452607.32 |  | 452607.32 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3357 | MEALS AND SNACKS WITH ACCOMMODATION | PLO | No | Competitive Bidding | 2024-06-11 | 2024-06-24 |  | 2024-07-02 | [16 empty] | Government of the Philipppiens | 3520000 |  | 3520000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1465 | MEALS AND SNACKS WITH VENUE | PHO | No | Competitive Bidding | 2024-06-11 | 2024-06-19 |  | 2024-07-02 | [16 empty] | Government of the Philipppiens | 588590 |  | 588590 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2604 | MEALS AND SNACKS WITH ACCOMMODATION | PAO | No | Competitive Bidding | N/A | 2024-06-12 |  | N/A | 2024-06-25 | [15 empty] | Government of the Philipppiens | 560000 |  | 560000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | N/A | 2024-06-20 | 2024-06-20 | 2024-06-20 | N/A | N/A | Ongoing Procurement Process
24-3279 | LAPTOP (CLERICAL WORK) | PGO | No | Competitive Bidding | N/A | 2024-06-19 | [18 empty] | Government of the Philipppiens | 468000 |  | 468000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3368 | MEDICAL, DENTAL AND LABORATORY EQUIPMENT | PHO | No | Competitive Bidding | N/A | 2024-06-19 |  | N/A | 2024-07-02 | [15 empty] | Government of the Philipppiens | 827000 |  | 827000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1482 | MEDICAL SUPPLIES | PDRRMO | No | Competitive Bidding | N/A | 2024-06-19 |  | N/A | 2024-07-02 | [15 empty] | Government of the Philipppiens | 265105 |  | 265105 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1486 | AGRICULTURAL SUPPLIES | PDRRMO | No | Competitive Bidding | N/A | 2024-06-19 |  | N/A | 2024-07-02 | [15 empty] | Government of the Philipppiens | 385110 |  | 385110 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3356 | RICE (WELL MILLED) 50KG/SACK | PDRRMO | No | Competitive Bidding | N/A | 2024-06-19 |  | N/A | 2024-07-02 | [15 empty] | Government of the Philipppiens | 300000 |  | 300000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1488 | MEALS AND SNACKS | PDRRMO | No | Competitive Bidding | N/A | 2024-06-19 |  | N/A | 2024-07-02 | [15 empty] | Government of the Philipppiens | 274580 |  | 274580 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3110 | MEALS AND SNACKS | PGO | No | Competitive Bidding | N/A | 2024-06-19 |  | N/A | 2024-07-02 | [15 empty] | Government of the Philipppiens | 395000 |  | 395000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1402 | MEALS AND SNACKS | PGO | No | Competitive Bidding | N/A | 2024-06-19 |  | N/A | 2024-07-02 | [15 empty] | Government of the Philipppiens | 690590 |  | 690590 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1440 | MEALS AND SNACKS WITH VENUE | PGO | No | Competitive Bidding | N/A | 2024-06-19 |  | N/A | 2024-07-02 | [15 empty] | Government of the Philipppiens | 404700 |  | 404700 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1512 | MEALS AND SNACKS WITH VENUE | PAGRO | No | Competitive Bidding | N/A | 2024-06-19 |  | N/A | 2024-07-02 | [15 empty] | Government of the Philipppiens | 501280 |  | 501280 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1435 | MEALS AND SNACKS WITH VENUE | PHO | No | Competitive Bidding | N/A | 2024-06-19 |  | N/A | 2024-07-02 | [15 empty] | Government of the Philipppiens | 268400 |  | 268400 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1437 | MEALS AND SNACKS | PGO | No | Competitive Bidding | N/A | 2024-06-19 |  | N/A | 2024-07-02 | [15 empty] | Government of the Philipppiens | 455850 |  | 455850 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1390 | JANITORIAL SUPPLIES | PEEMO | No | Competitive Bidding | N/A | 2024-06-24 |  | 2024-07-02 | [16 empty] | Government of the Philipppiens | 1524630 |  | 1524630 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1450 | JANITORIAL SUPPLIES | PDRRMO | No | Competitive Bidding | N/A | 2024-06-24 |  | 2024-07-02 | [16 empty] | Government of the Philipppiens | 1044600 |  | 1044600 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1396 | RICE (WELL MILLED) 50KG/SACK | PEEMO | No | Competitive Bidding | N/A | 2024-06-24 |  | 2024-07-02 | [16 empty] | Government of the Philipppiens | 1083000 |  | 1083000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1478 | MEALS AND SNACKS WITH ACCOMMODATION | PHO | No | Competitive Bidding | N/A | 2024-06-24 |  | 2024-07-02 | [16 empty] | Government of the Philipppiens | 1282500 |  | 1282500 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1479 | MEALS AND SNACKS | PHO | No | Competitive Bidding | N/A | 2024-06-24 |  | 2024-07-02 | [16 empty] | Government of the Philipppiens | 1418400 |  | 1418400 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-1824 | JOB ORDER: SUPPLY, LABOR AND INSTALLATION AT RADIO STATION (PHASE 1) | PAO- IPRD | No | Competitive Bidding | N/A | 2024-06-24 |  | 2024-07-02 | [16 empty] | Government of the Philipppiens | 3655000 |  | 3655000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1348 | COLORED PRINTER AND BINDING MACHINE | PBO | No | Competitive Bidding | 2024-06-18 | 2024-06-24 |  | N/A | 2024-07-02 | [15 empty] | Government of the Philipppiens | 291000 |  | 291000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1438 | FOOD SUPPLIES | PGO | No | Competitive Bidding | 2024-06-18 | 2024-06-24 |  | 2024-07-02 | [16 empty] | Government of the Philipppiens | 3047840 |  | 3047840 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2651 | FOOD SUPPLIES | PSWDO | No | Competitive Bidding | 2024-06-18 | [19 empty] | Government of the Philipppiens | 2903840 |  | 2903840 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3212 | COMPUTER SET WITH COMPLETE ACCESSORIES AND LAPTOP | PGO | No | Competitive Bidding | 2024-06-18 | [19 empty] | Government of the Philipppiens | 123000 |  | 123000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1446 | COMPUTER SET WITH COMPLETE ACCESSORIES AND LAPTOP | PSWDO | No | Competitive Bidding | 2024-06-18 | 2024-06-24 |  | N/A | 2024-07-02 | [15 empty] | Government of the Philipppiens | 162000 |  | 162000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3282 | LIVE AMMUNITIION FOR 9MM CALIBER | PGO-PS | No | Competitive Bidding | 2024-06-18 | [19 empty] | Government of the Philipppiens | 340560 |  | 340560 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1469 | OFFICE EQUIPMENT | PAGRO | No | Competitive Bidding | 2024-06-18 | 2024-06-24 |  | N/A | 2024-07-02 | [15 empty] | Government of the Philipppiens | 131600 |  | 131600 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3252 | MOBILE KITCHEN FACILITY (BRAND NEW) | PDRRMO | No | Competitive Bidding | 2024-06-18 | 2024-06-24 |  | 2024-07-02 | [16 empty] | Government of the Philipppiens | 4482023.84 |  | 4482023.84 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3220 | MINI DUMPTRUCK | PDRRMO | No | Competitive Bidding | 2024-06-18 | 2024-06-24 |  | 2024-07-02 | [16 empty] | Government of the Philipppiens | 2000000 |  | 2000000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3219 | LIVESTOCK VEHICLE (DUMP TRUCK) | PDRRMO | No | Competitive Bidding | 2024-06-18 | 2024-06-24 |  | 2024-07-02 | [16 empty] | Government of the Philipppiens | 3700000 |  | 3700000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1413 | RICE (WELL MILLED) 50KG/SACK | PGO | No | Competitive Bidding | 2024-06-18 | 2024-06-24 |  | 2024-07-02 | [16 empty] | Government of the Philipppiens | 3006000 |  | 3006000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1468 | MEALS AND SNACKS WITH ACCOMMODATION | PHO | No | Competitive Bidding | 2024-06-25 | [19 empty] | Government of the Philipppiens | 364800 |  | 364800 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1473 | SPAREPARTS (HEAVY EQUIPMENT) | PEO | No | Competitive Bidding | 2024-06-25 | [19 empty] | Government of the Philipppiens | 3676700 |  | 3676700 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1453 | MEALS AND SNACKS WITH ACCOMMODATION | PGO | No | Competitive Bidding | 2024-06-25 | [19 empty] | Government of the Philipppiens | 460000 |  | 460000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1487 | LABORATORY SUPPLIES | PDRRMO | No | Competitive Bidding | 2024-06-25 | [19 empty] | Government of the Philipppiens | 422941.6 |  | 422941.6 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3339 | OFFICE EQUIPMENT | PPDO | No | Competitive Bidding | 2024-06-25 | [19 empty] | Government of the Philipppiens | 215900 |  | 215900 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3789 | RICE (WELL-MILLED) 50KG/SACK | PGO | No | Competitive Bidding | 2024-06-25 | [19 empty] | Government of the Philipppiens | 462000 |  | 462000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1542 | FUEL, OIL AND LUBRICANTS | PGSO | No | Competitive Bidding | 2024-06-25 | [19 empty] | Government of the Philipppiens | 2788919.67 |  | 2788919.67 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-1882 | STAINLESS STEEL COFFEE BEAN SORTER | PAGRO | No | Competitive Bidding | 2024-06-25 | [19 empty] | Government of the Philipppiens | 291500 |  | 291500 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3703 | CU 5060I INCLINED CUTTER WITH 720 BAR WORKING PRESSURE, 205MM CUTIING OPENING, 1765KN CUTTING FORCE, 19.8 KG WEIGHT, 820 X 342 X 285 MM DIMENSIONS, 47MM ROUND BAR, EN13204 | PDRRMO | No | Competitive Bidding | 2024-06-25 | [19 empty] | Government of the Philipppiens | 1489000 |  | 1489000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1472 | LUBRICANTS | PEO | No | Competitive Bidding | 2024-06-25 | [19 empty] | Government of the Philipppiens | 2644808 |  | 2644808 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1451 | GROCERY SUPPLIES | PDRRMO | No | Competitive Bidding | 2024-06-25 | [19 empty] | Government of the Philipppiens | 392436 |  | 392436 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2986 | GEMELINA LUMBER OR EQUIVALENT | PEO | No | Competitive Bidding | 2024-06-25 | [19 empty] | Government of the Philipppiens | 859222.98 |  | 859222.98 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1422 | FLUIDS | PEEMO | No | Competitive Bidding | N/A | 2024-06-24 |  | N/A | 2024-07-02 | [15 empty] | Government of the Philipppiens | 425620 |  | 425620 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1387 | LABORATORY SUPPLIES | PEEMO | No | Competitive Bidding | N/A | 2024-06-24 |  | N/A | 2024-07-02 | [15 empty] | Government of the Philipppiens | 976294 |  | 976294 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1474 | VEHICLE SPAREPARTS | PEO | No | Competitive Bidding | N/A | 2024-06-24 |  | N/A | 2024-07-02 | [15 empty] | Government of the Philipppiens | 600600 |  | 600600 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1530 | SPAREPARTS (LIGHT VEHICLE) | PGSO | No | Competitive Bidding | N/A | 2024-06-24 |  | N/A | 2024-07-02 | [15 empty] | Government of the Philipppiens | 920686 |  | 920686 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1527 | SPAREPARTS (HEAVY EQUIPMENT) | PGSO | No | Competitive Bidding | N/A | 2024-06-24 |  | N/A | 2024-07-02 | [15 empty] | Government of the Philipppiens | 547615 |  | 547615 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1510 | SPAREPARTS (HEAVY EQUIPMENT) | PEO | No | Competitive Bidding | N/A | 2024-06-24 |  | N/A | 2024-07-02 | [15 empty] | Government of the Philipppiens | 851481 |  | 851481 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1492 | DRUGS AND MEDICINES | PDRRMO | No | Competitive Bidding | N/A | 2024-06-24 |  | 2024-07-02 | [16 empty] | Government of the Philipppiens | 1545471.8 |  | 1545471.8 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1443 | MEALS AND SNACKS WITH ACCOMMODATION | PSWDO | No | Competitive Bidding | N/A | 2024-06-24 |  | 2024-07-02 | [16 empty] | Government of the Philipppiens | 1150000 |  | 1150000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3207 | MEALS AND SNACKS WITH ACCOMMODATION | PSWDO | No | Competitive Bidding | N/A | 2024-06-24 |  | 2024-07-02 | [16 empty] | Government of the Philipppiens | 1472000 |  | 1472000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2091 | BRAND NEW DUMP TRUCK; IMPORTED COMPLETE BUILT-UP UNIT; FORWARD CONTROL, LEFT HAND DRIVE, 4X4, 6 WHEELER, AIR CONDITIONED | PEO | No | Competitive Bidding | 2024-04-05 | 2024-04-22 |  | 2024-04-30 | 2024-05-14 | 2024-05-14 |  | 2024-05-14 | [12 empty] | Government of the Philipppiens | 14850000 |  | 14850000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2133 | LUMBER | PEO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-18 | [18 empty] | Government of the Philipppiens | 77500 |  | 77500 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2517 | GUITAR AND MICROPHONE | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-05-10 | [18 empty] | Government of the Philipppiens | 13850 |  | 13850 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2231 | GROUP INSURANCE | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-05-10 | [18 empty] | Government of the Philipppiens | 108000 |  | 108000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2410 | Medical Kit | SEF | No | NP-53.9 - Small Value Procurement | 2024-05-14 | 2024-05-17 | [18 empty] | Government of the Philipppiens | 1925 |  | 1925 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2729 | SPAREPARTS(MOTORCYLE) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | 2024-05-28 | 2024-05-30 | [18 empty] | Government of the Philipppiens | 14420 |  | 14420 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2516 | GEMELINA LUMBER OR EQUIVALENT | SEF | No | NP-53.9 - Small Value Procurement | 2024-05-28 | 2024-05-30 | [18 empty] | Government of the Philipppiens | 4136 |  | 4136 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2497 | GEMELINA LUMBER OR EQUIVALENT | SEF | No | NP-53.9 - Small Value Procurement | 2024-05-28 | 2024-05-30 | [18 empty] | Government of the Philipppiens | 33472.49 |  | 33472.49 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3018 | GEMELINA LUMBER OR EQUIVALENT | PDRRMO | No | NP-53.9 - Small Value Procurement | 2024-05-28 | 2024-05-30 | [18 empty] | Government of the Philipppiens | 135187.51 |  | 135187.51 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2999 | GEMELINA LUMBER OR EQUIVALENT | PDRRMO | No | NP-53.9 - Small Value Procurement | 2024-05-28 | 2024-05-30 | [18 empty] | Government of the Philipppiens | 31787.51 |  | 31787.51 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2990 | GEMELINA LUMBER OR EQUIVALENT | PEO | No | NP-53.9 - Small Value Procurement | 2024-05-28 | 2024-05-30 | [18 empty] | Government of the Philipppiens | 13222.98 |  | 13222.98 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2849 | GEMELINA LUMBER OR EQUIVALENT | PEO | No | NP-53.9 - Small Value Procurement | 2024-05-28 | 2024-05-30 | [18 empty] | Government of the Philipppiens | 135187.51 |  | 135187.51 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2140 | OFFICE SUPPLIES | PEO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2024-05-28 | 2024-05-30 | [18 empty] | Government of the Philipppiens | 8885 |  | 8885 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2451 | BLENDER (HEAVY DUTY) | PAGRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-05-30 | [18 empty] | Government of the Philipppiens | 15000 |  | 15000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2731 | UTILITY PLASTIC BOX (20 L) | PACCO | No | NP-53.9 - Small Value Procurement | N/A | 2024-05-30 | [18 empty] | Government of the Philipppiens | 82500 |  | 82500 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2741 | PRINTING | PAO-ADMIN | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 120000 |  | 120000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2859 | WATER DISPENSER | PGSO | No | NP-53.9 - Small Value Procurement | N/A | 2024-05-30 | [18 empty] | Government of the Philipppiens | 60000 |  | 60000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2978 | COMPUTER SUPPLIES/SPAREPARTS | PSWDO | No | NP-53.9 - Small Value Procurement | N/A | 2024-05-30 | [18 empty] | Government of the Philipppiens | 5436 |  | 5436 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2630 | LAPTOP (CLERICAL WORK) | PSWDO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 39000 |  | 39000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2963 | MEALS AND SNACKS | VGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-05 | [18 empty] | Government of the Philipppiens | 99960 |  | 99960 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3076 | GEMELINA LUMBER OR EQUIVALENT | PEO | No | NP-53.9 - Small Value Procurement | 2024-06-11 | 2024-06-14 | [18 empty] | Government of the Philipppiens | 24972.98 |  | 24972.98 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3043 | GEMELINA LUMBER OR EQUIVALENT | PEO | No | NP-53.9 - Small Value Procurement | 2024-06-11 | 2024-06-14 | [18 empty] | Government of the Philipppiens | 55852 |  | 55852 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3672 | MEDICAL KIT | PEO | No | NP-53.9 - Small Value Procurement | 2024-06-11 | 2024-06-14 | [18 empty] | Government of the Philipppiens | 1925 |  | 1925 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3077 | MEDICAL KIT | PEO | No | NP-53.9 - Small Value Procurement | 2024-06-11 | 2024-06-14 | [18 empty] | Government of the Philipppiens | 1925 |  | 1925 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3046 | MEDICAL KIT | PEO | No | NP-53.9 - Small Value Procurement | 2024-06-11 | 2024-06-14 | [18 empty] | Government of the Philipppiens | 1925 |  | 1925 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2880 | OFFICE CHAIR | PICTO | No | NP-53.9 - Small Value Procurement | 2024-06-11 | 2024-06-14 | [18 empty] | Government of the Philipppiens | 108800 |  | 108800 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1377 | COMMUNICATION EQUIPMENT | PICTO | No | NP-53.9 - Small Value Procurement | 2024-06-11 | 2024-06-14 | [18 empty] | Government of the Philipppiens | 191040 |  | 191040 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1381 | COMPUTER SUPPLIES | PICTO | No | NP-53.9 - Small Value Procurement | 2024-06-11 | 2024-06-14 | [18 empty] | Government of the Philipppiens | 81996 |  | 81996 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2557 | CONSTRUCTION MATERIALS | PDRRMO | No | NP-53.9 - Small Value Procurement | 2024-06-11 | 2024-06-14 | [18 empty] | Government of the Philipppiens | 1961 |  | 1961 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2994 | COCO LUMBER OR EQUIVALENT | PDRRMO | No | NP-53.9 - Small Value Procurement | 2024-06-11 | 2024-06-14 | [18 empty] | Government of the Philipppiens | 1152 |  | 1152 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2563 | AIRCON WINDOWS TYPE 2.0 hp | PENRO | No | NP-53.9 - Small Value Procurement | 2024-06-11 | 2024-06-14 | [18 empty] | Government of the Philipppiens | 99000 |  | 99000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2863 | OFFICE SUPPLIES | PTO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2024-06-11 | 2024-06-14 | [18 empty] | Government of the Philipppiens | 14090 |  | 14090 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3065 | CASING, SELF INKING STAMP | PAO-ADMIN | No | NP-53.9 - Small Value Procurement | 2024-06-11 | 2024-06-14 | [18 empty] | Government of the Philipppiens | 682 |  | 682 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2993 | CONSTRUCTION MATERIALS | PEO | No | NP-53.9 - Small Value Procurement | 2024-06-11 | 2024-06-14 | [18 empty] | Government of the Philipppiens | 1961 |  | 1961 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3669 | GEMELINA LUMBER OR EQUIVALENT | PEO | No | NP-53.9 - Small Value Procurement | 2024-06-11 | 2024-06-14 | [18 empty] | Government of the Philipppiens | 2256 |  | 2256 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1526 | CONSTRUCTION MATERIALS | PEO | No | NP-53.9 - Small Value Procurement | 2024-06-11 | 2024-06-14 | [18 empty] | Government of the Philipppiens | 147219 |  | 147219 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3111 | OIL AND LUBRICANTS | PEO | No | NP-53.9 - Small Value Procurement | 2024-06-11 | 2024-06-14 | [18 empty] | Government of the Philipppiens | 38056 |  | 38056 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3021 | SPAREPARTS (LIGHT VEHICLE) | PGO | No | Shopping 52.1(a) - Unforeseen Contingency | 2024-06-11 | 2024-06-28 | [18 empty] | Government of the Philipppiens | 66200 |  | 66200 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3371 | MEALS AND SNACKS | PLO | No | NP-53.9 - Small Value Procurement | 2024-06-14 | 2024-06-17 | [18 empty] | Government of the Philipppiens | 10200 |  | 10200 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1392 | HEMATOLOGY ANALYZER | PEEMO | No | Direct Contracting | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 1976000 |  | 1976000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2977 | MEALS AND SNACKS WITH ACCOMMODATION | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 299000 |  | 299000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2742 | MEALS AND SNACKS WITH ACCOMMODATION | PAO-ADMIN | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 43700 |  | 43700 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2960 | MASSAGE THERAPHY KIT B | PAO-ADMIN | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 15000 |  | 15000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1458 | COMPLETE 14-14-14 FERTILIZER (50KG/BAG) | PENRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 20000 |  | 20000 |  |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1460 | AGRICULTURAL SUPPLIES | PENRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 434950 |  | 434950 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2461 | AQUARIUM (24x12x12 INCHES) | PAGRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 11550 |  | 11550 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1471 | LABORATORY INSTRUMENT | PAGRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 40590 |  | 40590 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1406 | CONSTRUCTION SUPPLIES | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 15070 |  | 15070 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3638 | DRAFTED DURIAN | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 132000 |  | 132000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1511 | SPAREPARTS (FARM MACHINERIES) | PAGRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 32352 |  | 32352 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1370 | MEALS AND SNACKS | PBO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 53105 |  | 53105 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3156 | CABINET MOBILE (BI-STEEL ) 3 DRAWERS | PAO-ADMIN | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 9900 |  | 9900 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3445 | MINERAL WATER (5 GAL.) | PAO-ADMIN | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 2665 |  | 2665 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3358 | MINERAL WATER (5 GAL.) | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 36244 |  | 36244 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3094 | FOOD SUPPLIES | VGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 50032 |  | 50032 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3134 | FUJI DRUM FOR S2520 | PHRMDO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 15000 |  | 15000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3133 | PRINTER HEAD FOR LQ 2190 | PHRMDO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 24000 |  | 24000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3243 | MINERAL WATER (5 GAL.) | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 13940 |  | 13940 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3317 | PAPER BAG 14X8 | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 2625 |  | 2625 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2647 | JANITORIAL SUPPLIES/HOUSEKEEPING | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 25950 |  | 25950 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3456 | GPS, COMPUTER | PENRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 40000 |  | 40000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1404 | OFFICE EQUIPMENT | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 67420 |  | 67420 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3671 | RICE WELL MILLED (50 KG/SACK) | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 90000 |  | 90000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1403 | AGRICULTURAL SUPPLIES | PENRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 66580 |  | 66580 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1523 | RUBBING ALCOHOL (70% ISOPROPHYL) | PENRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 2533 |  | 2533 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3455 | FULL FACED HELMET (HEAVY DUTY | PENRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 22110 |  | 22110 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3308 | FLASH DRIVE (32GB) | PIAO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 3245 |  | 3245 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3310 | JANITORIAL SUPPLIES/HOUSEKEEPING | PIAO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 8988 |  | 8988 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3195 | CALLING CARD (COLORED) AS PER SAMPLE | PAO-ADMIN | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 1400 |  | 1400 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1431 | TARPAULIN-AS PER SAMPLE | PHRMDO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 4256 |  | 4256 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2976 | PLAQUE/TROPHIES/MEDALS | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 72160 |  | 72160 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2975 | POLO SHIRT (AS PER DESIGN) | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 25000 |  | 25000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1497 | JANITORIAL SUPPLIES/HOUSEKEEPING | PAGRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 54055 |  | 54055 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3556 | FULL FACED HELMET WITH BUILT-IN GOGGLES (HEAVY DUTY | PAGRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 11000 |  | 11000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1502 | OFFICE EQUIPMENT | PAGRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 82550 |  | 82550 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1496 | OFFICE EQUIPMENT | PAGRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 26343 |  | 26343 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2788 | DIGITAL CAMERA-AS PER DESIGN | PAGRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 40000 |  | 40000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1439 | OFFICE EQUIPMENT | PAGRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 48146.7 |  | 48146.7 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2688 | MINERAL WATER , 5 GAL | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 1640 |  | 1640 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3186 | COMPUTER SUPPLIES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 15481 |  | 15481 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3281 | DOGFOOD ADULT 20 KG/SACK | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 73260 |  | 73260 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3280 | FUEL, OIL, AND LUBRICANTS | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 37050 |  | 37050 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3078 | TARPAULIN - AS PER DESIGN | PEO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 1792 |  | 1792 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3063 | SPAREPARTS (MOTORCYCLE) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 8115 |  | 8115 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2812 | HANDLE BAR (HONDA XR 150) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 2800 |  | 2800 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2844 | SPAREPARTS (MOTORCYCLE) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 3605 |  | 3605 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2810 | SPAREPARTS (LIGHT VEHICLES) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 1150 |  | 1150 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2792 | SPAREPARTS (MOTORCYCLE) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 5860 |  | 5860 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2809 | SPAREPARTS (MOTORCYCLE) | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 19915 |  | 19915 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2811 | PLUMBING SUPPLIES | PGSO | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 16860 |  | 16860 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2807 | OFFICE SUPPLIES | PHRMDO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 7920 |  | 7920 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1485 | OFFICE SUPPLIES | PDRRMO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 5080 |  | 5080 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1498 | OFFICE SUPPLIES | PAGRO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 25000 |  | 25000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3184 | OFFICE SUPPLIES | PGO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 39532 |  | 39532 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3330 | OFFICE SUPPLIES | PGO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 3192 |  | 3192 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3174 | OFFICE SUPPLIES | PGO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 22600 |  | 22600 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3327 | OFFICE SUPPLIES | PGO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-06-14 | [18 empty] | Government of the Philipppiens | 23307 |  | 23307 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2961 | OFFICE SUPPLIES | VGO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-06-15 | [18 empty] | Government of the Philipppiens | 170005 |  | 170005 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3275 | REPAIR AND MAINTENANCE - MACHINERY AND EQUIPMENT | DDOPH-PANTUKAN | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-06-18 | [18 empty] | Government of the Philipppiens | 50000 |  | 50000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3277 | REPAIR AND MAINTENANCE - BUILDING AND OTHER STRUCTURE | DDOPH-PANTUKAN | No | Shopping 52.1(a) - Unforeseen Contingency | N/A | 2024-06-18 | [18 empty] | Government of the Philipppiens | 50000 |  | 50000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3118 | OFFICE SUPPLIES | PGO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-06-18 | [18 empty] | Government of the Philipppiens | 5327 |  | 5327 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1429 | OFFICE SUPPLIES | PHRMDO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-06-18 | [18 empty] | Government of the Philipppiens | 79995 |  | 79995 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1424 | OFFICE SUPPLIES | PAO-ADMIN | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-06-18 | [18 empty] | Government of the Philipppiens | 166824.5 |  | 166824.5 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1354 | SPAREPARTS (AIRCONDITION) | SPO | No | Direct Contracting | N/A | 2024-06-18 | [18 empty] | Government of the Philipppiens | 141183.3 |  | 141183.3 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3294 | MEALS AND SNACKS | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-18 | [18 empty] | Government of the Philipppiens | 170000 |  | 170000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3295 | MEALS AND SNACKS | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-18 | [18 empty] | Government of the Philipppiens | 197500 |  | 197500 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3213 | MEALS AND SNACKS | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-18 | [18 empty] | Government of the Philipppiens | 95000 |  | 95000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3209 | MEALS AND SNACKS | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-18 | [18 empty] | Government of the Philipppiens | 129000 |  | 129000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1448 | COMPUTER SUPPLIES | PSWDO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-18 | [18 empty] | Government of the Philipppiens | 18340 |  | 18340 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2645 | RICE (WELL-MILLED) 50KG/SACK | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-18 | [18 empty] | Government of the Philipppiens | 144000 |  | 144000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3346 | OFFICE EQUIPMENT | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-18 | [18 empty] | Government of the Philipppiens | 14500 |  | 14500 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3597 | ACK-UP DRONE BATTERY | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-18 | [18 empty] | Government of the Philipppiens | 16500 |  | 16500 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3117 | RAIN COAT (PONCHO TYPE) | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-18 | [18 empty] | Government of the Philipppiens | 1200 |  | 1200 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1504 | COMPUTER SUPPLIES | PASSO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-18 | [18 empty] | Government of the Philipppiens | 125382 |  | 125382 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3328 | PAPER SHREDDER 20 LITERS (HEAVY DUTY) | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-18 | [18 empty] | Government of the Philipppiens | 28000 |  | 28000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1515 | MEALS AND SNACKS | PVO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-18 | [18 empty] | Government of the Philipppiens | 46039 |  | 46039 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1490 | PLUMBING SUPPLIES | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-18 | [18 empty] | Government of the Philipppiens | 22305.6 |  | 22305.6 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3115 | ANIMAL FEEDS | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-18 | [18 empty] | Government of the Philipppiens | 89000 |  | 89000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1459 | MEALS AND SNACKS | PENRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-18 | [18 empty] | Government of the Philipppiens | 44550 |  | 44550 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1338 | MEALS AND SNACKS | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-18 | [18 empty] | Government of the Philipppiens | 57031 |  | 57031 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1432 | COMPUTER SUPPLIES | PDRRMO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-18 | [18 empty] | Government of the Philipppiens | 61458 |  | 61458 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3630 | MEALS AND SNACKS | PAO-ADMIN | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-18 | [18 empty] | Government of the Philipppiens | 51250 |  | 51250 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3639 | OFFICE SUPPLIES | SPO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-06-20 | [18 empty] | Government of the Philipppiens | 6666 |  | 6666 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1401 | OFFICE SUPPLIES | PDRRMO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-06-20 | [18 empty] | Government of the Philipppiens | 12799 |  | 12799 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3536 | OFFICE SUPPLIES | SEF | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-06-20 | [18 empty] | Government of the Philipppiens | 49863.6 |  | 49863.6 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1388 | MEDICAL SUPPLIES | PEEMO | No | Direct Contracting | N/A | 2024-06-20 | [18 empty] | Government of the Philipppiens | 120960 |  | 120960 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1389 | ELECTROLYTES ANALYZER (SODIUM, POTASSIUM, CHLORIDE, CALCIUM) | PEEMO | No | Direct Contracting | N/A | 2024-06-20 | [18 empty] | Government of the Philipppiens | 630375 |  | 630375 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1415 | LABORATORY SUPPLIES/REAGENT | PEEMO | No | Direct Contracting | N/A | 2024-06-20 | [18 empty] | Government of the Philipppiens | 266000 |  | 266000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1394 | LABORATORY SUPPLIES/REAGENT | PEEMO | No | Direct Contracting | N/A | 2024-06-20 | [18 empty] | Government of the Philipppiens | 571850 |  | 571850 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3651 | SPAREPARTS (HEAVY EQUIPMENT) | PEO | No | Direct Contracting | 2024-06-18 | 2024-06-20 | [18 empty] | Government of the Philipppiens | 226948.3 |  | 226948.3 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-1631 | OFFICE SUPPLIES | PGO | No | Direct Contracting | N/A | 2024-06-25 | [18 empty] | Government of the Philipppiens | 9989 |  | 9989 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1483 | OFFICE SUPPLIES | PDRRMO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-06-25 | [18 empty] | Government of the Philipppiens | 97911 |  | 97911 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3044 | OFFICE SUPPLIES | PPDO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-06-25 | [18 empty] | Government of the Philipppiens | 24346 |  | 24346 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1457 | OFFICE SUPPLIES | PPDO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-06-25 | [18 empty] | Government of the Philipppiens | 128144 |  | 128144 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3383 | OFFICE SUPPLIES | PPDO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-06-25 | [18 empty] | Government of the Philipppiens | 15045 |  | 15045 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1462 | DRUGS AND MEDICINES | PHO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-25 | [18 empty] | Government of the Philipppiens | 161853 |  | 161853 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3444 | MEALS AND SNACKS | PAO-ADMIN | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-25 | [18 empty] | Government of the Philipppiens | 104500 |  | 104500 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3203 | MEALS AND SNACKS | PHO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-25 | [18 empty] | Government of the Philipppiens | 105000 |  | 105000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3206 | MEALS AND SNACKS WITH VENUE | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-25 | [18 empty] | Government of the Philipppiens | 76500 |  | 76500 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3412 | TARPAULIN - AS PER DESIGN | PAGRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-25 | [18 empty] | Government of the Philipppiens | 4704 |  | 4704 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1493 | OFFICE DEVICES AND SUPPLIES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-25 | [18 empty] | Government of the Philipppiens | 21460 |  | 21460 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3183 | PAPER SHREDDER (HEAVY DUTY) | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-25 | [18 empty] | Government of the Philipppiens | 7000 |  | 7000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3292 | MOBILE TENT TRAPAL COVER | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-25 | [18 empty] | Government of the Philipppiens | 38000 |  | 38000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1522 | OFFICE DEVICES | PENRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-25 | [18 empty] | Government of the Philipppiens | 41235 |  | 41235 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3781 | JANITORIAL SUPPLIES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-25 | [18 empty] | Government of the Philipppiens | 2121 |  | 2121 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3786 | CORRUGATED G.I. SHEET | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-25 | [18 empty] | Government of the Philipppiens | 297000 |  | 297000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3787 | ENAMEL PAINT | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-25 | [18 empty] | Government of the Philipppiens | 219200 |  | 219200 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3785 | HDPE PIPES | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-25 | [18 empty] | Government of the Philipppiens | 157120 |  | 157120 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1507 | OFFICE DEVICES | PAO-ADMIN | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-25 | [18 empty] | Government of the Philipppiens | 25192 |  | 25192 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3720 | CANNED GOODS | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-25 | [18 empty] | Government of the Philipppiens | 9240 |  | 9240 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1480 | STORAGE BOXES AND TARPAULIN STAND | PHO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-25 | [18 empty] | Government of the Philipppiens | 14800 |  | 14800 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3306 | MEALS AND SNACKS | PIAO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-25 | [18 empty] | Government of the Philipppiens | 20400 |  | 20400 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3744 | NITROGEN TANK | PGSO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-25 | [18 empty] | Government of the Philipppiens | 16000 |  | 16000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3680 | AIRCON MAINTENANCE SUPPLIES | PGSO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-25 | [18 empty] | Government of the Philipppiens | 105096 |  | 105096 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3757 | GARDENING TOOLS AND SUPPLIES | 0 | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-25 | [18 empty] | Government of the Philipppiens | 16056 |  | 16056 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3677 | ELECTRICAL SUPPLIES | PGSO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-25 | [18 empty] | Government of the Philipppiens | 145905 |  | 145905 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3718 | PORTABLE WELDING MACHINE | PGSO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-25 | [18 empty] | Government of the Philipppiens | 13090 |  | 13090 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1509 | GAVEL AND PLAQUES | PAO-ADMIN | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-25 | [18 empty] | Government of the Philipppiens | 12000 |  | 12000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3682 | LAPTOP (CLERICAL WORK) | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-25 | [18 empty] | Government of the Philipppiens | 39000 |  | 39000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1539 | JANITORIAL SUPPLIES | PGSO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-25 | [18 empty] | Government of the Philipppiens | 93995 |  | 93995 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3755 | GARDENING TOOLS AND SUPPLIES | PGSO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-25 | [18 empty] | Government of the Philipppiens | 38149 |  | 38149 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3803 | T-SHIRT JERSEY | PGO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-25 | [18 empty] | Government of the Philipppiens | 134750 |  | 134750 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3656 | MINERAL WATER | PGSO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-25 | [18 empty] | Government of the Philipppiens | 41000 |  | 41000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2558 | COCO LUMBER OR EQUIVALENT | PEO | No | NP-53.9 - Small Value Procurement | 2024-06-25 | 2024-06-28 | [18 empty] | Government of the Philipppiens | 1152 |  | 1152 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1395 | GROCERY SUPPLIES | PEEMO | No | NP-53.9 - Small Value Procurement | 2024-06-25 | 2024-06-28 | [18 empty] | Government of the Philipppiens | 23714 |  | 23714 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3141 | ID SHEETS 10S/PACK | PHRMDO | No | NP-53.9 - Small Value Procurement | 2024-06-25 | 2024-06-28 | [18 empty] | Government of the Philipppiens | 5250 |  | 5250 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3635 | FOOD SUPPLIES | SPO | No | NP-53.9 - Small Value Procurement | 2024-06-25 | 2024-06-28 | [18 empty] | Government of the Philipppiens | 33775 |  | 33775 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1418 | MEDICAL SUPPLIES | PEEMO | No | NP-53.9 - Small Value Procurement | 2024-06-25 | 2024-06-28 | [18 empty] | Government of the Philipppiens | 189695 |  | 189695 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1513 | SPAREPARTS (HEAVY EQUIPMENT POWERKING | PEO | No | Direct Contracting | 2024-06-25 | 2024-06-28 | [18 empty] | Government of the Philipppiens | 1306204.54 |  | 1306204.54 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3809 | SPAREPARTS (LIGHT VEHICLES) | PDRRMO | No | NP-53.9 - Small Value Procurement | 2024-06-25 | 2024-06-28 | [18 empty] | Government of the Philipppiens | 6875 |  | 6875 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1425 | SPAREPARTS (LIGHT VEHICLES) | PEEMO | No | NP-53.9 - Small Value Procurement | 2024-06-25 | 2024-06-28 | [18 empty] | Government of the Philipppiens | 251140 |  | 251140 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1397 | FUEL, OIL, AND LUBRICANTS | PEEMO | No | NP-53.9 - Small Value Procurement | 2024-06-25 | 2024-06-28 | [18 empty] | Government of the Philipppiens | 103520 |  | 103520 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3631 | MEALS AND SNACKS | SPO | No | NP-53.9 - Small Value Procurement | 2024-06-25 | 2024-06-28 | [18 empty] | Government of the Philipppiens | 200000 |  | 200000 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1461 | OFFICE SUPPLIES | PPDO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2024-06-25 | 2024-06-28 | [18 empty] | Government of the Philipppiens | 9526 |  | 9526 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-3493 | OFFICE SUPPLIES | PHO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2024-06-25 | 2024-06-28 | [18 empty] | Government of the Philipppiens | 9560 |  | 9560 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1506 | JANITORIAL SUPPLIES/HOUSEKEEPING | PAO-ADMIN | No | NP-53.9 - Small Value Procurement | 2024-06-25 | 2024-06-28 | [18 empty] | Government of the Philipppiens | 4513 |  | 4513 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1518 | OFFICE SUPPLIES | PICTO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2024-06-25 | 2024-06-28 | [18 empty] | Government of the Philipppiens | 12741 |  | 12741 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1470 | OFFICE SUPPLIES | PGO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 2024-06-25 | 2024-06-28 | [18 empty] | Government of the Philipppiens | 29928 |  | 29928 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2460 | CRAYFISH BREEDER (TRIO-2 FEMALE AND 1 MALE) | PAGRO | No | NP-53.9 - Small Value Procurement | 2024-06-25 | 2024-06-28 | [18 empty] | Government of the Philipppiens | 8250 |  | 8250 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-C1467 | OFFICE SUPPLIES | PHO | No | Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | N/A | 2024-06-28 | [18 empty] | Government of the Philipppiens | 101637 |  | 101637 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
24-2457 | COCO COIR DUST | PAGRO | No | NP-53.9 - Small Value Procurement | N/A | 2024-06-28 | [18 empty] | Government of the Philipppiens | 58350 |  | 58350 | 0 |  |  |  | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | [6 empty] | Ongoing Procurement Process
[33 empty] | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[33 empty] | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[33 empty] | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[33 empty] | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[33 empty] | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[33 empty] | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[33 empty] | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[33 empty] | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[33 empty] | ENGR. MICHAEL C. SALARDA MS. LEONARDA M. NATOR MS. CARMENCITA VALDEZ MS. SORAYA P. VERGARA | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
[25 empty] | Total Allotted Budget of On-going Procurement Activities | 560063080.43 | 21192165.5 | 538870914.93 | 77489220.48 | 19801452.17 | 57687768.31
[7 empty] | #N/A | [17 empty] | Total Allotted Budget of On-going Procurement Activities | 560063080.43 | 21192165.5 | 538870914.93 | 77489220.48 | 19801452.17 | 57687768.31 | 1.613%
|  | Prepared by: | [9 empty] | Reviewed and Checked by: | [16 empty] | Recommending Approval:
|  | MELISSA N. SAMENTAR | [10 empty] | JENES B. MIÑOZA, MPA | [15 empty] | ROLANDO S. SIMENE, DVM, MRDM
|  | Clerk II- BAC Secretariat | [10 empty] | Head-BAC Secretariat | [15 empty] | BAC Chairperson
ROLANDO S. SIMENE, DVM, MRDM
APPROVED BY:
GOV. DOROTHY P. MONTEJO-GONZAGA
Head of the Procuring Entity
Formulas:
Actual Procurement Activities = VLOOKUP(Complete[[#This Row],[Code (PAP)]],[1]Sheet1!$A:$AO,6,FALSE)
Ads/Post of IB = VLOOKUP(Complete[[#This Row],[Code (PAP)]],[1]Sheet1!$A:$AO,7,FALSE)
Eligibility Check = VLOOKUP(Complete[[#This Row],[Code (PAP)]],[1]Sheet1!$A:$AO,10,FALSE)
Sub/Open of Bids = VLOOKUP(Complete[[#This Row],[Code (PAP)]],[1]Sheet1!$A:$AO,11,FALSE)
Notice of Award = VLOOKUP(Complete[[#This Row],[Code (PAP)]],[1]Sheet1!$A:$AO,19,FALSE)
Contract Signing = VLOOKUP(Complete[[#This Row],[Code (PAP)]],[1]Sheet1!$A:$AO,20,FALSE)
Notice to Proceed = VLOOKUP(Complete[[#This Row],[Code (PAP)]],[1]Sheet1!$A:$AO,21,FALSE)
Delivery/ Completion = VLOOKUP(Complete[[#This Row],[Code (PAP)]],[1]Sheet1!$A:$AO,24,FALSE)
Inspection & Acceptance = Complete[[#This Row],[Delivery/ Completion]]
Pre-bid Conf = VLOOKUP(Complete[[#This Row],[Code (PAP)]],[1]Sheet1!$A:$AO,9,FALSE)
Bid Evaluation = VLOOKUP(Complete[[#This Row],[Code (PAP)]],[1]Sheet1!$A:$AO,13,FALSE)
Post Qual = VLOOKUP(Complete[[#This Row],[Code (PAP)]],[1]Sheet1!$A:$AO,14,FALSE)
Date of Receipt of Invitation = VLOOKUP(Complete[[#This Row],[Code (PAP)]],[1]Sheet1!$A:$AO,35,FALSE)
Eligibility Check5 = VLOOKUP(Complete[[#This Row],[Code (PAP)]],[1]Sheet1!$A:$AO,36,FALSE)
Sub/ Open of Bids6 = VLOOKUP(Complete[[#This Row],[Code (PAP)]],[1]Sheet1!$A:$AO,37,FALSE)
Bid Evaluation7 = VLOOKUP(Complete[[#This Row],[Code (PAP)]],[1]Sheet1!$A:$AO,38,FALSE)
Post Qual8 = VLOOKUP(Complete[[#This Row],[Code (PAP)]],[1]Sheet1!$A:$AO,38,FALSE)

## Tool 1-Processing (hidden)
Summary of Information for Processing of IRPP
Indicator 1: % of Processed Procurement Activities vs Planned in terms of amount |  | #REF!
Formula | Value | Remarks
Total Amount of APP as updated | #REF!
Divide by: Total Amount of ABC of procurement activities started | #REF! | ABC of awarded + ABC of on-going procurement projects (less ABC of Failure of Bids)
Indicator 2: Average % of Variance Between Contract Amount vs Approved Budget for the Contract |  | #REF!
Particular | Value | Remarks
Total Amount of ABC of procurement activities started | #REF!
Total Contact Cost | 186274065.54
Total Variance for Each Awarded Procurement Project | #REF! | Column shall be hidden
Divide by Number of Awarded Procurement Projects | 329
Indicator 3. Timeliness on the Conduct of Procurement
|  | Indicator 3.1 Average No. of Days to commence procurement (Pre-Proc to Posting of IB) |  | Indicator 3.2: Average No. of Days to open bid proposals (Posting of IB/ to Opening of Bids) |  | Indicator 3.3: Average Number of Days to Recommend Award (Opening of Bids to Recommend Award) |  | Indicator 3.4: Average Number of Days to Conclude Procurement (Posting of IB to Recommend Award) |  | Indicator 3.5: Average Number of Days to Issue Notice to Proceed (from Issuance of NOA to Issuance of NTP) |  | Indicator 3.6: Accumulated Number of Days for the Procurement Process (Posting of IB to NTP)
Mode of Procurement | Total No. of Activities under subject modality | Total No. of Days from PreProc to IB | Average Days from Pre-Proc to Posting of IB | Total No. of Days from IB to Opening | Average Days from Posting of IB to Opening of Bids | Total No. of Days Opening to Recommend Award) | Average Days from Opening of Bids to Recommend Award | Total No. of Days from Posting of IB to Recommend Award | Average Days from Posting of IB to Recommend Award | Total No. of Days from Issuance of NOA to Issue NTP | Average Days from NOA to NTP | Total No. of Days from Posting of IB to Issue NTP | Average Days from Posting of IB to NTP
Competitive Bidding | 55 | #N/A | #N/A | -543 | #N/A | 230 | 4.1818 | -313 | -5.6909 | 102 | 1.8545 | -275 | -5
Limited Source Bidding | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Direct Contracting | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Repeat Order | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Shopping 52.1(a) - Unforeseen Contingency | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NP-53.1 Two Failed Biddings | 4 | 44 | 11 | 33 | 11 | 1 | 0.25 | 34 | 8.5 | 32 | 8 | 0 | 0
NP-53.2 Emergency Cases | 16 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0.0625 | 8 | 0.5 | 9 | 0.5625
NP-53.3 Take-Over of Contracts | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.4 Adjacent or Contiguous | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.5 Agency-to-Agency | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.7 Highly Technical Consultants | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.8 Defense Cooperation Agreement | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.9 - Small Value Procurement | 323 | 8 | 0.024768 | 55 | 0.024768 | 50 | 0.1548 | 105 | 0.32508 | 87 | 0.26935 | 0 | 0
NP-53.10 Lease of Real Property and Venue | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.11 NGO Participation | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.12 Community Participation | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Emergency Procurement under Bayanihan Act | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Foreign Guidelines - Competitive Bidding | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Foreign Guidelines - Alternative Method | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Total | 536 | #N/A | #N/A | -19.7391 | #N/A | 12.2174 | 0.65523 | -7.5217 | 0.45667 | 9.9565 | 1.5177 | -11.5652 | -0.63393
*formula for days interval for each procurement activity for each indicator are embedded in the PMR.
Indicator 4. Percentage of Amount and Volume by Tender and Award of Procurement Activities per Mode of Procurement
Mode of Procurement | Total No. of Activities | Total Number of Awarded | Total ABC | Total Contract Cost | %Vol of Awarded | %ABC of Awarded | Total Number of Failed | ABC of Failed
Competitive Bidding | 179 | 83 | 135518659.7 | 119496386.01 | 46.37% | 88.18% | 0 | #VALUE!
Limited Source Bidding | 0 | 0 | 0 | 0 |  |  | 0 | #VALUE!
Direct Contracting | 48 | 0 | 0 | 0 | 0% |  | 0 | #VALUE!
Repeat Order | 0 | 0 | 0 | 0 |  |  | 0 | #VALUE!
Shopping 52.1(a) - Unforeseen Contingency | 149 | 0 | 0 | 0 | 0% |  | 0 | #VALUE!
Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 87 | 29 | 3272470.9 | 3215454.55 | 33.33% | 98.26% | 0 | #VALUE!
NP-53.1 Two Failed Biddings | 26 | 21 | 13474945.2 | 8237679 | 80.77% | 61.13% | 0 | #VALUE!
NP-53.2 Emergency Cases | 16 | 16 | 24998616.85 | 24838102.75 | 100% | 99.36% | 0 | #VALUE!
NP-53.3 Take-Over of Contracts | 0 | 0 | 0 | 0 |  |  | 0 | #VALUE!
NP-53.4 Adjacent or Contiguous | 0 | 0 | 0 | 0 |  |  | 0 | #VALUE!
NP-53.5 Agency-to-Agency | 3 | 3 | 6097365 | 4971040.25 | 100% | 81.53% | 0 | #VALUE!
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services | 0 | 0 | 0 | 0 |  |  | 0 | #VALUE!
NP-53.7 Highly Technical Consultants | 0 | 0 | 0 | 0 |  |  | 0 | #VALUE!
NP-53.8 Defense Cooperation Agreement | 0 | 0 | 0 | 0 |  |  | 0 | #VALUE!
NP-53.9 - Small Value Procurement | 715 | 177 | 27029992.41 | 25515402.98 | 24.76% | 94.4% | 0 | #VALUE!
NP-53.10 Lease of Real Property and Venue | 0 | 0 | 0 | 0 |  |  | 0 | #VALUE!
NP-53.11 NGO Participation | 0 | 0 | 0 | 0 |  |  | 0 | #VALUE!
NP-53.12 Community Participation | 0 | 0 | 0 | 0 |  |  | 0 | #VALUE!
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions | 0 | 0 | 0 | 0 |  |  | 0 | #VALUE!
NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets | 0 | 0 | 0 | 0 |  |  | 0 | #VALUE!
Emergency Procurement under Bayanihan Act | 0 | 0 | 0 | 0 |  |  | 0 | #VALUE!
Foreign Guidelines - Competitive Bidding | 0 | 0 | 0 | 0 |  |  | 0 | #VALUE!
Foreign Guidelines - Alternative Method | 0 | 0 | 0 | 0 |  |  | 0 | #VALUE!
Total | 1223 | 329 | 210392050.06 | 210392050.06 | 48.15% | 87.14% | 0 | #VALUE!
Total for Alternative Mode of Procurement | 1044 | 246 | 74873390.36 | 66777679.53 | 48.41% | 86.93% | 0 | #VALUE!
Indicator 5: Accumulated No. of Days for On-going Procurement Activities
Timeline | No. of Procurement Activities | %
Exceeds 180 days | 0 | 0%
Within 91 to 180 days | 0 | 0%
Within 45 to 90 days | 0 | 0%
Within 0 to 44 days | 0 | 0%
Total | 0 | 0%
*Validation shall be provided for the PMR so that the PMO can easily select and determined the total count
Indicator 6. Distribution of On-going, Awarded, and Failed procurement Activities
Status | No. of Procurement Activities | % by No. of Procurement of Activities | ABC Amount of Activities | % by ABC | Contract Cost | Contract/ABC | Variance
Awarded | 0 | 0% | 0 | 0% | 0 | 0% | #DIV/0!
Completed | 530 | 100% | 160861639.62 | 100% | 148778961.98 | 100% | 0.075112
Failed | 0 | 0% | 0 | 0% | 0 | 0% | #DIV/0!
Ongoing | 0 | 0% | 0 | 0% | 0 | 0% | #DIV/0!
Total | 530 | 100% | 160861639.62 | 100% | 148778961.98 | 100% | 0.075112
*Validation shall be provided for the PMR so that the PMO can easily select and determined the total count
Indicator 7a: % of Number of Procurement activities conducted under early procurement |  |  | 0%
Indicator 7b: % of ABC of Procurement activities conducted under early procurement |  |  | 0%
Particular | No. of Procurement Activities | ABC Amount of Activities
Under EPA | 0 | 0
Regular Procurement | 532 | 164613655
Total | 532 | 164613655
Indicator 8a: Percentage of Number of Awarded Contracts under EPA |  |  | 0%
Indicator 8b: Percentage of Contract Cost of EPA against the total ABC under EPA |  |  | 0%
Formula | No. of Procurement Activities | Amount of ABC Procurement Activities | Contract Cost of Procurement Activities | Percentage Variance
Total Contracts Awarded under EPA* | 0 | 0 | 0 | 0%
Total Contracts Completed under EPA* | 0 | 0 | 0 | 0%
Total Failed Bid under EPA* | 0 | 0 | 0 | 0%
Total Ongoing Activities under EPA* | 0 | 0 | #VALUE! | #VALUE!
Total Procurement Activities under EPA | 0 | 0 | #VALUE!
To compute for the total, a separate sheet may be created of the PMO may simply filter the cells to capture the total number.
Indicator 9: Stages where failure of bidding are encountered
Particular | No. of Procurement Activities | Amount of ABC | Vol. % | Amount %
Invitation To Bid | 0 | 0 | 0% | 0%
Pre-bidding Conference | 0 | 0 | 0% | 0%
Opening of Bids | 0 | 0 | 0% | 0%
Bid Evaluation | 0 | 0 | 0% | 0%
Post-Qualification | 0 | 0 | 0% | 0%
BAC Resolution | 0 | 0 | 0% | 0%
Award | 0 | 0 | 0% | 0%
Cancelled | 0 | 0 | 0% | 0%
TOTAL | 0 | 0

## Validation Menu (hidden)
REMARKS | STATUS | STAGE OF PROCUREMENT | Source of Funds
Awarded with issued Notice of Award | Awarded | Invitation To Bid | Government of the Philippines (current year's budget)
Completed | Completed | Pre-bidding Conference | Government of the Philippines (continuing budget)
Ongoing Procurement Process | Failed | Opening of Bids | Government of the Philippines (current year's and continuing budget)
Failed under Section 32.2.1 (a) | Ongoing | Bid Evaluation | Grant by an International Financing Institution
Failed under Section 35.1 (a) |  | Post-Qualification | Loan from an International Financing Institution
Failed under Section 35.1 (b) |  | BAC Resolution
Failed under Section 35.1 (c) |  | Award
Failed under Section 41 (b) |  | Cancelled
Failed under Section 41 (c)
Contract was extended
Contract was renewed
Cancelled
Others, please encode directly on the cell